## Slide 1: Scientific Publications Repository https://wiki.egi.eu/wiki/VT_Scientific_Publications_Repository
Geneviève Romier
Institut des Grilles et du Cloud
France

## Slide 2: Outline
Goal
VT Project and Members
Tasks
Achievements
Next Steps

## Slide 3: Goal
  Improve the process of collecting the
  scientific publications that used EGI resources
  for better demonstrating the
  EGI impact on science

## Slide 4: Current Situation
Scientific publications collected through NGI contacts
Ad hoc processes in place
  Incomplete collection
Researchers may not know that they are using EGI

## Slide 5: Virtual Team Project
VT Scientific Publications Repository
  Start date: 20 June 2012
  End date: early October (foreseen)
Members
  EGI.eu: S. Andreozzi (Leader), C. Gater, S. Coelho
  NGI-DE: T. Antoni, W. Bühler
  NGI-TR: B. Ortakaya
  NGI-FR: G. Romier
  APGI-ASGC: V. Huang

## Slide 6: Tasks
  Collection of current practices from various organisations
  Defining a schema for data to collect and from whom
  Draft policy for citing EGI and for reporting scientific outcome
  Analysis of tools suitable to collect and defining recommendations
  Define a process in alignment with European policies
    e.g.: open access
  Define a communication plan to increase awareness of the new process
  Write report with recommendations for the EGI Council

## Slide 7: Achievements
Collected current practices from 10 organisations
Drafted schema of data to collect
Drafted policy amendment for Grid User AUP
Analysed OpenAIRE and EU open access policies
Found potential partners to develop common solutions
Organised workshop during the EGI TF12 to discuss the proposal

## Slide 8: Next Steps
Workshop @ EGITF12: 18/09 16:00-17:30
  With presentation from the OpenAIRE project
Define a communication plan
Write proposal for EGI Council with recommendations and implementation plan (early October)

## Slide 9: Conclusion
We need to make sure that all scientific publications which work relied on EGI/NGIs are collected
The VT will discuss a set of proposal during the EGITF12 workshop
  18/09 16-17:30
The outcome will be a document with recommendations on policies, processes and tools to improve the current situation