## Slide 1: E-ScienceTalk PMB
E-ScienceTalk PMB Meeting 8
12 June 2012
Telcon

## Slide 2: Open actions
ACTION | DESCRIPTION | RESPONSIBLE | DATE | STATUS
20110127:2 | Establish a plan for working with the Digital Library | Catherine Gater |  | Support for DL will end in May 2012, EC to be informed. OPEN
20110127:4 | Request profile pages based on the SSO database from CESNET | Catherine Gater |  | Using iSGTW RSS feed from people profiles – no permissions issues. CLOSED
20110511:5 | Contact EUDAT and ESFRI cluster projects via PMB contacts | Catherine / PMB | Next PMB | Advanced discussions with BioMedBridges and ENVRI. Will sign after 14 June with CRISP. OPEN
20111018:1 | Allocate checking the trademarking and copyright actions to a member of staff. | Bob Jones | Next PMB | OPEN
20111018:2 | Advertise the translated GridCafé sites to CHAIN, GISELA and SAGrid. | Catherine Gater | Next PMB | Leaflet distributed, participating in a remote GridCast at GISELA/CHAIN meeting. CLOSED
20111018:3 | Send an MoU template or letter of intent to NewWorldGrid via APO. | Catherine Gater | Next PMB | Template sent but no response so far. Active collaboration but MoU not needed OPEN
20120117:2 | Confirm the approval of the ToR and date of next meeting | Catherine Gater | Next PMB | Meeting held on 4 June, ToR approved. CLOSED

## Slide 3: Web stats
Product | Unique visitors | Page views
GridCafe | 300 + 2,511=2,811 | 911 + 19,545 =20,457
e-ScienceCity | 849 | 2,858
GridGuide | 420 | 636
GridCast blog | 2,772 | 5,756
iSGTW | 46,665 | 89,625
RTM | 1,577 | 4,339
e-ScienceTalk | 543 | 1,617
Unique page views and visitors over the last quarter

## Slide 4: WP1: Grid policy outreach
Progress
Stefan Janusz has settled in well with the team – attended EGI TF in Munich, ERF in Hamburg and e-IRG in Copenhagen
Abstract accepted for eChallenges, 17-19 October, full paper submitted on time
Gridcasts held at EGI Community Forum, Munich (March), HealthGrid’12 and ERF Impact Workshop
Briefing on Visualisation issued at the end of April at HealthGrid’12
Next Briefing on Open Data for the end of July
Zara Qadir now working at 0.5 FTE now QMUL is fully staffed
MoU signed with Global Excursion project May 2012
Collaboration agreement received from ERINA+, e-ScienceTalk to be added to the tool

## Slide 5: WP1: Grid policy outreach
Next steps
Feedback collection for D1.4 Annual Report on Impact and Sustainability and D4.4 Annual Report on Feedback and Metrics
Summer intern at QMUL planned for marketing and multimedia work
Future topic ideas for briefings
  Data (with EUDAT) – next briefing?
  International dimension of grids
  eGovernment
  Impact indicators - eNVENTORY
  Digital Agenda for Europe / Horizon 2020
  eInfrastructure governance
  Exascale/future computing
  Costs of cloud, e-infrastructure
  Tech transfer eg openLab, CRISP – next briefing?

## Slide 6: WP2: GridCafé, GridCast, GridGuide
Progress
e-ScienceTalk
  Added partners and MoU collaborations to the website
  ShareThis added to each page, and to individual briefings, figures being tracked
e-ScienceCity / GridCafé
  Volunteer garage area – need to improve traffic to this section, marketing plan needed
  Some graphics still needed to be able to push the site properly – driven by the 3D version
  Moved to individual URLs for each area, now indexed by Google
  Good traffic to and from the Virtual World area
GridCast
  GridCasts held at EGI TF 2012 Munich and HealthGrid.
GridGuide / RTM
  Working on organising the panels more intuitively ie gLite, PANDA, GEANT
  New graphics nearly ready for the data transfers panel
  Working on tracking heavy users of RTM – will approach for feedback
  Possibility that RTM will be added to a Science Museum exhibit on the LHC
Digital Library
  Support for this ending May 2012
  Waiting to resolve iSGTW issues before involving the EC

## Slide 7: WP2: GridCafé, GridCast, GridGuide
Next steps
e-ScienceCity
  New areas in order: supercomputing, networking and data garden – HPC text being developed
  Common areas ie News, In Debate, Multimedia, People Bay being developed
  Need to trademark e-ScienceCity and e-ScienceIsland – URLs all purchased
GridCafé
  Need a handover date for the old and new versions of GridCafe as both sites – site must be functionally complete to do this
GridCast
  Need to have a presence at events outside the usual community to increase the audience and advertise products such as iSGTW.
  Next events are GISELA-CHAIN meeting, Mexico (remote GridCast), Helix-Nebula kick off, XSEDE’12
GridGuide / RTM
  Indexed/tagged content could be displayed through a map interface – similar to the EGI trainers and events map interface at http://www.egi.eu/user-support/ngi_support/
  Need to make sure there is information that is displayed when you click on a site in the RTM that is linked to the GridGuide – added 25 sites to meet the milestone, but additional content needed
  Kinect interface possible, just need to map the controls across – use for SC12?

## Slide 8: WP3: iSGTW
Progress
Miriam Boon leaving on 15 June, Vivian Chang left on 1 June
Working with Indiana University to recruit a US editor to start Sep/Oct when/if NSF funding is confirmed
EU Editor Andrew Purcell starts at CERN on 1 August
ASGC still committed to providing an Asia-Pacific editor, covering with existing staff for now
Staff shortage during late June / early July – Board agreed to hold 2 week break in publishing
CG meeting with Maria Ramalha at ISC’12 PRACE workshop - new comms officer has started
Made contact with Reagan Moore of IRODS/RENCI at ISGC2012 – article published
Subscriptions hovering around 8000 but will now decrease as up 1500 could be defunct addresses – to be auto removed over time.
Continued good impact of social media policy – Twitter followers and Facebook fans continuing to increase, retweets by large accounts eg CERN, NatureNews is driving spikes of traffic to the website (1.6million followers of followers)
Move of the iSGTW site to QMUL took place on 17 May, email to move in 1-2 weeks
iSGTW Advisory Board took place on 4 June
Articles picked up by Wired US, Wired UK, Symmetry and DiscoveryNews

## Slide 9: WP3: iSGTW
Next steps / Issues
Following up with EC on 3rd party funds for website maintenance – 8K identified
Freelancers identified for short term shortage, and possible on going support
New name issue is still outstanding – to be reconsidered when the new US and EU editors are on board
Need to increase subscriber numbers as well as social media numbers
US preview has been consistently late in recent weeks
Need to handover with Miriam and identify the publishing weeks in July

## Slide 10: WP4: Management
Progress
Kirsti Ala-Mutka has left as Project Officer, replaced by Sonia Spasova
Review will be consecutive with eFiscal – 15/16 October, Brussels (rooms booked)
One more e-Concertation meeting possible in Feb-April 2013, Brussels – being rethought by Kostas, ERINA+ want to take this over but logistics seem to stay with us
Weekly meetings continuing with the project team
Travel: CG will attend XSEDE’12 to meet Daphne Siefert-Herron, Indiana for iSGTW and the XSEDE dissemination team
Implementation plan agreed with CRISP, to be agreed after 14 June. Travel costs of 4.5K to be provided by CRISP, possibly more after May 2013
SAGrid and REUNA agreements need to be pursued, as well as DiscovertheCosmos, BioMedBridges, DCH-RP and ENVRI.
F2F at EGICF in Munich held, new team members now all met
Year 2 amendment session submitted, feedback expected in the next few days on the iSGTW costs

## Slide 11: Project issues
WP1-WP4
Ensure a good balance of information and contributions from collaborating projects for e-ScienceBriefings – style may need adjusting
Funding for iSGTW – editorial effort and web support
Lack of sites for GridGuide – end of project milestone a concern
New name for iSGTW and development costs – no funds available
High travel costs for all WPs – funding for 2 people for CRISP meetings
Protection of current and future e-ScienceTalk product names
iSGTW subscriber numbers may not reach the milestone, especially with the removal of the defunct email addresses
Non reporting of effort by partners for Quarterly Reports

## Slide 12: Deliverables and milestones tracking
Complete
In preparation
Overdue
Months | 13 (Sep) | 14 (Oct) | 15 (Nov) | 16 (Dec) | 17 (Jan) | 18 (Feb) | 19 (Mar) | 20 (Apr) | 21 (May) | 22 (Jun) | 23 (Jul) | 24 (Aug)
WP1 Policy |  |  |  |  |  |  |  |  |  |  |  | 
T1.1 Policy |  | D1.2.5 |  |  | D1.2.6 |  |  | D1.2.7 |  |  | D1.2.8 | 
T1.2 Impact |  |  |  |  |  |  |  |  |  |  | D1.4 | 
T1.3 Events |  | MS2 |  |  |  |  |  |  |  |  |  | 
WP2 GridCafé |  |  |  |  |  |  |  |  |  |  |  | 
T2.1 GridCafé | D2.2 |  |  |  |  |  |  |  |  |  |  | 
T2.2 GridGuide |  |  |  |  |  | MS5 |  |  |  |  | D2.3 | 
T2.3 GridCast |  | MS4 |  |  |  | MS4 |  |  |  | MS4 |  | 
WP3 iSGTW |  |  |  |  |  |  |  |  |  |  |  | 
T3.1 Weekly |  |  |  |  | MS8 |  |  |  |  |  |  | D3.5
T3.2 New media |  |  |  |  | MS7 |  |  |  |  |  | MS7 | 
WP4 Mgmt |  |  |  |  |  |  |  |  |  |  |  | 
T4.1 | MS10 |  |  | MS10 |  | MS13 | MS10 |  |  | MS10 |  | D4.4 MS14

## Slide 13: Y2 Effort
Overall effort achieved in Q7 in PMs: per work package
Overall effort achieved in Q7 in PMs: per partner
Workpackage | Total plan (PM) | Linear Plan | Q5 % achieved | Q6 % achieved | Q7 % achieved
WP1 | 46 | 4.2 | 104% | 50% | 92%
WP2 | 64 | 5.8 | 90% | 61% | 63%
WP3 | 52 | 4.7 | 122% | 78% | 76%
WP4-M | 17 | 1.5 | 111% | 71% | 83%
WP2-UNF | 8 | 0.7 | 0% | 0% | 0%
WP4-UNF | 5 | 0.5 | 40% | 12% | 0%
Total | 192 | 17.5 | 98% | 60% | 70%
Partner | Total plan (PM) | Linear Plan | Q5 % achieved | Q6 % achieved | Q7% achieved
CERN | 67 | 6.1 | 105% | 78% | 67%
APO | 34 | 3.1 | 87% | 61% | 63%
QMUL | 47 | 4.3 | 107% | 60% | 117%
IMPERIAL | 26 | 2.4 | 70% | 3% | 0%
EGI.eu | 18 | 1.6 | 112% | 71% | 78%
Total | 192 | 17.5 | 98% | 60% | 70%
Under reporting of effort across all partners!
Timesheets must be filled in on time

## Slide 14
CRISP – willing to pay for e-ScienceTalk team services post May 2013 (but will not fund core work)
Support from other ESFRI projects is unclear
Freelancers for iSGTW – ongoing contracts for content on EU side
US funding for the iSGTW editor is potentially for 5 years
No cost extension of e-ScienceTalk – underspending partners?
FP7-SCIENCE-IN-SOCIETY-2013 project call in July 2012
Horizon2020 – earliest date for call to open is 1 January 2014
Sustainability