## Sheet1
| SA1 task | Area | Description | Criticality 1 (no) - 5 (high) | Mitigation
Support | SA1.7 | Specialized middleware support | Availability of 3rd level support units. Some of the workflows might need to be adapted in case technology specific support units are not operating anymore. The technology helpdesk will likely continue, but possibly used by a subset of TPs. Different levels of support depending on the PT: Full support (ARC), Specific communities and best effort for other communities (all CERN products for WLCG - BDII, FTS; INFN, CESNET NIKHEF products (ARGUS, CREAM, WMS and VOMS, gridsite, LB, glexec, CANL) and dCache, Discontinued (LFC), Best effort (UNICORE), Commercial support (Hydra and Security Token Service - STS), community project (DPM). Level of support of GRAM-BES, GridSafe from IGE to be understood | 5 | MITIGATIONs: rebalancing of effort within TSA1.7 to strenghten support of products that do not get external support, leveraging on community support for technologies with a lot expertise in the community. ACTIONs: (1) Verify willingness to provide 3rd level support in the future for each PT, in case of discontinuation of some SUs. (2) collect information about needed IGE products and negotiate maintenance and support.
Security | SA1.2 | Software Vulnerability Reporting and Assessment | EGI Software Vulnerability Issue Handling Procedure : coordinated release and exchange of information about vulnerabilities, agreed response time by TP if a potential vulnerability is found in the software they supply regulated by a SLA. TP participation to Risk Assment activities (RAT) | 5 | MITIGATIONs: New procedures for vulnerability handling: Negotiation of individual SLAs with TPs (and possible different response time depending on the TP) - coordination problem. ACTION: contact PTs to understand their commttment to support in case of high risk/critical vulnerabilities
Support | SA1.7 | Discontinuation of support/fees for support services | Products are retired or a fee for service is required. LFC (Local File Catalogue support) supported until 2013-2014. BDII is going to be supported by CERN only for WLCG purposes (no plans to phase it out yet, but WLCG usage of information system may change, and consequently the BDII), no clear long-term evolution plans HYDRA and STS fees for support service have an impact on BIOMED | 5 | MITIGATIONs: Seek for catalogue alternative technical solutions (will require adaptations to other services), collaboration with EUDAT under investigation. Evolve products into community projects (as DPM). Pay a fee for support services. ACTIONs: (1) Request more information about HYDRA/STS support policy. (2) Information discovery workshop at TF12.
Security | SA1.2 | Security middleware | All essential security middleware continues to be supported (and developed where necessary). Common Authentication Library: released with EMI 2 but still to be integrated with services. ARGUS and VOMS: Baseline support of components required by the current Italian User Communities and their international collaborative efforts. For future major developments rely on EC funding. no STS yet released: Issues short-lived X.509 certificates based on authentication at a Shibboleth Identity Provider – thus linking AAI and Grid infrastructures X.509 certificate issuing process automated and invisible to the end-user. Will be extended within EMI into a Security Token Service, capable of handling multiple security token types (X.509, SAML, Kerberos, ...) | 4 | ACTION. Clarify support conditions of STS with EMI
Tools | SA1.4 | SAM | Maintenance of monitoring probes in order to provide availability of the EGI infrastructure. We assume that support for existing probes will be continued by parties continuing maintenance of respective middleware components. EMI document states that "EMI-NAGIOS" will be supported by WLCG and ARC-related probes by Nordugrid. | 4 | ACTIONS. (1) Check release process for Nagios probes were still maintained. (2) Get more information about IGE and UNICORE probes.
Accouting | SA1.5 | APEL repository/IGE | IGE accounting plan is that GridSafe will send data to APEL. Gridsafe is also used by PRACE. | 4 | ACTION. Notify IGE about the need to continue the support of GridSafe as a mechanism to integrate GLOBUS and PRACE accounting.
Quality assurance | SA1/SA2 | Integration and Interoperability | No interoperation nor interoperability tests performed by the several technology providers. EMI test up to a certain level the integration between different components, also the testing with new Globus releases. Also does some level of interoperability between different services. | 4 | MITIGATION. EGI performs more extensive tests of interoperation and interoperability between different components in “Verification” and “Staged Rollout”. More effort is needed. Support calendars and policies to be discussed individually with the various PTs.
RFC | SA1.1 | Evolution | Requirements. New developments of various products will be ensured only in case replacement funding will be procured. This affects: CANL, gridsite, LB (CESNET); MPI (CSIC); CREAM, gLite-cluster, StoRM, VOMS/VOMSAdmin, WMSm WNoDES (INFN). Some PTs are willing to support a subset of relevant communities (e.g. CERN for WLCG) | 3 | MITIGATION. In case of new features requested are not endorsed, an alternative product could be available (most likly this will be possible in few cases and replacement of an existing product will require integration/developments from other supported products). Investigate support fees.
Quality assurance | SA1/SA2 | Certification | Certification by TP. EMI and IGE perform certification of each component, they produce and publish reports about the certification. Will PTs continue to do own certification? | 2 | MITIGATION. EGI performs extra testing activities
Tools | SA1.4 | Messaging | EMI provisioning of messaging libraries for WLCG by CERN. As CERN participates in running production message brokers, we expect that libraries will be kept compatible (at least in the medium term) with broker technology used. | 2 | NA
Accouting | SA1.5 | Apel repository/EMI | APEL - The bulk of accounting data received originates from CREAM CEs so the completeness of future data is strongly connected with the future of the CREAM/BLAH family (baseline support is guaranteed but no new developments). While the part of the parser that deals directly with the batch system itself is not dependent on the CE, the part that retrieves the user and VO identity information relies on BLAH as used by CREAM. The EMI sustainability plan suggests that CREAM/BLAH will continue to be supported, so at first glance there is no great risk. However APEL (and other site accounting systems) will have to be adapted if other submission interfaces will emerge. Support of accounting for cloud and virtualization is an internal EGI effort. | 2 | MITIGATION. Evolve APEL to new submission interfaces that may emerge in the future.
Software Provisioning | SA2 | Repositories | Multiple source repositories. At the end of those projects, SW components will be distributed through EPEL (for RHEL compatible OS’s) and Debian repositories. (In fact they are already doing so for all components in the case of IGE, and a fraction of components in the case of EMI). It may happen, that more repositories are used for certain components. Annuncement of new releases: EMI – Announces a new release, EGI people are in their announcement mail lists. The release notes and list of packages belonging to a given component is known and published in EMI web locations. IGE – submits new releases into the EGI SW provisioning process, the list of packages and release notes are part of the submission. | 2 | ACTIONS. Since EGI SW provisioning process starts when packages are pulled from EMI and IGE known repositories, then it should be a matter of changing the repositories locations in order to point the EGI tools to fetch the packages from the new repositories. Assumption: All repository locations are known to EGI, as well as its structure. (1) Request all technology providers, to provide information of the new location of web pages. (2) Ask to provide and publish the list of packages of each new release.
Tools | SA1.4 | Operations Portal | Operations Portal uses information system to retrieve information about sites and services. EMI plans state that BDII will be supported in the long term so we expect that Operations Portal will be able to use it as source of information, but may be adapted to changes in the information discovery services. | 1 | NA
Tools | SA1.4 | Metrics Portal | Operations Portal uses information system to retrieve information about sites and services. EMI plans state that BDII will be supported in the long term so we expect that Operations Portal will be able to use it as source of information, but may be adapted to changes in the information discovery services. | 1 | NA
Helpdesk | SA1.6 | GGUS and technology helpdesk | No impact on GGUS sofware, as it is independently provided through JRA1. | 1 | NA
Support | SA1.7 | Network, Grid oversight (COD and ROD) | No impact | 1 | NA
Accouting | SA1.5 | Accounting portal | CESGA Portal relies heavily on other operational tools (ops portal, GOCDB, APEL) but has a weaker dependence on VOMS which it uses to obtain access control lists for VO members and managers (other dependencies to be checked with the team). No other middleware is involved (needs confirmation) so it is not otherwise affected by middleware availability. | 1 | NA
Availability | SA1.8 | Availabilty Reports, Core services and catch all services | No impact | 1 | NA