## Slide 1: CB – 20/9/12

## Slide 2: Agenda
Welcome
Project Status
Amendment #2
Review Report
AOB

## Slide 3: Project Status

## Slide 4: Project Status PQ9
Planning for EGITF 2012
  It seems to have worked so far!
EGI-InSPIRE 2nd Review of PY2
  https://indico.egi.eu/indico/conferenceDisplay.py?confId=1046
  Feedback to be discussed later
Discovery of a Higgs like particle announced

## Slide 5: Project Effort PQ9
Work Package | Worked PM Funded | Committed PM | Achieved PQ9 PM % | Achieved PM (YEAR 2) % | Achieved PM (YEAR1) %
WP1 | 20.6 | 21.1 | 98% | 99% | 77%
WP2 | 86.7 | 112.9 | 77% | 89% | 80%
WP3 | 0 | 0 | 0 | 128% | 86%
WP4 | 298.8 | 310.2 | 96% | 105% | 98%
WP5 | 27.8 | 48.1 | 58% | 92% | 81%
WP6 | 49.1 | 60.4 | 81% | 98% | 102%
WP7 | 20.1 | 21.5 | 93% | 87% | 76%
Total | 503.1 | 574.2 | 88% | 101% | 93%
Low effort overall due to the summer
Low effort inNA2 due to NILs related NGI activity
Low effort in SA2 due to new cloud task

## Slide 6: PY2 Cost Statements
Almost all clarifications sent last week
  Few travels info (meeting place and date) have not been forwarded by partners
Hopefully, will not prevent the cost session being submitted
  Need to wait for EC contact to return from holiday

## Slide 7: Communications
Impact of the new website was assessed for MS231 Review of the website.
800,000 page views in the past 12 months, most popular pages are Indico (the event planning website), the about section and news and events.
Booths sent to HealthGrid/IWSG-Life 2012 event in Amsterdam, the iPv6 World Launch Day in Amsterdam, and ISC2012, Hamburg.
Articles published in PanEuropeanNetworks: Science & Technology, iSGTW, the e-IRG newsletter and e-Research South.
Press release on the sonification of the CERN Higgs data released by DANTE, mentioning EGI, picked up by Bloomberg BusinessWeek, Discovery News and Wired.
Communications team participated in the ENVRI VT, Scientific publications VT and NGI Compendium VT.

## Slide 8: Strategy and Policy
Collaborations:
  Signed new MoU with UVACSE (Technology Provider)
  Progress in drafting the DANTE MoU
  Finalised the new tool to track milestones execution with collaborating partners
Deliverables and Milestones
  D2.13 EGI Sustainability Plan delivered
  D2.18 Evolving the EGI Business Models delivered
VT Scientific Publications Repository
  Preparation of the activities, kick-off, run four phone meetings, collected best practices, draft policies, discussion around processes and tools, planned session for EGI TF12
Global Tasks cost analysis for PY2
EGI Glossary:
  First version approved and integrated in the main EGI website

## Slide 9: Strategy and Policy
Reports
  EGI Compendium 2011: delivered preliminary analysis to the EGI Council
  Leaflet about Structural Funds: delivered to the EGI Council
  MoU Annual Report 2011-2012: delivered to the EGI Council
  Drafting of the ERIC report to support the discussion within the EGI Council
  eChallenges: camera ready version of the paper delivered to conf. organisers
  2 blog posts
  1 article for the EGI Inspired newsletter
  Contribution of the security chapter for the e-IRG Blue Paper on Data Management
Surveys:
  ERINA+, IPv6, eScienceTalk
Policy Groups
  Secretariat support for TCB; UCB; SCG; SPG
  Attended EUGridPMA and TAGPMA as relying party
  Continued work on “Security for Collaborating Infrastructures” to build a standard framework for security policy and trust for interoperation
  Attended workshop on Identity Management for Research
  Participated in Security Risk Assessment group and helped prepare report before 2nd EGI-InSPIRE review

## Slide 10: Community Outreach
Planning and preparation for EGITF12
  EGI Operations, Resource Infrastructure Services, Virtualised Resources: challenges and opportunities, Virtual Research Environments, Community and Co-ordination
Federated Cloud Task Force PlugFest held at the Science Park
  Developers present and five user communities represented – teleconferencing facilities used
UCB convened for a telcon on 7th May 2012
Articles have been written to reach out to communities:
  EPOS (European Plate Observing System) Newsletter
  e-Research South Newsletter article published in UK on EGI and the UK
  Inspired – article produced on the Federated Cloud Task Force

## Slide 11: Community Outreach
VERCE (Virtual Earthquake and seismology Research Community in Europe)
  Discussions started with VERCE on integration with EGI of their plans for a data-intensive e-science environment to support Earth Science research projects such as EPOS
Paper accepted for the Digital Research 2012 conference, Oxford
  'EGI Federated Cloud Taskforce: delivering innovative distributed computing solutions for diverse research communities from proof of concept prototypes to a blueprint for implementation’
Supported the International Workshop on Science Gateways for Life Sciences (IWSG-Life)
  EGI.eu had a display table for promotional activities and co-led an workshop on Science Gateways. Discussions are underway to co-locate the next event with the EGICF 2013 in Manchester with a broader role across all disciplines in terms of Science Gateways.
Astronomy and Astrophysics Community Group (Astro-CG)
  OGF meeting in Delft. EGI involved in the inaugural meeting for this reactivated group
Structural Biology ESFRI project, INSTRUCT
  Conference in Abingdon, UK, 21-23 May2012 of which EGI’s VRC WeNMR was a participant. Presentation delivered on EGI.

## Slide 12: Technical Outreach to New Communities
Support 6 VTs, two of which started, another 2 finished during PQ9
Defined structure for VRE track of EGI TF, invite presenters
Hosting Jelena Tamuliene from the Lithuanian NGI working in the ‘Application expert’ secondment position at EGI.eu. Jelena reviews and helps us improve computational chemistry services
One requirement addressed through TCB, two resubmitted with additional details
Started the setup of support processes and documents for users of the EGI Federated Cloud: http://go.egi.eu/cloud
Bring one use case to the EGI FedCloud from ‘The Milky Way: Stars, Gas, Dust and Magnetic Fields in 3D’ workshop
EGI presentation and discussions at the ‘4th Federated Identity Management’ workshop
Three training & outreach slideshows in Training Marketplace
Technical input for EGI discussion @ Workshop on Science Gateways for Life Sciences
  2 blog posts, 1 newsletter article, numerous facebook and twitter updates

## Slide 13: Technical Outreach to New Communities
AppDB: http://appdb.egi.eu
  REST API that supports authenticated writes and updates of the database
  Broken link detector and notification system
  Expiration watcher system, excluding out of date entries from searches
  Mechanism to classify software entries into any number of categories (not just Tools and Applications). This will be used in PQ10
  Outreach tool for managers to send emails to owners of specific software entries
Customer Relationship Management system (CRM): http://crm.egi.eu
  Improve usability and robustness
  Setup a CRM dashboard to monitor and report activities per NGI
  Ability to trace user activities with migrating to vTiger 5.4.0 (to be completed in PQ10)
Training Marketplace: http://training.egi.eu
  Webinar about the tool (to be repeated in the autumn)
  New filter to display local events. Available through a new gadget
  Script to monitor usage of central instance and gadget instances
  Ability to capture number of trainee days (= number of attendees * length of training event)
  Correct resizing of events within iFrame

## Slide 14: SA1
Main documents
  MS418 Operational Level Agreements (OLAs) within the EGI production infrastructure
  Security Threat Risk Assessment report
  Action plan for EGI PKI SHA-2 migration
Preparation of Operations Track programme at TF12
Sustainability
  Survey on sustainability of NGI and EGI.eu opened in August 2012
Infrastructure
  Improving performance of authoritative list of top-BDII services per NGI
  Integration of Ukraine. No progress with SAGrid integration
  Improving performance of Armenia and FYROM
Availability
  Number of sites below 75%/70% targets in May/June/July: 33/40/30
  New top-BDII NGI Availability/Reliability statistics and RC statistics now provided by the Operations Portal

## Slide 15: SA1
Technology deployment and integration
  Staged rollout of 57 products (for UMD 2.0.0 and 2.1.0), 2 rejected, 75 tests in total, 65 EA teams (56 in PQ7)
  Streamlining of staged rollout procedure
  Improved integration of UNICORE tests, completed integration of Desktop Grids and QosCosGrid middleware into SAM
  Integration of GLOBUS and UNICORE services into a unified information discovery system in progress
  Helpdesk and accounting integration between EGI and PRACE under discussion
Tools
  GOCDB read-write portal decommissioned on July 31st and replaced by a single read-write version at https://goc.egi.eu/portal
  Two new Operations Portal versions rolled to production (2.9.4 and 2.9.5), new availability dashboard!
  SAM Update 17 and 17.1 staged rollout. SAM central instance for operations tools monitoring under provisioning
Accounting
  CERN and OSG moved their production accounting infrastructure to the new Python-based STOMP Secure Messaging infrastructure (SSM)

## Slide 16: SA1
Security: 2 security incidents handled, 2 security alerts (one critical), 4 vulnerability reports, 4 SVG advisories
  Security threat risk assessment report finalized
  Running of SSC5 at NGI level, preparation of SSC6 in collaboration with CMS
  Discussion of a unsupported software retirement policy
  Handover of EGI CSIRT and TSA1.2 coordination duties
Support
  ROD performance index measuring the quality of NGI support services, monitored monthly
  On-going IPv6 testing in collaboration with HEPIX and EMI
  Implementation plan of a unified support activity merging TPM (SA1) and DMSU (SA2)
GGUS and Technology Helpdesk
  First release of GGUS report generator
  New interface to NGI_FRANCE helpdesk system under preparation
  Two new xGUS instances in production
Stephen Burke secondment to EGI.eu to work on GLUE 2 activities

## Slide 17: SA2
Release of UMD 2
  Components from EMI
  Further components coming in from IGE
Establishment of Federated Cloud Task
  Additional partners coming on board

## Slide 18: SA3
HEP Dashboard Application
  “The accelerator – the experiments – Grid computing”
Data Management Monitoring
  WLCG Transfer Dashboard validated & in production.
Life Science Dashboard Design
  VRC-wide storage utilisation now monitored.
HammerCloud
  Code optimisation → 20 - 3,000% speed improvement of web views.
Ganga
  Code refactoring → Experiment-neutral Gaudi framework.
Hydra
  New partner provisioned a Hydra Key Store.
GReIC
  DashboardDB updated: registry & monitoring gadgets improved.
Workflows & Schedulers
  New release of SOMA2 (v1.4.1: Aluminium).

## Slide 19: SA3
MPI
  Support unit is now active.
HEP: LHCb Dirac
  Data popularity service in production & being evaluated.
HEP: CRAB Client
  New, CouchDB-based monitoring system.
HEP: Persistency Framework
  Development continues; new CORAL & COOL releases.
HEP: ATLAS & CMS Common Analysis Framework
  Feasibility study reported: no “showstoppers” identified.
Life Sciences
  Investigating new procedures & tools.
Astronomy & Astrophysics
  Focused on long-term sustainability.
Earth Sciences
  Improvements to data-transfer tool “Synchro-data” & “gsearch” utility.

## Slide 20: JRA1
Operations Portal
  2 major releases have been delivered
    alarm flapping detection implemented for the security and VO dashboards
    collection of VO shifters authorized to post "Team" Tickets
  the availability / reliability module added to the portal
    Currently this module provides information about availability / reliability of Top BDII and also sites.
      different granularities: a monthly summary , or daily values ( for sites) and hourly values (for Top Bdii)
      results are also available in 2 different chart formats.
GOCDB
  GOCDB 4.3 was released (end of PQ8)
    This included finer grained role/permissions model and support for Service Groups (i.e. Virtual Sites)
  Engaged with EUDAT representatives to review their requirements and to assess the potential for GOCDB deployment and customisation within EUDAT
  New service type additions.
  The GOCDB service was unified into a single portal instance (replacing the previous two separate portal deployments;
Metrics Portal
  New metrics for the SA2, NA2, SA1 and NA3 tasks
    These metrics will also promote the development of connectors for new information sources.

## Slide 21: JRA1
EGI Helpdesk (GGUS)
  The first version of the GGUS report generator was released in June 2012.
  Various new support units were introduced during the last quarter: REBUS (2nd level support), EMI Common, EMI Common Data Library and LHC Experiment Dashboard (3rd level support).
  The GGUS web interface was extended with extra information fields in the ticket body to track which middleware product is affected by the reported incident.
  Tests were implemented to probe the interface between GGUS and the remote helpdesk systems. These tests are executed before each GGUS release.
  The interface with the ticketing system of NGI_FRANCE (OTRS) is being set-up and will be rolled to production in September.
  The implementation work on the GGUS-SNOW interface of CERN was completed.
  New xGUS instances were rolled to production: one instance for the French national VO vo.france-grilles.fr which is a catch-all VO for multiple communities in France, and one instance for NGI_SI
Accounting Repository
  Working with EMI to simplify the SSM protocol.
  Designing migration strategy for APEL central database.
  Creating a prototype consumer for CAR records in XML document format, rather than our own keyword format.
  Continued to activity on cloud accounting records as part of Federated Cloud

## Slide 22: JRA1
SAM
  SAM U17 and 17.1 in Staged Rollout
    The main objective of this update was the deployment in production of the new POEM component, which substitutes the old MDDB
    DesktopGrid probes were integrated into SAM
    UNICORE probes are distributed as part of SAM and manual installation is not needed.
  SAM U18 (internal) and U19 (not yet released) developed:
    the logging and monitoring of the SAM database improved
    Integration of QCG/MAPPER probes
Accounting Portal
  miscellaneous query improvement and index optimization
  better HTML output
  testing with several browsers
  tweaks on the graph engine
  preliminary work prior to the implementation of new interNGI usage features.
Messaging
  Implemented the credential synchronization system, which is responsible to keep user and group records synced between the brokers of the same broker network. It is deployed and tested in TEST broker network.
  Created a new metapackage to ease the installation procedure

## Slide 23: Milestones and deliverables
Id. | Title | DocDB URL
D2.16 | EGI-InSPIRE Presentation | https://documents.egi.eu/document/1145
MS228 | Marketing and Communication Handbook | https://documents.egi.eu/document/1160
MS511 | Deployed Middleware Support Unit Operations Procedures | https://documents.egi.eu/document/1134
MS512 | Software Provisioning Process | https://documents.egi.eu/document/1135
MS616 | Services for High Energy Physics | https://documents.egi.eu/document/747
MS617 | Services for the Life Science Community | https://documents.egi.eu/document/1289

## Slide 24: Amendment #2

## Slide 25: DoW Change #2
Merger of SA2.5 and SA1.7
Establishing SA2.6 for federated cloud
Moving coordination of document
Moving coordination of interoperation
New changes (slides to follow)
  Moving INFN effort to CERN
  TCD leaving the project
  Russian JRU changes

## Slide 26: INFN Changes
INFN costs at CERN in SA3
  PY1: Staff recruitment. No effort recorded
  PY2: Staff in place. Effort recorded
    Costs not allowed  effectively subcontracting
Propose transferring to CERN:
  24PM for PY3: EUR130K
  Equivalent to effort at INFN costs of:
    20PMs (PY2) @ 40% (EUR 59K)
    24 PMs (PY3) @ 40% (EUR 71K)

## Slide 27: TCD
TCD has announced it is leaving:
  EGI
  EGI-InSPIRE
Provided a formal letter
Probably process in separate amendment

## Slide 28: Russian JRU
Issue
  Needed to restructure to allow redistribution of funds
  No funds distributed in PY1 & PY2 due to local tax rules potentially adding VAT
Final documents arrived Tuesday this week
Will be processed by EC next week
Changes made in with Amendment #2

## Slide 29: EC Review

## Slide 30: EC Review
Issues that need a response now
  Draft letters to the EC from the PMB & EGI.eu
  List of major factual errors in the report
Strategic Issues for the EGI Council
Technical Issues for the EGI-InSPIRE AMB
  Cross-cutting Task & Activity issues
  Individual independent Task/Activity issues

## Slide 31: Significant Issues
For the EGI-InSPIRE project
  Experts have gone beyond their mandate
  Experts use two different DoWs for their comments
  EGI-InSPIRE boards need to be replaced
  User representation is provided through EAC
For the EGI.eu Executive Board
  EGI.eu is a foundation and is legal
  ERIC is still on the agenda for discussion

## Slide 32: Strategic Issues for EGI
Use a scientific board to review applications?
Do NGIs need to stop non-local use?
Prepare for a pay-for-use by users model?
Should EGI change its name?
Review split of work between EGI.eu & NGIs?
Will NGIs provide a price for their resources?
Should NILs be employed directly by EGI.eu
EGI.eu expand projects: RTD & portals

## Slide 33: Key Technical Issues
VO specific availability & reliability metrics
  Kill this availability & reliability discussion!
  Probably shows 95% of VOs 100% A & R
Integrated NA2 tasks
  Strategy (with metrics) for outreach
Review the Activity & Strategic Metrics
Provide thought experiment on pay-for-use
  Which NGIs? How much? Through EGI.eu?

## Slide 34: Other Discussions
Changing EC e-Infrastructure landscape
  “Keeping the status quo is not an option”
EC believe in a more market driven ERA
  Provide an additional overhead to buy services
  Improve efficiency and bring in new SMEs
ERA Communication
  “A Reinforced European Research Area Partnership for Excellence and Growth”

## Slide 35: AOB