## Slide 1
www.e-sciencetalk.eu
WP4: Project and Consortium Management
Catherine Gater
e-ScienceTalk Project Coordinator, EGI.eu

## Slide 2: Content
Consumption of effort and resources
Deliverables and milestones
Project metrics
WP4 achievements
Project issues
Summary

## Slide 3
www.e-sciencetalk.eu
Consumption of effort and resources

## Slide 4: WP overview
WP No. | Work package title | Type of activity | Lead partic no. | Lead partic. short name | Personmonths
1 | Policy, impact and sustainability | SUPP | 2 | QMUL | 46
2 | GridCafé, GridCast and GridGuide | SUPP | 3 | APO | 72
3 | International Science Grid This Week | SUPP | 5 | CERN | 52
4 | Management | MGT | 1 | EGI.eu | 22
 | TOTAL |  |  |  | 192

## Slide 5: Y2 achieved effort
Overall effort achieved in Q5-8 in PMs: per work package
Workpackage | Total plan (PM) | Q5 % achieved | Q6 % achieved | Q7 % achieved | Q8 % achieved | Total Y2 (PM) | YEAR 2 % achieved | YEAR 1 % achieved
WP1 | 46 | 104% | 50% | 99% | 96% | 15.34 | 92% | 92%
WP2 | 64 | 90% | 61% | 68% | 68% | 20.82 | 89% | 75%
WP3 | 52 | 122% | 78% | 79% | 84% | 17.68 | 93% | 121%
WP4-M | 17 | 111% | 71% | 83% | 79% | 5.24 | 85% | 113%
WP2-UNF | 8 | 0% | 0% | 0% | 0% | 0 | 0% | 0%
WP4-UNF | 5 | 40% | 12% | 36% | 18% | 0.7 | 39% | 18%
Total | 192 | 98% | 60% | 76% | 76% | 59.77 | 86% | 90%
Overall at 86% of planned effort for WP1-4.
Funded effort at 89.8% of planned effort for WP1-4.
Unfunded effort under-reported in Year 2 but activities are ongoing.
Under reporting in WP2 at 89% - no impact on M&D, improvement on PY1
Under reporting in WP3 and WP4 121% to balance against PY1
Slight over reporting in the management activity due to project start up.
Rebalanced reporting in WP2/WP3 in Y2 as the partners and staff overlap.

## Slide 6: Y2 achieved effort
Overall effort achieved in Q5-8 in PMs: per partner
Partner | Total plan (PM) | Q5 % achieved | Q6 % achieved | Q7 % achieved | Q8 % achieved | Total Y2 (PM) | YEAR 2 % achieved | YEAR 1 % achieved
CERN | 67 | 105% | 78% | 67% | 64% | 20 | 82% | 90%
APO | 34 | 87% | 61% | 92% | 51% | 10.64 | 86% | 110%
QMUL | 47 | 107% | 60% | 117% | 116% | 17.15 | 100% | 80%
IMPERIAL | 26 | 70% | 3% | 0% | 63% | 6.53 | 69% | 80%
EGI.eu | 18 | 112% | 71% | 78% | 79% | 5.47 | 84% | 110%
Total | 192 | 98% | 60% | 76% | 76% | 59.79 | 86% | 90%
Overall at 86% of planned effort for WP1-4.
Slight under reporting for APO and EGI.eu to balance over reporting in PY1.
Slight under reporting for CERN due to gap in recruitment between iSGTW editors.
Imperial under reporting for a 0.5FTE post and for unfunded effort but D&M not affected

## Slide 7: Effort consumed
PLANNED
CONSUMED
Chart: 
| WP1: Policy | WP2: GridCafe | WP3: iSGTW | WP4: Management
 | 0.23926 | 0.37536 | 0.27077 | 0.11461
Chart: 
| WP1: Policy | WP2: GridCafe | WP3: iSGTW | WP4: Management
 | 0.25661 | 0.34828 | 0.29575 | 0.099364

## Slide 8: Partners PY2 expenditure
Overall at xx% of planned spend for PY2.
xxxxxxxxxxxxx
EGI.eu central budget for e-Concertation for PY2/3 used for 9th e-Concertation meeting in Lyon 25K.
Partner | Cumul Direct | Cumul Indirect | Cumul Eligible | PY2 Estimated Funding | PY2 Planned Funding | % use
CERN |  |  |  |  |  | 
APO |  |  |  |  |  | 
QMUL |  |  |  |  |  | 
IMPERIAL |  |  |  |  |  | 
EGI.eu |  |  |  |  |  | 
Total |  |  |  |  |  | 

## Slide 9: Project Y2 expenditure
xxxxxx
Central budget e-Concertation meeting:
  15k included in QMUL budget in category Other Costs: Shift 10k to the central budget (EGI.eu)
  25k included in EGI.eu budget (central budget) used at 100%
  15K remaining for PY3
ALL PARTNERS | PY2 plan | PY2 used | PY1 used | PY2 % used
PMs |  |  | 63.25 | 
Personnel Costs |  |  | 382,038 | 
Travel |  |  | 30,584 | 
Subcontracting |  |  | 16,501 | 
Other |  |  | 15,284 | 
e-concertation meeting |  |  | 8,743 | CENTRAL BUDGET
Total Direct Costs |  |  | 453,150 | 
Indirect costs |  |  | 208,803 | 
Total Eligible Costs |  |  | 661,952 | 
Max. EC Requested Contribution |  |  | 479,495 | 

## Slide 10: Concertation expenditure
€40K is allocated in the DoW for the e-Infrastructure concertation events to fund logistical costs such as catering, travel and venue costs.
This is allocated as €25K to EGI.eu under WP4 and €15K to QMUL under WP1.
Costs for 9th Concertation meeting, 22-23 September met by EGI.eu as local organisers.
Total cost is 24.8K (average 12.4K per event). Remaining budget for 2012 is 15.2K Euros.
The 10th Concertation meeting will be in Brussels on 6/7 March
8th CONCERTATION MEETING
9th CONCERTATION MEETING
Description | Cost (Euros)
Security | 1,438.00
Catering | 4,574.00
EC diner on the 4th | 318.00
Cleaning | 260.00
Badges | 145.00
Coffee break during the EC meeting | 74.00
TOTAL | 6,809.00
Description | Cost (Euros) | 
Venue main room | 4,502.50 | based 1.5 days
Venue booths area + equipment (panels) | 4,167.00 | based 1.5 days
WIFI, A/V | 1,377.85 | based 120 attendees
Security, cleaning | 934.03 | based 120 attendees
Catering ~18€ | 2,162.40 | based 120 attendees
Breaks 5€ | 1,800.00 | based 120 attendees
Cocktail | 2,649.00 | based 120 attendees
Booths (agINFRA, EUDAT, DASISH @150) | 450.00 | 3 projects
TOTAL | 18,042.78 | 
TOTAL | 24,851.78

## Slide 11
www.e-sciencetalk.eu
Deliverables and Milestones

## Slide 12: Review process
Internal draft ready by day 1 of the PM the report is due
Document internally reviewed by the e-ScienceTalk team – 2 weeks
Document reviewed by the PMB – 1 week
Document submitted at the end of the PM the report is due

## Slide 13: Deliverables
Del. no. | Deliverable name | WP no. | Lead beneficiary |  | Delivery date (PM) | Actual delivery date | Status | Comments
D3.1 | Weekly issues of iSGTW | 3 | CERN | R | 1-33 | 13-24 | Submitted | 
D2.2 | Updated version of the GridCafe website | 2,1,3 | APO | O | 13 | 13 | Submitted | 
D1.2.5 | GridBriefings | 1,2 | QMUL | R | 14 | 14 | Submitted | 
D1.2.6 | GridBriefings | 1, 2 | QMUL | R | 17 | 18 | Submitted | Staffing issue
D1.2.7 | GridBriefings | 1, 2 | QMUL | R | 20 | 20 | Submitted | 
D1.2.8 | GridBriefings | 1, 2 | QMUL | R | 23 | 23 | Submitted | 
D1.4 | Annual impact and sustainability report on e-ScienceTalk products | 1 | QMUL | R | 23 | 23 | Submitted | 
D2.3 | Annual upgraded version of RTM | 2 | APO | O | 23 | 23 | Submitted | 
D3.5 | Report on survey of iSGTW readers and annual metrics | 3 | CERN | R | 24 | 24 | Submitted | 
D4.4 | Annual report on feedback and metrics | 4 | EGI.eu | R | 24 | 25 | Submitted | Submitted in PM13 by agreement with the EC

## Slide 14: Milestones
Milestone no. | Milestone name | Work package no | Lead beneficiary | Delivery date from Annex I dd/mm/yyyy | Achieved Yes/No | Actual / achievement date | Comments
MS10.5 | PMB meetings | 4 | EGI.eu | 13 | 13 | Submitted | 
MS2 | E-concertation event | 1,2,3 | QMUL | 14 | 13 | Submitted | Held early
MS4 | GridCasts | 2 | APO | 14 | 14 | Submitted | 
MS10.6 | PMB meetings | 4 | EGI.eu | 16 | 17 | Submitted | Scheduling
MS7 | iSGTW posters and marketing materials | 3 | CERN | 17 | 17 | Submitted | 
MS8 | Increase iSGTW readership by 15% | 3 | CERN | 17 | 17 | Submitted | 
MS4 | GridCasts | 2 | QMUL | 18 | 18 | Submitted | 
MS5 | GridGuide expanded to 25 new sites | 2 | APO | 18 | 18 | Submitted | 
MS13 | Dissemination materials | 4 | EGI.eu | 18 | 18 | Submitted | 
MS10.7 | PMB meetings | 4 | EGI.eu | 19 | 19 | Submitted | 
MS4 | GridCasts | 2 | APO | 22 | 22 | Submitted | 
MS10.8 | PMB meetings | 4 | EGI.eu | 22 | 22 | Submitted | 
MS7 | Posters and marketing materials | 3, 2 | CERN | 23 | 23 | Submitted | 
MS14 | Dissemination materials | 4 | EGI.eu | 24 | 24 | Submitted | 

## Slide 15
www.e-sciencetalk.eu
Project metrics

## Slide 16: Project metrics
Recommendations from PY1 reviewers:
  Define what constitutes impact in D1.4
  Include more detail on the outcomes and outputs of the products
  Track cross fertilisation amongst the e-ScienceTalk products
  Report metrics based on activities at events
Annual Deliverables on Impact (D1.4) and Metrics (D4.4)
Project and work package level metrics gathered quarterly
Small changes to the metrics for PY3 are included in D4.4

## Slide 17: Project Metrics PY2
WP | No. | Description | PY2 Target | PY1 | PY2 | % of Target
WP1 | 1.1 | Projects covered | 30 per year | 38 (190%) | 74 | 250%
 | 1.2 | Reports and briefings circulated | 4 per year | 300 (75%) | 4 | 100%
 | 1.3 | Countries where reports or briefings are distributed | 30 per year | 36 (120%) | 32 | 94%
WP2 | 2.1 | Sites on GridGuide | 75 | 38 (50%) | 59 | 78% of end target
 | 2.2 | Bloggers contributing to GridCasts | 5 per GridCast | 5 (100%) | 6 | 100%
 | 2.3 | GridCasts per year | 4 in Europe per year, 1 outside Europe | 16 (533%) | 16 | 250%
 | 2.4 | New areas in GridCafé | 3, one per year | 1 (100%) | 2 | 200%
WP3 | 3.1 | iSGTW subscribers | 30% increase | 21% (70%) | 28% | 95% of end of project target
 | 3.2 | Articles on European projects | 50 per year | 108 (216%) | 131 | 261%
 | 3.3 | Projects in the iSGTW/GridCafé resources | 150 in total | 134 (134%) | 134 | 89%
 | 3.4 | iSGTW printed materials distributed | 1000 in total | 330 (33%) | 610 | 61%

## Slide 18: Project metrics PY3
Work Package | Metric no. | Description | Target Metric | Comments
WP1 | 1.1 | Projects covered | 40 per year | Increased from 30
 | 1.2 | Reports and briefings published | 4 per year | Adjusted to number of reports published not printed
 | 1.3 | Countries where reports or briefings are distributed | 30 per year | Unchanged
WP2 | 2.1 | Sites on GridGuide | 75 | Unchanged
 | 2.2 | Bloggers contributing to GridCasts | 5 per GridCast | Unchanged
 | 2.3 | GridCasts per year | 4 in Europe per year, 1 outside Europe | Increased from 2 in Europe
 | 2.4 | New areas in GridCafé | 3, one new area per year | Unchanged
WP3 | 3.1 | iSGTW subscribers | 30% increase | Including social media followers
 | 3.2 | Articles on European projects | 50 per year | Unchanged
 | 3.3 | Projects in the iSGTW/GridCafé resources section | 150 in total | Increased from 100
 | 3.4 | iSGTW printed materials distributed | 1000 in total | Unchanged

## Slide 19
www.e-sciencetalk.eu
WP4 achievements and project issues

## Slide 20: WP4: Major achievements
Kick-off of the project
  PY2 amendment completed in April 2012
  PY1 costs accepted and payments processed
  PMB meetings held, risk register created and monitored
  Project team expanded, including recruitment of iSGTW EU Editor (CERN) and e-Science Impact Reporter (QMUL)
Presentations about the project at:
  EGI Technical Forum2012 - Prague, eChallenges2012 - Lisbon, 9th e-Infrastructure Concertation Meeting – Lyon, ISGC’12 - Taipei
Additional activities
  Quarterly Reports prepared for Q5-7 in addition to agreed Deliverables and Milestones
  Social media and website report for CRISP
  Media training planned at DESY, EUDAT 1st Conference, ESRF

## Slide 21: WP4: Major achievements
MoUs signed with 8 collaborating projects
  Outreach: GlobalExcursion, Virtus
  User community & infrastructures: EGI, EUDAT, N4U, SHIWA
  ESFRI cluster project: CRISP
  Policy: ERINA+
International collaborations
  PM is current Chair of EU/US/Asia iSGTW Advisory Board
  Programme Committee for the 11th International Symposium on Grids and Clouds 2013, Taipei
  Media partner for XSEDE’12, ISC’12
Events organisation
  9th e-Infrastructure Concertation event in Lyon, September 2011
  10th e-Infrastructure Concertation event in Brussels, March 2013
  Preparation of event budgets, registration, invoicing
  Live video feed for Lyon event with GRDI20

## Slide 22: Project issues
Ensuring a good balance of information and contributions from collaborating projects eg for e-ScienceBriefings
Adding Russian to the GridCafé – lacking a translator
Slow addition of new sites for the GridGuide
Sustainability of iSGTW EU funding and recruitment of US and AP Editors
New name for iSGTW and protection of all e-ScienceTalk product names
High travel costs for all work packages due to late booking of travel – event organisers late to confirm participation
iSGTW subscriber numbers are not representative of the wider readership achieved – social media and web stats give a more accurate picture
Euro/CHF exchange rate for WP3 – CERN is making far higher contributions to the costs of the project than foreseen
Redistribution of underspent funds in final 9 months

## Slide 23: Mitigations for PY3
Continue to explore MoUs and collaborations with other projects eg ESFRI cluster projects to ensure balance and promote ongoing sustainability
Low usage of non-English websites
Implment new ideas for GridGuide as an area inside the e-ScienceCity website – project oriented structure could be preferable.
Continue Chair role of iSGTW Advisory Board to promote funding sustainability and resolve name issue.
Protection of current and future e-ScienceTalk product names before project end.
Several media sponsorship arrangements in progress, including journalist and press delegate rates.
Monitor social media figures for iSGTW through the metrics and pursue media partnerships to include subscription to iSGTW as part of the registration process.

## Slide 24: Summary
Project start up achieved successfully
Recruitment to US iSGTW Editor and AP Editor
Effort consumption at 86% of planned levels
Estimated costs at 79% of planned levels
Most Deliverables and Milestones submitted on time, or early
High number of MoUs signed in Year 2
Project level metrics largely met or exceeded
High impact for the project in Year 2

## Slide 25
www.e-sciencetalk.eu
Additional slides

## Slide 26: Metrics for WP1
Metric no. | Description | Comments | Q1 | Q2 | Q3 | Q4 | TOTAL
1.1 | Projects covered | In the e-ScienceBriefings | 15 | 4 | 13 | 17 | 38
1.2 | Reports and briefings circulated | In print or by email | 1 report | 1 report | 1 report | 1 report | 4
1.3 | Countries where reports or briefings are distributed | In print or by email | 36 | 36 | 36 | 36 | 36
1.4 | Policy articles published | In print or online | 3 | 2 | 22 | 7 | 34
1.5 | Policy reports written | In print or online | 1 | 1 | 1 | 1 | 4
1.6 | Printed policy reports circulated | To policy makers | 100 | 0 | 100 | 100 | 300
1.7 | Policy events organised | Number organised | 1 | 0 | 0 | 0 | 1
1.8 | Attendees at policy events | Number of delegates | 111 | 0 | 0 | 0 | 111
1.9 | Collaborating projects to which articles have been distributed | In print or by email | 13 | 6 | 9 | 8 | 36
1.10 | Countries to which articles or reports have been distributed | In print or by email | 36 | 36 | 36 | 36 | 36

## Slide 27: Metrics for WP2
Metric no. | Description | Comments | Q1 | Q2 | Q3 | Q4 | TOTAL
2.1 | Sites on GridGuide | Number of sites included | 30 | 34 | 34 | 38 | 38
2.2 | Bloggers contributing to GridCasts | Average number of bloggers on GridCast | 2 | 3 | 6 | 2 | 3
2.3 | GridCasts per year | Including major and mini GridCasts | 7 | 2 | 5 | 2 | 16
2.4 | New areas of GridCafé | Covering topics other than grid computing | 1 in development | 1 in development | 1 in development | 1 | 1
2.5 | Unique visitors to the GridCafé website | From Google Analytics | 4422 | 4020 | 4490 | 2994 | 15926
2.6 | Page views of the GridCafé website | From Google Analytics | 48676 | 41380 | 48567 | 27788 | 166411
2.7 | Number of bloggers for GridCast | Total number of bloggers | 15 | 7 | 28 | 9 | 59
2.8 | Blog entries | Total number | 92 | 15 | 115 | 22 | 244
2.9 | Podcasts | Total number | 20 | 0 | 36 | 0 | 56
2.10 | Unique visitors to the GridCast | From Google Analytics | 2295 | 1621 | 2765 | 1963 | 8644
2.11 | Page views of the GridCast | From Google Analytics | 5343 | 3526 | 7900 | 3743 | 20512
2.12 | EU sites on GridGuide | European based sites | 24 | 24 | 24 | 28 | 28
2.13 | Non-EU sites on GridGuide | Non-European located sites | 10 | 10 | 10 | 11 | 11

## Slide 28: Metrics for WP2
Metric no. | Description | Comments | Q1 | Q2 | Q3 | Q4 | TOTAL
2.14 | Unique visitors to the GridGuide | From Google Analytics | 345 | 331 | 441 | 645 | 1762
2.15 | Page views of the GridGuide | From Google Analytics | 665 | 536 | 821 | 987 | 3009
2.16 | GridGuide sites on RTM | Total number | 27 | 34 | 34 | 34 | 34
2.17 | Countries in the RTM | Total number | 64 | 64 | 64 | 64 | 64
2.18 | Events demo-ing the RTM | Including events attended by collaborating projects demo-ing the RTM | 9 | 0 | 6 | 1 | 16

## Slide 29: Metrics for WP3
Metric no. | Description | Comments | Q1 | Q2 | Q3 | Q4 | TOTAL
3.1 | iSGTW subscribers | Registered in the database | 6838 | 7942 | 8074 | 8077 | 8077
3.2 | Articles on European projects | Based on EU funded projects | 33 | 24 | 26 | 25 | 108
3.3 | Projects in the iSGTW/GridCafé resources section | Total number | 134 | 134 | 134 | 194 | 194
3.4 | iSGTW printed materials distributed | At events attended by e-ScienceTalk or by collaborating projects | 120 | 0 | 160 | 50 | 330
3.5 | Issues published | Issued by email to subscribers each week and posted on the website | 13 | 11 | 13 | 14 | 51
3.6 | US articles published | Based on US projects | 30 | 24 | 32 | 27 | 113
3.7 | Worldwide articles published | Based on non US or EU projects | 1 | 7 | 7 | 5 | 20
3.8 | Unique visitors to the website | From Google Analytics | 39,130 | 20,036 | 39,569 | 45,866 | 126,151
3.9 | Page views of the website | From Google Analytics | 74,542 | 42,528 | 64,652 | 84,103 | 265,539
3.10 | Countries visiting the iSGTW website | From Google Analytics | 140 | 148 | 163 | 183 | 193
3.11 | Marketing materials distributed | In print or by email or at events | 120 | 0 | 50 | 50 | 220
3.12 | Survey responses | Through Zoomerang survey tool | No survey issued | No survey issued | No survey issued | 134 | 134

## Slide 30: Metrics for WP4
Metric no. | Description | Comments | Q1 | Q2 | Q3 | Q4 | TOTAL
4.1 | Deliverables submitted | By email and online | 6 | 1 | 0 | 3 | 10
4.2 | Milestones agreed | By email and online | 3 | 4 | 2 | 1 | 10
4.3 | Late Deliverable and Milestones | Submitted or agreed after the date agreed with the EC | 0 | 0 | 0 | 1 (by agreement with the EC) | 1
4.4 | e-ScienceTalk materials produced | Included printed materials, pens, banners etc | 8 posters, 200 pens, 100 annual reports, 150 GridBriefings, 500 pens | 0 | Poster on e-ScienceCity | 0 | Various
4.5 | Unique visitors to the e-ScienceTalk website | From Google Analytics | 206 | 310 | 500 | 418 | 1434
4.6 | Page views of the e-ScienceTalk website | From Google Analytics | 1072 | 1149 | 1422 | 737 | 4380
4.7 | Media releases issued | Issued via Alphagalileo and by email | 1 | 0 | 2 | 0 | 3
4.8 | Press cuttings | Measured by Google Alerts | 3 | 0 | 5 | 5 | 7
4.9 | Events attended | By e-ScienceTalk project team | 9 | 2 | 6 | 1 | 18