22 December 2011, via telephone conference

Present:

Claire Devereux STFC UK-IE-NL Chair

Celine Bitoune EGI.eu

Steven Newhouse EGI.eu 
Sjomara Specht      EGI.eu

Denise Small STFC UK-IE-NL Minutes

Anders Wannanen UCPH DK

Anna Loukaku GRNET GR

Jana Hrdličková CESNEET CZ|

Serge A. Salamanka UIIP NASB BY

Hank Nussbacher IUCC IL

Andres Aeschlimann SWITCH CH

Sergio Maffioletti SWITCH CH

Simon Leinen SWITCH CH

Monica Anghel ICI RO

Alessandra Casotto INFN IT

Тодор Гюров IICT BAS BG 
Luka Filipovic    UOM  ME

Apologies:

Catherine Gater EGI.eu

Geraldine Fettahi IN2P3 FR

Florence Pesce CERN CH

Agenda

1. The merging of NA2-NA3, and the practicalities of how it works

2. Mailing list for NILs

3. The requirement to account for Global tasks actual costs in Y1

4. Update on payments from EC

5. Q&A, AOBs?

Page 1 of 4

Claire Devereux introduced the agenda and asked if there were any additions or amendments, of which there were none. The items above were then discussed as follows:

Merging of NA2/NA3

Celine briefly described the changes which have taken effect and Steven Newhouse confirmed several points which had been raised:

All effort in NA2 and NA3 NGI (International) tasks has been merged and it now sits in TNA2.1N.

The responsibility for the work from TNA3.2 + TNA3.3 (Users Support) has been moved to TSA1.7. BUT no effort or funding has been moved to SA1.7. NGIs must use their existing effort in TSA1.7 to complete work under the revised TSA1.7 task. If they are unable to do so with the effort allocated, they should reprioritise work within the task according to its local importance and report any difficulties to the Project Office (e.g. drop of the level of support). The Project Office will then report this to the EC and reviewers.

Up to two names of staff working as NGI International Liaisons (NILs) can be reporting under NA2.1N. Note: These people must be recorded in the NILs mailing list and to be provided as soon as possible. It is expected that most NGIs will have one NIL and his/her deputy. Only Germany, Italy and Turkey are expected to have more,  this because of the large allocation of effort within TNA2.1.

Within the new NA2 activities, there will be Virtual Teams (VTs) set up to execute distinct, defined short-term projects (usually lasting a couple of months). NGIs can use effort from their total NA2.1 effort allocation for VTs. In this case they should inform the Project Office and an appropriate amount of effort from their NA2.1 allocation will be moved into their NA2.6 task. The people involved will then report VT work in NA2.6. The NA2.6 task will help the Project Office track effort involved in VTs.

If an NGI draws on people from their NGI that are not a part of EGI InSPIRE the activity of the people can be reported in the quarterly activity report but the corresponding PMs should not be registered in PPT.

VTs are short lived, transitory groups. As such reporting for any one VT in NA2.6 will be similarly short-term.  The partner has to inform the EGI project leader of the virtual team in parallel because the project office will validate with them prior to registering people on this specific tasks.

Further help and clarification regarding how to report effort in the new NA2 tasks is available at the following wiki page:

https://wiki.egi.eu/wiki/Quarterly_reports#Merging_of_NA2- NA3:_how_to_declare_your_efforts_from_Nov_1st:

NGI - NILS officer (International Liaison Officer) - mailing lists

Page 2 of 4

ACTION: any NGIs that have not yet provided the names of their NIL(s) to the project office to do so as soon as possible. For the mailing list please email Erika and for the changes in PPT please email Sjomara.

Global Tasks Accounting (Only applicable to NGIs running Global Tasks)

Steven Newhouse explained that the EC Reviewers wanted an understanding of the true costs of running the global tasks, to be able to understand the future sustainability of the tasks. They also noted some discrepancies in claims across the NGIs and requested more accuracy and detail, for example, some global tasks required more travel funding than others.

Despite it being half way through P2 we have been asked to provide the true costs of the Global Services for P1.

Celine described in more detail the request for providing the accounting information for Period 1. A spreadsheet has been put up on the wiki.

https://wiki.egi.eu/wiki/Sustainability:_Global_tasks_costs

The spreadsheet has each global task listed along with those involved with the tasks and the number of person months reported in PPT. Travel costs and other costs such as laptops should also be listed. Celine will be emailing the spreadsheets to those who are required to complete it.

The deadline for completing the spreadsheets and returning to Celine is 20 January 2012. Ideally the data and it's implications can then be discussed at the NGI Sustainability workshop.

Claire asked whether unfunded effort that was devoted to a global task, but not reported in PPT, should also be given. Steven asked for this data but said it should be supplied separately to the funded effort.

Update on EC Payments

Celine confirmed that all P1 costs had now been cleared by the EC on 14th December 2011. The EC financial Department accepted our costs and are proceeding to payment. The process has started and funds should be released in January 2012. PQ5 payment still requires validation from the EC Project Officer and will take a little longer to process as we have a new EC Project Officer who is on his Christmas break until January 9th 2012. Celine will be chasing this on his return from holiday. The calculation of the payments is available on the wiki. There are detailed tables. All costs will be covered as all were accepted, including for overspending partners. Please check the wiki for your NGI's costs.

Page 3 of 4

Celine confirmed that the payments will be on top of the initial pre-financing amount which is good news for all! Thus NGIs will have received all P1 actual costs plus their 6 months pre-financing. Soon after we expect the PQ5 payment to be released.

AOB

Steven Newhouse advised Bulgaria to check the wiki to find out which VTs have been set up. Once they had identified any they wished to be involved with they should contact the VT Leader and then confirm their involvement with the Project Office.

Claire reminded all that there is the forthcoming Sustainability Workshop in Amsterdam and registration is now open.

Merry Christmas and a happy new year to all!

Page 4 of 4

** How to report SA1.7 in PPT? (Just give access to the old NA3.2/3.3 people, (If they inform the PO) and explicitly tell them to record as usual or tell them to put there efforts as unfunded?(as mentioned everywhere)

## As funded because  we will see that it is (if applicable) not there usual  task to report in. (for members n SA1.7, we have to bare in mind  that the overspending, could be, due to the old NA3.2/3.3 members)

** Will the old NA3.2/3.3 effort be deducted from the (total) 2.1 effort?
and added to TSA1.7 in PPT but without the money?

** How to allocate effort from NA2.1 to 2.6?
## When we are informed that they will ONLY use 2.6 shift all 2.1 effort.
## When we are informed that they will split, ask how the (total) effort will be split, then do the split in PPT.