## Foglio1
TJRa1.3
|  | PY1 | [10 empty] | Project Period 2 |  |  |  | p1+p2
Task | Partner | Worked PM Funded | Originally Committed PM | New Committed PM | Achieved PM % | [5 empty] | Task | Partner | Worked PM Funded | Committed PM | Achieved PM %
TJRA1.3 | 12B-FCTSG | 0.632 | 3 | 1.5 | 42.13% | [5 empty] | TJRA1.3 | 12B-FCTSG | 2.2401 | 1.5 | 149.3%
TJRA1.3 | 14A-CNRS | 1.2882 | 3 | 1.5 | 85.88% | [5 empty] | TJRA1.3 | 14A-CNRS | 2.1776 | 1.5 | 145.2%
TJRA1.3 | 17-SRCE | 3.5668 | 3 | 1.5 | 237.8% | [5 empty] | TJRA1.3 | 17-SRCE | 0 | 1.5 | 0%
TJRA1.3 | 34A-STFC | 1.4394 | 3 | 1.5 | 95.96% | [5 empty] | TJRA1.3 | 34A-STFC | 1.433 | 1.5 | 95.53%
TJRA1.3 | 35-CERN | 4.3458 | 6 | 3 | 144.9% | [5 empty] | TJRA1.3 | 35-CERN | 0 | 3 | 0%
| TOTAL | 11.2722 | 18 | 9 | 125.2% | [7 empty] | 5.8507 | 9 | 0.65008 |  | 17.1229 | 18 | 0.95127
|  | PQ5-PQ6-PQ7 |  |  |  |  | TOTAL PY1 + PQ5/PQ6/PQ7
Task | Partner | Worked PM Funded | Originally Committed PM | Committed PM | Achieved PM % |  | Worked PM Funded | Committed PM | Achieved PM % |  |  |  |  | PY1+PY2
TJRA1.3 | 12B-FCTSG | 1.03 | 0 | 1.125 | 91.56% |  | 1.662 | 2.625 | 63.31% |  |  | Task | Partner | Worked PM Funded | Committed PM | Achieved PM %
TJRA1.3 | 14A-CNRS | 2.1776 | 0 | 1.125 | 193.6% |  | 3.4658 | 2.625 | 132% |  |  | TJRA1.3 | 12B-FCTSG | 2.8721 | 3 | 95.74%
TJRA1.3 | 17-SRCE | 0 | 0 | 1.125 | 0% |  | 3.5668 | 2.625 | 135.9% |  |  | TJRA1.3 | 14A-CNRS | 3.4658 | 3 | 115.5%
TJRA1.3 | 34A-STFC | 0.14647 | 0 | 1.125 | 13.02% |  | 1.5859 | 2.625 | 60.41% |  |  | TJRA1.3 | 17-SRCE | 3.5668 | 3 | 118.9%
TJRA1.3 | 35-CERN | 0 | 0 | 2.25 | 0% |  | 4.3458 | 5.25 | 82.78% |  |  | TJRA1.3 | 34A-STFC | 2.8724 | 3 | 95.75%
| TOTAL | 3.3541 | 0 | 6.75 | 49.69% | [6 empty] | TJRA1.3 | 35-CERN | 4.3458 | 6 | 72.43%
TOTAL PY1 + PQ5/PQ6/PQ7 |  | 14.6263 | 0 | 15.75 | 92.87% |  | 14.6263 | 15.75 | 92.87% |  |  |  | total | 17.1229 | 18 | 95.13%
TJRA1.2
|  | PY1 | [6 empty] | Project Period 2 |  |  |  |  | p1+p2
Task | Partner | Worked PM Funded | Committed PM | Achieved PM % |  |  | Task | Partner | Worked PM Funded | Committed PM | Achieved PM %
TJRA1.2 | 10B-KIT-G | 9.6117 | 11.75 | 81.8% |  |  | TJRA1.2 | 10B-KIT-G | 13.3762 | 11.75 | 113.8%
TJRA1.2 | 12B-FCTSG | 5.6 | 3 | 186.7% |  |  | TJRA1.2 | 12B-FCTSG | 4.3721 | 3 | 145.7%
TJRA1.2 | 14A-CNRS | 3.0594 | 3 | 102% |  |  | TJRA1.2 | 14A-CNRS | 3.0019 | 3 | 100.1%
TJRA1.2 | 16A-GRNET | 0.91429 | 3 | 30.48% |  |  | TJRA1.2 | 16A-GRNET | 1.9011 | 3 | 63.37%
TJRA1.2 | 17-SRCE | 3.2903 | 3 | 109.7% |  |  | TJRA1.2 | 17-SRCE | 3.47 | 3 | 115.7%
TJRA1.2 | 34A-STFC | 5.2693 | 6 | 87.82% |  |  | TJRA1.2 | 34A-STFC | 5.2722 | 6 | 87.87%
TJRA1.2 | 35-CERN | 0.53271 | 3 | 17.76% |  |  | TJRA1.2 | 35-CERN | 5.6636 | 3 | 188.8%
TOTAL PY1 |  | 28.2777 | 32.75 | 86.34% |  |  | Total: |  | 37.0571 | 32.75 | 113.2% |  |  | 65.3348 | 65.5 | 0.99748
37.0571
|  | PQ5-PQ6-PQ7 |  |  |  | TOTAL PY1+ PQ5/PQ6/PQ7 | Committed PM | Achieved PM %
Task | Partner | Worked PM Funded | Committed PM | Achieved PM % |  | Worked PM Funded | 20.5625 | 99.93% | [6 empty] | PY1+PY2
TJRA1.2 | 10B-KIT-G | 10.9369 | 8.8125 | 124.1% |  | 20.5485 | 5.25 | 173.8% |  |  |  |  | Task | Partner | Worked PM Funded | Committed PM | Achieved PM %
TJRA1.2 | 12A-CSIC | 3.5222 | 2.25 | 156.5% |  | 9.1222 | 5.25 | 101.1% |  |  |  |  | TJRA1.2 | 10B-KIT-G | 22.9879 | 23.5 | 97.82%
TJRA1.2 | 14A-CNRS | 2.2505 | 2.25 | 100% |  | 5.3099 | 5.25 | 35.27% |  |  |  |  | TJRA1.2 | 12B-FCTSG | 9.9721 | 6 | 166.2%
TJRA1.2 | 16A-GRNET | 0.93714 | 2.25 | 41.65% |  | 1.8514 | 5.25 | 112.8% |  |  |  |  | TJRA1.2 | 14A-CNRS | 6.0613 | 6 | 101%
TJRA1.2 | 17-SRCE | 2.6336 | 2.25 | 117.1% |  | 5.924 | 10.5 | 94.54% |  |  |  |  | TJRA1.2 | 16A-GRNET | 2.8154 | 6 | 46.92%
TJRA1.2 | 34A-STFC | 4.6577 | 4.5 | 103.5% |  | 9.927 | 5.25 | 89.72% |  |  |  |  | TJRA1.2 | 17-SRCE | 6.7604 | 6 | 112.7%
TJRA1.2 | 35-CERN | 4.1776 | 2.25 | 185.7% |  | 4.7103 | [6 empty] | TJRA1.2 | 34A-STFC | 10.5414 | 12 | 87.85%
TOTAL PQ5/PQ6/PQ7 |  | 29.1156 | 24.5625 | 118.5% |  |  | 57.3125 | 100.1% |  |  |  |  | TJRA1.2 | 35-CERN | 6.1963 | 6 | 103.3%
TOTAL PY1+ PQ5/PQ6/PQ7 |  | 57.3933 | 57.3125 | 100.1% |  | 57.3933 | [6 empty] | Total: |  | 65.3348 | 65.5 | 99.75%
TJRA1.4
|  | PQ5-PQ6-PQ7 | [8 empty] | Project Period 2
Task | Partner | Worked PM Funded | Committed PM | Achieved PM % |  |  |  |  | Task | Partner | Worked PM Funded | Committed PM | Achieved PM %
TJRA1.4 | 10B-KIT-G | 5.716 | 4.5 | 127% |  |  |  |  | TJRA1.4 | 10H-LUH | 6.6335 | 6 | 110.6%
TJRA1.4 | 12A-CSIC | 0.12965 | 4.5 | 2.881% |  |  |  |  | TJRA1.4 | 12B-FCTSG | 0.73469 | 6 | 12.24%
TJRA1.4 | 21A-INFN | 0.90476 | 6.5 | 13.92% |  |  |  |  | TJRA1.4 | 21A-INFN | 1.2381 | 8.6667 | 14.29%
TJRA1.4 | 34A-STFC | 5.8851 | 6.75 | 87.19% |  |  |  |  | TJRA1.4 | 34A-STFC | 6.9147 | 9 | 76.83%
TOTAL PQ5/PQ6/PQ7 |  | 12.6356 | 22.25 | 56.79% |  |  |  |  | Total: |  | 15.521 | 29.6667 | 52.32%
TJRA1.5
Project Period 2
[10 empty] | Task | Partner | Worked PM Funded | Committed PM | Achieved PM %
|  | PY1 | [7 empty] | TJRA1.5 | 14A-CNRS | 17.4824 | 17.6667 | 98.96%
Task | Partner | Worked PM Funded | Committed PM | Achieved PM %
TJRA1.5 | 14A-CNRS | 13.4875 | 17.6667 | 76.34% | [5 empty] | p1+p2
|  | PQ5-PQ6-PQ7 | [9 empty] | PY1+Py2
|  | Worked PM Funded | Committed PM | Achieved PM % | [5 empty] | Task | Partner | Worked PM Funded | Committed PM | Achieved PM %
TJRA1.5 | 14A-CNRS | 12.0498 | 13.25 | 90.94% | [5 empty] | TJRA1.5 | 14A-CNRS | 30.97 | 35.3333 | 87.65%
TOTAL PY1+ PQ5/PQ6/PQ7 |  | 25.5374 | 30.9167 | 82.6%
TJRA1.1
|  | Project Period 1 | [6 empty] | Project Period 2
Task | Partner | Worked PM Funded | Committed PM | Achieved PM % |  |  |  | Task | Worked PM Funded | Committed PM | Achieved PM %
TJRA1.1 | 21A-INFN | 6.8571 | 6 | 114.3% |  |  |  | TJRA1.1 | 6.5159 | 6 | 108.6%
PY1+P2
[8 empty] | Task | Worked PM Funded | Committed PM | Achieved PM %
[8 empty] | TJRA1.1 | 13.373 | 12 | 111.4%
Tool | PY1 |  | PY2 |  | PY3 forecast
| Maint | Dev | Maint | Dev | Maint | Dev
GOCDB | 50% | 50% | 50% | 50% | 40% | 60%
Ops Portal | 20% | 80% | 20% | 80% | 30% | 70%
GGUS | 45% | 55% | 45% | 55% | 50% | 50%
SAM | 55% | 45% | 65% | 35% | 75% | 25%
Accounting Repository | 25% | 75% | 25% | 75% | 40% | 60%
Accounting Portal | 80% | 20% | 70% | 30% | 60% | 40%
Metrics Portal | 10% | 90% | 10% | 90% | 50% | 50%