## Slide 1: JRA1 tasks effort used versus plan (updated until QR9)

## Slide 2: Effort Reporting Analysis
closely tracking with PO
  2 quarters checkpoint
main issues:
  TJRA1.4 highly under reported by almost all partners
    activities not done
    Requirements gathering phase completed, development started (see next slides)
  GRNET in TJRA1.2 very low
    no reason for this, activities done
Minor issues are being tracked but not critical

## Slide 3: Effort Reporting Analysis
TJRA1.1:
  The overspent identified in Y1-Y2 is balanced in QR9.
  Watch situation in forthcoming QRs.
TJRA1.2:
  GRNET: underspent in Y1-Y2 and in QR9, total to catch up ~4 PMs
  If the situation is the same than in QR9, GRNET should provide 10 PMs for the remaining 18 months till the end of he project

## Slide 4
TJRA1.2:
  FCTSG: over reporting 10 PMs out of 6 PMs planned. The activity done is very ok (no additional budget)
  SRCE: slight overspending ok and inline with activity
  STFC: on track in QR9, although a few more PMs are expected to be reported in the coming months to catch up the undone activity in TRAJ1.3
  CERN: on track at the end of Y2, balancing the under reporting of Y1 (Y1 18%; Y2 188%)
Effort Reporting Analysis

## Slide 5
TJRA1.3 (WP initially planned over Y1 and extended to Y2):
  STFC shall report the undone activity during Y1-Y2 within TRJ1.2 (~0,2 PMs)
  CERN although under-reporting in Y1-Y2 has delivered all the work expected.
Effort Reporting Analysis

## Slide 6
TJRA1.4:
  Consumption of efforts is very low and reflects the low activity
  FCTSG/INFN used less than 20% of their cumulated effort in Y2
  STFC used 77% of efforts
  Situation is not improving in QR9 but getting worst for all partner including Germany
Effort Reporting Analysis

## Slide 7
TJRA1.5:
  Under-reporting of Y1-Y2 (CNRS) is being caught up in QR9
Effort Reporting Analysis

## Slide 8: Conclusion
Discuss with your manager to define a plan to fix big deviations
Please, inform us about critical issues that not allow you to fix deviations
All the big deviations must be fixed and/or managed by next review (end Y3)