## Slide 1: E-ScienceTalk PMB
E-ScienceTalk PMB Meeting 10
10 January 2013
Telcon

## Slide 2: Open actions
ACTION | DESCRIPTION | RESPONSIBLE | DATE | STATUS
20110511:5 | Contact EUDAT and ESFRI cluster projects via PMB contacts | Catherine / PMB | Next PMB | Joint ESFRI cluster meeting held at EUDAT. Next meeting at EGICF13. OPEN
20111018:1 | Allocate checking the trademarking and copyright actions to a member of staff. | Bob Jones | Next PMB | Actions added to the team action plan CLOSED
20121008:1 | Draw up a list of events to be attended by the e-ScienceTalk team during the remainder of the project | Catherine Gater | Next PMB | List added to PM report CLOSE
20121008:2 | Explore CMS support options with QMUL and CERN for iSGTW | Catherine Gater | Next PMB | Discussed at board meeting on 14 Nov’12. No action from Xeno OPEN
20121008:3 | CG to confirm funding available for a no cost project extension and support from partners for products after this. | Catherine Gater | Next PMB | Presented at the review. Revised DoW in progress CLOSE

## Slide 3: Review report
e-ScienceTalk has demonstrated significant potential for improving dissemination and outreach activities across a broad range of disciplines and research areas.
Through structured collaboration with a large number of other projects the team has demonstrated the significant potential value of this suite of services. The reviewers urge the Commission to recognise this opportunity and to consider some form of direct funding for the professional skills and services developed by e-ScienceTalk perhaps along the lines of OpenAIRE.
In particular, the reviewers approve of the project team's pro-active approach - for example in pursuing new technologies to attract readers to iSGTW, exploring new methods for collecting and analysing usage data to understand impact, and developing new services such as training. This is impressive added value.
e-ScienceTalk has transformed itself from a project to a suite of services, with potential to contribute in a fundamental and across-the-board way to the work which will be funded under Horizon 2020.
The reviewers are pleased to note how enthusiastically the project team has followed up on the recommendations from the first review, particularly in terms of the further development and refinement of quality metrics.
The information produced to date will remain accessible, and that important lessons learnt about how to disseminate this kind of information to the different audiences will be made available for future EC projects.

## Slide 4: WP1: Grid policy outreach
Progress
Zara Qadir will be full time from January 2013
Paper presented at eChallenges, 17-19 October
Paper accepted for ISGC’13, Taipei – Zara to present
Gridcasts held at eChallenges, EUDAT, SC’12
Briefing on Big Data issued in early December
Next Briefing on security in e-science in February 2013
MoUs signed with BlogForever who will use GridCast as a case study for archiving a blog

## Slide 5: WP1: Grid policy outreach
Next steps
2 more briefings – D1.2.11 and D1.2.12
Add an extra one in the extension? June D1.2.13
Compendium planned for the end of PY3 – shifted to June 2013 (PM34)
10th e-concertation meeting on 6/7 March at The Hotel – staffing issue at reception
Future topic ideas for briefings
  Security in e-science – next briefing?
  International dimension of grids
  eGovernment
  Impact indicators - eNVENTORY
  Digital Agenda for Europe / Horizon 2020- final briefing?
  eInfrastructure governance
  Exascale/future computing – final briefing?
  Costs of cloud, e-infrastructure

## Slide 6: WP2: GridCafé, GridCast, GridGuide
Progress
e-ScienceTalk
  Tracking downloads and shares of e-ScienceBriefings
e-ScienceCity / GridCafé
  Communications area including multimedia, image bank, news, People bay area now live
  Some graphics still needed to be able to push the site properly – driven by the 3D version
  Moved to individual URLs for each area, now indexed by Google
  Traffic is still low to non GridCafe sites
GridCast
  GridCasts held at eChallenges, EUDAT and SC12.
GridGuide / RTM
  Working on organising the panels more intuitively ie gLite, PANDA, GEANT
  New graphics added to the data transfers panel
  Phedex data transfers demo-ed at the review

## Slide 7: WP2: GridCafé, GridCast, GridGuide
Next steps
e-ScienceCity
  New areas in order: joint networking and data garden section – Data Park
  Need to trademark e-ScienceCity and e-ScienceIsland – URLs all purchased
  Marketing plan: wikipedia, social media, iSGTW, internal linking, schools pack, conferences, videos underway through the Action Plan
GridCafé
  Need a handover date for the old and new versions of GridCafe– site must be functionally complete to do this so can be done once common areas complete – only remaining barrier is the French and Spanish version sites
  Cannot redirect to an external site from a CERN URL any more – dead links – need a CERN contact
GridCast
  Need to have a presence at events outside the usual community to increase the audience and advertise products such as iSGTW.
  Next events are CRISP 2nd conference, ISGC’13, EGI CF13
GridGuide / RTM
  Challenge to reach 100 new sites by May 2013

## Slide 8: Remaining events for PY3
  Helix Nebula General Assembly, Frascati, Italy, 16-18 January 2013 (mini)
  ENVRI meeting, Frascati, Italy, 5-7 February 2013 (mini)
  CloudScape V, Brussels, 27-28 February 2013 (mini)
  10th e-Infrastructure Concertation meeting, Brussels, 6-7 March 2013 - MAJOR
  CRISP Annual Event, Villigen, Switzerland, 18-20 March 2013 – MAJOR + TRAINING
  ISGC 2013, Taipei, Taiwan, 18-22 March 2013 - MAJOR
  EGI Community Forum, Manchester, UK 8-12 April 2013 – MAJOR
  5th CAPRI meeting, Utrecht, Netherlands, 17-19 April 2013 (mini)
  ISC’13, Leipzig, Germany, 16 – 20 June 2013 - MAJOR

## Slide 9: Plan for GridGuide
Next steps
  Add any missing XSEDE, PRACE sites to bring total up to 100
  Shrink sites to skeletons with links back to original websites
  Remove all out of date content
  Redirect www.gridguide.org to new pages in e-ScienceCity

## Slide 10: WP3: iSGTW
Progress
Amber Harmon started at Indiana University in mid-November as US Desk Editor – fully supported by NSF funding for up to 5 years
Adrian Giordani leaving CERN on 14 January 2013 – will not be replaced
ASGC still committed to providing an Asia-Pacific editor, covering with existing staff for now
PRACE not very engaged despite new communications officer – new CEO being recruited
Subscriptions hovering around 8200 but decrease due to defunct addresses doesn’t seem to have impacted so far
Continued good impact of social media policy – Twitter followers and Facebook fans continuing to increase, retweets by large accounts eg CERN, NatureNews is driving spikes of traffic to the website
NASA website pick up of space music article
iSGTW site and email now at QMUL – CMS transfer is experiencing delays
iSGTW Advisory Board took place on 14 November at SC’12, with Indiana reps
Agreed 3rd party funds for website maintenance – 8K identified in total but no invoice from Xenomedia yet

## Slide 11: WP3: iSGTW
Next steps / Issues
Freelancers identified previously not very active – Andrew is pursuing contacts
New name will left until after the end of the project i.e. as part of a new project
Need to increase subscriber numbers as well as social media numbers – have crept up a bit
Ongoing funding is an issue, especially for web and CMS support

## Slide 12: WP4: Management
Progress
One more e-Concertation meeting in March 2013, Brussels – budget issues resolved, registration underway, competition for most successful FP7 projects launched.
Weekly meetings continuing with the project team
Action Plan set up to the end of the project: https://docs.google.com/document/d/1uIv28N-fjeHSybVt3Rrn97LcB_4iHNkR7GT6T0QJ2Yg/edit
Activities being implemented with CRISP – training carried out at ILL in November – next phase at the CRISP annual event in Villagen in March (clashes with ASGC)
SAGrid and REUNA agreements need to be pursued, as well as DiscovertheCosmos, BioMedBridges, DCH-RP, DASISH and ENVRI
MoU signed with BlogForever, LinkSCEEM-2 discussions
Supporting a joint ESFRI meeting at EGI CF13 conference with CRISP, BioMedBridges, ENVRI and DASISH
DoW amendment to be submitted by PM30 (Feb 2013)

## Slide 13: Project issues
WP1-WP4
GridCast and GridCafe access issues at CERN – still have 404 error and loss of traffic
Lack of sites for GridGuide – end of project milestone a big concern - intern
Funding for iSGTW – editorial effort and web support
iSGTW subscriber numbers may not reach the milestone, especially with the removal of the defunct email addresses
Travel costs to the end of the project tbc
Few staff remaining available to travel
Protection of current and future e-ScienceTalk product names
Non reporting of effort by partners for Quarterly Reports and at year end
Very little unfunded effort reported < 20% reported

## Slide 14: Deliverables and milestones PY3
Complete
In preparation
Months | 25 (Sep | 26 (Oct) | 27 (Nov) | 28 (Dec) | 29 (Jan) | 30 (Feb) | 31 (Mar) | 32 (Apr) | 33 (May) | 34 (June) | 35 (July)
WP1 Policy |  |  |  |  |  |  |  |  |  |  | 
T1.1 Policy | D1.2.9 |  |  | D1.2.10 |  | D1.2.11 |  | D1.2.12 | D1.6 | D1.6 + Briefing? (D1.2.13) | 
T1.2 Impact |  |  |  |  |  |  | D1.5 |  |  |  | D1.5
T1.3 Events |  | MS3 |  |  |  |  | MS3 |  |  |  | 
WP2 GridCafé |  |  |  |  |  |  |  |  |  |  | 
T2.1 GridCafé |  |  |  |  |  |  |  |  | D2.5 | D2.5 + Schools pack (D2.6) | 
T2.2 GridGuide |  |  |  |  |  |  |  | D2.4 | MS6 | D2.4 | 
T2.3 GridCast |  | MS4 |  |  | MS4 |  |  | MS4 |  | MS4 | 
WP3 iSGTW |  |  |  |  |  |  |  |  |  |  | 
T3.1 Weekly |  |  |  |  |  |  |  | D3.6 | MS9 |  | 
T3.2 New media |  |  | MS7 |  |  |  | MS7 |  | D3.7 | D3.7 | 
WP4 Mgmt |  |  |  |  |  |  |  |  |  |  | 
T4.1 | MS10 |  |  | MS10 |  | MS15 | MS10 | D4.5 | D4.6 MS10 | D4.5 MS10 | D4.6

## Slide 15: PY2 Effort
Overall effort achieved in PY2 in PMs: per work package
Table 5: Overall effort achieved in YEAR2 (view 1) |  |  |  | 
Workpackage | Total | Project plan | Linear Y2 plan | YEAR 2 % achieved
WP1 | 15.34 | 46 | 16.7 | 92%
WP2 | 20.82 | 64 | 23.3 | 89%
WP3 | 17.68 | 52 | 18.9 | 93%
WP4-M | 5.24 | 17 | 6.2 | 85%
WP2-UNF | 0 | 8 | 2.9 | 0%
WP4-UNF | 0.7 | 5 | 1.8 | 39%
Total | 59.77 | 192.00 | 69.82 | 86%
Table 6: Overall effort achieved in YEAR2 (view 2) |  |  |  | 
Partner | Total | Year plan | Linear Y2 plan | YEAR 2 % achieved
CERN | 20 | 67 | 24.4 | 82%
APO | 10.64 | 34 | 12.4 | 86%
QMUL | 17.15 | 47 | 17.1 | 100%
IMPERIAL | 6.53 | 26 | 9.5 | 69%
EGI.eu | 5.47 | 18 | 6.5 | 84%
Total | 59.79 | 192.00 | 69.82 | 86%

## Slide 16: PY2 Expenditure
Overall costs in PY2 in Euros: per partner
Under spent against plan for PY2
Costs at 79% against effort at 86%
Partner | YEAR 2 Form C | YEAR 2 Planned Funding | % use
EGI.eu | 72,115 | 79,924 | 90%
QMUL | 90,955 | 107,778 | 84%
APO | 60,826 | 76,748 | 79%
IMPERIAL | 35,265 | 38,801 | 91%
CERN | 108,621 | 163,611 | 66%
Total | 367,930 | 466,863 | 79%

## Slide 17: PY2 Costs Accepted
CERN incidental costs rejected (318€ + indirect costs linked)
EGI.eu audit costs rejected (605€)

## Slide 18: PY1 + PY2 Costs Accepted

## Slide 19: Remaining funds distribution
Pre-financing + interim payments has reached 90% ceiling
No more funds to the project from the EC
Some pre-financing funding left to distribute (77.9K) – minus CERN overpayment (785 Euros)
Proposed distribution according to % share

## Slide 20: Proposed PY2 payment
 |  |  |  |  | PRE-FINANCING TOTAL PAID | Y1 PAYMENTS | Funding left for Y2 payments | Proposed Y2 payments
Participant | TOTAL ELIGIBLE* | TOTAL FUNDING* | Ceiling for Funding 85% | share % |  |  |  | 
EGI.EU* | € 246,498.00 | € 219,794.00 | € 186,824.90 | 17% | € 106,234.00 | € 64,143.00 | € 14,831.90 | € 14,046.90
QMUL | € 332,398.00 | € 296,388.00 | € 251,929.80 | 23% | € 143,254.00 | € 63,487.00 | € 45,188.80 | € 45,188.80
APO | € 236,700.00 | € 211,057.00 | € 179,398.45 | 16% | € 102,011.00 | € 71,428.00 | € 5,959.45 | € 5,959.45
Imperial | € 122,054.00 | € 108,831.00 | € 92,506.35 | 8% | € 52,602.00 | € 27,244.00 | € 12,660.35 | € 12,660.35
CERN | € 518,595.00 | € 463,930.00 | € 394,340.50 | 36% | € 224,233.00 | € 170,892.50 | € - | € -
TOTAL | € 1,456,245.00 | € 1,300,000.00 | € 1,105,000.00 | 100% | € 628,334.00 | € 397,194.50 | € 78,640.50 | € 77,855.50

## Slide 21: Remaining Funds PY3
Overall costs in PY3 in Euros: per partner
Remaining:
PM 25-33
27% of project
Partner | TOTAL Funding | PY 3 Remaining | % Remaining
EGI.eu | 219,972 | 81,512 | 37%
QMUL | 296,389 | 141,249 | 48%
APO | 211,058 | 78,345 | 37%
IMPERIAL | 108,831 | 46,089 | 42%
CERN | 463,930 | 105,725 | 23%
Total | 1,300,000 | 452,576 | 35%

## Slide 22
CRISP – willing to pay for e-ScienceTalk team services post May 2013 (but will not fund core work)
Support from other ESFRI projects is still unclear
Freelancers for iSGTW – ongoing contracts for content on EU side, especially now Adrian is leaving
US funding for the iSGTW editor is for 5 years
ASGC unlikely to recruit
No cost extension of e-ScienceTalk – until end of July 2013
Horizon2020 – earliest date for call likely to be after 1 January 2014
Sustainability

## Slide 23: DoW changes
Estimated underspent budget: 36k
Move estimated underspent budget to central budget for:
  management travels
  final e-Concertation meeting (6-7 March 2013)
Finalise costings for support of the iSGTW website to the end of the project – Xenomedia unresponsive
Convert salary costs for Adrian to freelance fees?
Zara Qadir increases to full time Jan to end July 2013
Legal protection of e-ScienceTalk products beyond the end of the project
Move MS3 from PM26 to PM31 plus final reports to June and July
Extra deliverables & milestones – GridCast, Briefing, Schools Pack
No cost extension to end July 2013 (PM35)
Review in Sep 2013

## Slide 24: Beyond PY3
WP1: Policy and impact
  Current: 1.6 FTE QMUL – increasing to 2.0 FTE for Jan to July 2013
  In-kind after 2013: not currently foreseen
WP2: GridCafe, GridGuide and RTM
  Current: 1 FTE APO, 0.5 FTE Imperial
  In-kind after 2013: 0.1 - 0.2 FTE Imperial
  APO hosting costs for websites
WP3: iSGTW
  Current: 2 FTE CERN – dropping to 1 FTE from 14 Jan 2013
  In-kind after 2013: 1 fellow CERN editorial <1FTE, QMUL 0.1 FTE CMS and hosting.
WP4: Management
  Current: 0.5 FTE EGI.eu
  In-kind after 2013: 0.1 FTE to keep consortium together and coordinate project proposals.
In kind resources proposed on the assumption that the Commission foresees funding for these activities in Horizon2020.
Reviewers endorse e-ScienceTalk consortium is an ideal vehicle to provide communication channels for the e-Infrastructure projects, going into Horizon2020.
Long gap until first Horizon2020 project – September 2014?