## Slide 1: E-ScienceTalk PMB
E-ScienceTalk PMB Meeting 11
8 March 2013
Telcon

## Slide 2: Open actions
ACTION | DESCRIPTION | RESPONSIBLE | DATE | STATUS
20110511:5 | Contact EUDAT and ESFRI cluster projects via PMB contacts | Catherine / PMB | Next PMB | Joint ESFRI cluster meeting held at EUDAT. Next meeting at EGICF13. OPEN
20121008:2 | Explore CMS support options with QMUL and CERN for iSGTW | Catherine Gater | Next PMB | Discussed at board meeting on 14 Nov’12. No action from Xeno OPEN
20130110:1 | Work with CERN to establish how much money can be transferred back into the central budget with Adrian’s departure for freelancers | Catherine Gater | Next PMB | Covered in the amendment CLOSE
20130110:2 | Work with QMUL, CERN and Xeno to resolve the non-responsive server issue for iSGTW during peak loading | Catherine Gater | Next PMB | Covered in the amendment Purchase server OPEN

## Slide 3: WP1: Grid policy outreach
Progress
Zara Qadir is full time from Jan to July 2013
Confirmation of extension needed in writing for QMUL contracts
10th e-concertation meeting on 6/7 March held at The Hotel – good initial feedback, report to be drafted for the EC
Paper accepted for ISGC’13, Taipei – Zara to present, Neasan to assist with GridCast (travel funded)
Training scheduled at CRISP in Villagen with Stefan and Andrew (?)
Gridcasts held at CloudScape V and e-Concertation
Briefing on Security issued at the end of February
Final briefing on Horizon2020 in April 2013
Summary document including all briefings to be issued in June 2013, with foreword from the EC

## Slide 4: WP1: Grid policy outreach
Next steps
One more briefing – D1.2.12
Focus groups at the EGI Community Forum plus survey for e-ScienceCity
Final impact and sustainability report
iSGTW readers survey
Guide to dissemination for EC projects
Schools pack based on e-ScienceCity

## Slide 5: WP2: GridCafé, GridCast, GridGuide
Progress
e-ScienceTalk
  Online discussion forum set up for e-Concertation – could continue to use this
e-ScienceCity / GridCafé
  Data Park text in progress, final content area of e-ScienceCity
  Some graphics still needed to be able to push the site properly – driven by the 3D version
  Traffic is still low to non GridCafe sites – need to create more buzz using social media
  GridCafe now transferred to the new version, with translated sites
GridCast
  GridCasts held at CloudScape V and e-Concertation
GridGuide / RTM
  Working on organising the panels more intuitively ie gLite, PANDA, GEANT
  Fixing a Java problem for Mac users in the webstart version

## Slide 6: WP2: GridCafé, GridCast, GridGuide
Next steps
e-ScienceCity
  Need to trademark e-ScienceCity and e-ScienceIsland – URLs all purchased
  Marketing plan: wikipedia, social media, iSGTW, internal linking, schools pack, conferences, videos underway through the Action Plan
GridCafé
  Cannot redirect to an external site from a CERN URL any more – dead links – need a CERN contact
GridCast
  Planned events are CRISP 2nd conference, ISGC’13, EGI CF13, 5th CAPRI meeting, ISC’13
GridGuide / RTM
  Challenge to reach 100 new sites by May 2013
  Also need to transfer the GridGuide into the e-ScienceCity

## Slide 7: Remaining events for PY3
  CloudScape V, Brussels, 27-28 February 2013 (mini)
  10th e-Infrastructure Concertation meeting, Brussels, 6-7 March 2013 - MAJOR
  CRISP Annual Event, Villigen, Switzerland, 18-20 March 2013 – MAJOR + TRAINING
  ISGC 2013, Taipei, Taiwan, 18-22 March 2013 - MAJOR
  EGI Community Forum, Manchester, UK 8-12 April 2013 – MAJOR
  5th CAPRI meeting, Utrecht, Netherlands, 17-19 April 2013 (mini)
  ISC’13, Leipzig, Germany, 16 – 20 June 2013 - MAJOR

## Slide 8: Plan for GridGuide
Next steps
  Add any missing XSEDE, PRACE sites to bring total up to 100
  Shrink sites to skeletons with links back to original websites
  Remove all out of date content
  Redirect www.gridguide.org to new pages in e-ScienceCity

## Slide 9: WP3: iSGTW
Progress
Amber Harmon US Desk Editor now providing articles, but is not engaging in social media or publishing
ASGC still committed to providing an Asia-Pacific editor, covering with existing staff for now but no articles received recently
PRACE not very engaged despite new communications officer – unlikely to get buy in now before the end of the project
Subscriptions have now gone up to 8700 and should increase after ISC’13
Continuing to be active in social media and to see increases in page views and referrals to the website
Next iSGTW Advisory Board to be agreed – April 2013?
Discussions between QMUL and Xenomedia about the CMS seem to have stalled.- ongoing maintenance of the CMS after the project closes now becoming urgent
3K Euros set aside in the amendment to buy a dedicated faster server at QMUL for hosting to improve support for peaks in
10K Euros set aside in the amendment for freelancers

## Slide 10: WP3: iSGTW
Next steps / Issues
Andrew to source freelancers to ease issues with excessive workload
Zara to act as short term back up for publishing during holidays / emergencies
Call to be set up with Amber’s managers at Indiana before the Board meeting
QMUL to purchase and set up new server (instead of the ongoing costs of a hosted service)
CMS issues needs to be resolved – how to do this, when Xenomedia is unresponsive?

## Slide 11: WP4: Management
Progress
e-Concertation meeting took place on 6&7 March 2013, Brussels – winners announced, success stories to be featured in iSGTW over time, report to be collated, invoice expected from the venue
Weekly meetings continuing with the project team
Action Plan set up to the end of the project: https://docs.google.com/document/d/1uIv28N-fjeHSybVt3Rrn97LcB_4iHNkR7GT6T0QJ2Yg/edit
Supporting a joint ESFRI meeting at EGI CF13 conference with CRISP, BioMedBridges, ENVRI and DASISH – invitation / reminder to be sent next week
DoW amendment submitted this week, letter requesting extension sent

## Slide 12: Project issues
WP1-WP4
GridCast and GridCafe access issues at CERN – still have 404 error and loss of traffic
Lack of sites for GridGuide – end of project milestone a big concern - intern
Funding for iSGTW – editorial effort and web support – partly addressed
Few staff remaining available to travel but should be able to cover the events we have in the calendar if no more absences
Protection of current and future e-ScienceTalk product names
Non reporting of effort by partners for Quarterly Reports and at year end
Very little unfunded effort reported < 20% reported
Budget underspent overall, could be as much as 100k Euros

## Slide 13: Deliverables and milestones PY3
Complete
In preparation
Months | 25 (Sep | 26 (Oct) | 27 (Nov) | 28 (Dec) | 29 (Jan) | 30 (Feb) | 31 (Mar) | 32 (Apr) | 33 (May) | 34 (June) | 35 (July)
WP1 Policy |  |  |  |  |  |  |  |  |  |  | 
T1.1 Policy | D1.2.9 |  |  | D1.2.10 |  | D1.2.11 |  | D1.2.12 |  | D1.6 | 
T1.2 Impact |  |  |  |  |  |  |  |  |  |  | D1.5
T1.3 Events |  | MS3 |  |  |  |  | MS3 |  |  |  | 
WP2 GridCafé |  |  |  |  |  |  |  |  |  |  | 
T2.1 GridCafé |  |  |  |  |  |  |  |  |  | D2.5 D2.6 | 
T2.2 GridGuide |  |  |  |  |  |  |  |  | MS6 | D2.4 | 
T2.3 GridCast |  | MS4 |  |  | MS4 |  |  | MS4 |  | MS4 | 
WP3 iSGTW |  |  |  |  |  |  |  |  |  |  | 
T3.1 Weekly |  |  |  |  |  |  |  |  | MS9 D3.6 |  | 
T3.2 New media |  |  | MS7 |  |  |  | MS7 |  |  | D3.7 | 
WP4 Mgmt |  |  |  |  |  |  |  |  |  |  | 
T4.1 | MS10 |  |  | MS10 |  | MS15 | MS10 |  |  | D4.5 MS10 | D4.6

## Slide 14: Remaining funds distribution
Pre-financing + interim payments has reached 90% ceiling
No more funds to the project from the EC
The pre-financing funding left has been distributed as proposed at the last PMB
Proposed distribution according to % share

## Slide 15: Remaining Funds PY3
Overall costs in PY3 in Euros: per partner
Remaining:
PM 25-33
27% of project
Partner | TOTAL Funding | PY 3 Remaining | % Remaining
EGI.eu | 219,972 | 81,512 | 37%
QMUL | 296,389 | 141,249 | 48%
APO | 211,058 | 78,345 | 37%
IMPERIAL | 108,831 | 46,089 | 42%
CERN | 463,930 | 105,725 | 23%
Total | 1,300,000 | 452,576 | 35%

## Slide 16
CRISP – willing to pay for e-ScienceTalk team services post July 2013 (but will not fund core work), need to pursue this after the annual event in March
Support from other ESFRI projects is still unclear – use the meeting at the EGI Community Forum with the cluster project leaders to clarify
Freelancers for iSGTW
US funding for the iSGTW editor is for 5 years but issues to be addressed
ASGC unlikely to recruit
No cost extension of e-ScienceTalk until end of July 2013 should be
Horizon2020 – earliest date for start of funding likely to be autumn 2014, with a call opening in late 2013.
Sustainability

## Slide 17: Beyond PY3
WP1: Policy and impact
  Current: 1.6 FTE QMUL – increasing to 2.0 FTE for Jan to July 2013
  In-kind after 2013: not currently foreseen
WP2: GridCafe, GridGuide and RTM
  Current: 1 FTE APO, 0.5 FTE Imperial
  In-kind after 2013: 0.1 - 0.2 FTE Imperial
  APO hosting costs for websites
WP3: iSGTW
  Current: 2 FTE CERN – dropping to 1 FTE from 14 Jan 2013
  In-kind after 2013: 1 fellow CERN editorial <1FTE, QMUL 0.1 FTE CMS and hosting.
WP4: Management
  Current: 0.5 FTE EGI.eu
  In-kind after 2013: 0.1 FTE to keep consortium together and coordinate project proposals.
In kind resources proposed on the assumption that the Commission foresees funding for these activities in Horizon2020.
Reviewers endorse e-ScienceTalk consortium is an ideal vehicle to provide communication channels for the e-Infrastructure projects, going into Horizon2020.
Long gap until first Horizon2020 project – September 2014?

## Slide 18: Future project proposals?
Need to identify the elements we want to keep e.g. e-ScienceCity, iSGTW, RTM, policy, impact
EC looking for horizontal projects across e-Infrastructures and Ris
Developing human capital is a key aim for Horizon2020 – formalise the blogging team into a network of ambassadors, with travel paid from the budget?
Training as a stronger element?
Bring in other EIROs eg EMBL?
Bring in other e-Infrastructures e.g. DANTE?
EGI.eu is prepared to coordinate