## Meeting participation
VT member mail address | VT reqd | Vt Not req | Response to Doodle of Mar 13 | Meeting on 27 Mar 13 | Meeting in April 13 …..date tbc
breton@clermont.in2p3.fr
catherine.gater@egi.eu
claire.devereux@stfc.ac.uk | Yes |  | un-available
coen.schrijvers@surfsara.nl | Yes |  | un-available
daniele.cesini@cnaf.infn.it
ebayonne@i3m.upv.es
eric.yen@twgrid.org | Yes |  | un-available
genevieve.romier@idgrilles.fr | Yes |  | Available
gergely.sipos@egi.eu |  |  | Available | Yes
giacinto.donvito@ba.infn.it
goncalo@lip.pt |  |  | Available | Yes
iblanque@dsic.upv.es
isabel@campos-it.es
j.l.konijn@uva.nl |  | Remove
kkoum@grnet.gr
m.sterzel@cyfronet.pl | Yes |  | Available | Yes
paola.materia@ingv.it
richard.mclennan@egi.eu | No |  | Available | Yes
rlovas@sztaki.hu
suhaimi@putra.upm.edu.my | Yes |  | un-available
vic@twgrid.org | Yes |  | un-available
w.los@uva.nl | Yes |  | Available | Yes
yannick.legre@idgrilles.fr | Yes |  | Available | Yes
Rob Hooft <rob.hooft@nbic.nl> | New |  |  | Yes
Giorgio Pietro Maggi <giorgio.maggi@ba.infn.it> | New
Note on C1: R McLennan: VT members were surveyed to determine if they needed to be in the VT. Few responded.

## Meeting Actions
Action No | Date | Task | Lead | Status | Remarks
1.1 | 2013-03-27 | The meeting agreed that more detail needed to be added to the very broad and high level objectived described in the VT's Wiki page. Clarity was required regarding the objectives, tasks, benefits and expectations of the VT and an ensuing VRC in order that VT members could see how each of them could contribute in practice to the outputs. Wouter Los undertook to draft out such descriptive guidance as a first step, aiming to discuss this Tues 2 Apr during a scheduled ENVRI teleconf with Yannick and Jacko. | Wouter Los | Open | Target 2 Apr
1.2 | 2013-03-27 | Gonçalo Borges commented that the VT already had substantial data on useful contacts in this community and he recommended that such information be used "to start important conversations" with them. As an initial step, the VT should identify relevant synergies (especially for the ENVRIs) and circulate this knowledge to the VT. Yannick undertook to do this before the next meeting. | Yannick Legre | Open | Target 18 Apr
1.3 | 2013-03-27 | Set up follow up E&B VT teleconference. Proposed dates are 18/19 Apr after the EGI Forum. | Yannick Legre | Open | Indico container at https://indico.egi.eu/indico/conferenceDisplay.py?confId=1431