## VT CTA Contacts
| user name | full name |  | postal address | email address | Nation | 2013-01-18 | 2013-02-15 | 2013-03-01 | 2013-03-25 | 2013-04-10
1 | hrach | Alessandro Costa, | INFN |  | alessandro.costa@oact.inaf.it | Italy | Y | Y | Y
|  | Alessandro Costantini, | IGI |  |  | Italy | Y |  | Y
|  | Aneta Karaivanova |  | Bulgarian Academy of Sciences, Institute of Information and Communication Technologies |  | Bulgaria
14 | mclennan | Brook Schofield | Terena institute | Netherlands |  | Observer | Y |  | Y | Y
20 | sipos | Cecile Barbier | CNRS/IN2P3/LAPP |  |  | France | Y | Y |  | Y
|  | Claudio Vuerli | INFN |  | vuerli@oats.inaf.it | Italy | Y | Y | Y | Y
|  | Daniele Cesini | IGI | viale b. pichat 13/2 - 40100 - bologna, italy | daniele.cesini@cnaf.infn.it | Italy |  | Y
|  | Enol Fernandez |  |  |  | Spain
|  | Fabio Vitello | INFN |  | fabio.vitello@oact.inaf.it | Italy
12 | tm483 | Genevieve Romier | Institute de Grilles |  |  | France | Y |  |  | Y
|  | Gergely Sipos | EGI.EU | Stichting European Grid Initiative, 140 Science Park, 1098 XG Amsterdam, The Netherlands | gergely.sipos@egi.eu | EGI | Y | Y | Y | Y
|  | Giovanni Lamanna | CNRS/IN2P3/LAPP |  |  | France
|  | Giuliano Castelli |  |  | giuliano.castelli@oats.inaf.it |  |  |  | Y | Y
|  | Hrachya Astsatryan Հրաչյա Ասցատրյան | IIAP NAS RA | 1, P. Sevak str., Yerevan 0014, Armenia | hrach@sci.am | Armenia
|  | Isabel Campos |  |  |  | Spain
|  | Licia Florio | Terena institute | Netherlands |  | Observer
|  | Lukas Hämmerle | SWITCH | Switzerland |  | Observer | Y | Y
3 | cesini | Marco Bencivenni | IGI |  | marco.bencivenni@cnaf.infn.it | Italy
15 | irene | Mariusz Sterzel | CYFRONET | ACC Cyfronet AGH Nawojki 11 Str. 30-950 Krakow Poland | m.sterzel@cyfronet.pl | Ploand | Y | Y |  | A
21 | sterzel | Nadia Sluer | Terena institute | Netherlands |  | Observer
2 | iblanque | Nadine Neyroud | CNRS/IN2P3/LAPP |  |  | France | Y | Y | Y | Y
17 | burcu | Nukri Komin | CNRS/IN2P3/LAPP |  |  | France
24 | wallom | Ricardo Graciani |  |  |  | Spain
|  | Richard McLennan | EGI.EU | Stichting European Grid Initiative, 140 Science Park, 1098 XG Amsterdam, The Netherlands | richard.mclennan@egi.eu | EGI | Y
|  | Todor Gurov |  | Bulgarian Academy of Sciences, Institute of Information and Communication Technologies |  | Bulgaria |  | Y | Y
|  | Ugo Becciani, | INFN |  | ugo.becciani@oact.inaf.it | Italy | Y
|  | Viktor Kisko |  | Vilnius University, Faculty of Mathematics and Informatics |  | Lithuania

## Meeting Actions
Action No | Date | Task | Lead | Status | Remarks
1.1 | 2013-01-18 | All people who already joined the VT are kindly invited to register the wiki page dedicated to the CTA VT, to periodically look at it and to contribute to it. | ALL | Closed | Contributing to the Wiki page' is a continuous activity
1.2 | 2013-01-18 | Go ahead in contacting new potential CTA groups and individuals that could join the CTA VT. Nadine will help in this activity given that she works in close contact with Giovanni Lamanna who is the leader of the Data management WP of CTA. The spreadsheet currently in preparation will be used for this purpose (A1.3). | Claudio | Open | Claudio and Nadine are contacting people in Poland and France. Further contacts will be made in parallel with Task 2.
1.3 | 2013-01-18 | Preparation of a spreadsheet to be distributed within the VT to gather information from all VT members, mainly to see the social network between EGI and CTA, and the circle of reach of the VT in CTA (important for Task 1). / Richard to setup and circulate a Table to the VT based on the questions that are in the meeting agenda under point 4. | Richard | Closed | Spreadsheet is available at https://docs.google.com/spreadsheet/ccc?key=0AuJ2eJMcDFv7dHJBcEZhdFo5UkYwQVpzOU9Kc21rVUE&usp=sharing. The first round of entries are already in the table. The structure was found suitable
1.4 | 2013-01-18 | Start the users requirements gathering process. This activity will start by processing the already existing CTA user requirements documents extracting from them those requirements that pertain the Science gateways and the SSO system. Almost certainly such requirements are general, so they have to be specialized. This process and the process of adding new requirements not yet captured in the existing documents require close interactions with all CTA end users. | Claudio and Nadine | Open | Nadine worked with Cecile on the existing CTA documents. They will add details to the current list of CTA requirements with French, Italian, Polish people. After this the requirements will be validated by Giovanni, the requirements will be circulate to the VT.
2.1 | 2013-02-15 | After the first set of inputs come togehter in the shared google sheet (see action 1.3), look at the data about the VT social network, cluster the data by country and see where the gaps are and how those could be filled. This relates to Task 1 of the project. | Claudio | Open
2.2 | 2013-02-15 | Send the FIM paper to VT - this demonstrates the kind of requirements that a community can have concerning SSO | Gergely | Closed | The paper is available at https://cdsweb.cern.ch/record/1442597. Link was sent to the VT email list.
3.1 | 2013-03-01 | Ask all members of the VT to fill in the spreadsheet provided by Richard with information on themselves, on CTA groups they belongs and on the NGI in their country. | Claudio | Open | File is available at https://docs.google.com/spreadsheet/ccc?key=0AuJ2eJMcDFv7dHJBcEZhdFo5UkYwQVpzOU9Kc21rVUE&usp=sharing
3.2 | 2013-03-01 | Preparation of the presentation on CTA VT to be shown at the EGI CF 13, Manchester, 10 April 2013. Post the first draft of the presentation on the VT mailing list to collect feedback. | Claudio | Open
3.3 | 2013-03-01 | Preparation of the first draft of the agenda of the CTA VT F2F meeting to be held at the EGI CF 13 in Manchester. Proposal for the date/time of the meeting: Wednesday 10 April at lunch time of during the coffee break in the afternoon. Message posted on the VT mailing list to discover who of the VT membes will be in Manchester attending the EGI CF and the VT face to face meeting. | Claudio | Open
4.1 | 2013-03-25 | Brainstorming with French CTA end users to gather further requirements not yet captured in the previous phases. | Nadine Cecile | Open
4.2 | 2013-03-25 | Brainstorming with Italian CTA end users to gather further requirements not yet captured in the previous phases. | Claudio | Open
4.3 | 2013-03-25 | Brainstorming with Polish CTA end users to gather further requirements not yet captured in the previous phases. | Mariusz | Open
4.4 | 2013-03-25 | Collection of SSO-related requirements coming from eduGAIN. | Brook | Open
4.5 | 2013-03-25 | Analysis of requirements related to the CTA authentication system to verify that the eduGAIN-based SSO system for CTA is able to meet them. | Brook | Open
4.6 | 2013-03-25 | Issue of the first version of the CTA user requirements document related to the Science Gateways and to the SSO authentication system | Nadine Claudio | Open