## Slide 1: Project Extension

## Slide 2: Schedule for H2020 Calls
Open in late 2013
Closing in Spring 2014
Feedback Summer 2014
Negotiation late Summer 2014
Grant awards Autumn 2014

## Slide 3: Impact
There will be no new EC money until Nov 2014
  Project due to finish April 2014
  Certainly an issue for EGI.eu and EGI Global Tasks
  Probably for other partners

## Slide 4: Funding within EGI
EGI-InSPIRE: EC funds
Time
Money
Horizon 2020 Projects
(EC Funds)
EGI.eu fees
May
2013
May
2014
May
2010
Nov
2014
EGI-InSPIRE:
Partner Contributions
EGI Community
Funds
Other EC
Project Funds
EGI.eu fees
EGI
Participant
Contributions
EGI.eu fees
EGI-InSPIRE: EC funds
EGI-InSPIRE:
Partner Contributions
?
EGI-InSPIRE: EC funds
EGI-InSPIRE:
Partner Contributions
EGI.eu fees
6 month extension
Sustain EGI Services that are critical and prevent degradation
Develop innovate new services and integrate into EGI to grow and diversify the supported research community

## Slide 5: Proposal to EGI Council
Define baseline funding level for EGI.eu
  Staff at EGI.eu
  Staff undertaking tasks outside of EGI.eu
Constraints for planning purposes
  No increase in EGI.eu fees
  No increase in partner’s in kind contribution
  Ensure the operational infrastructure works
  Ensure EGI.eu retains a critical mass

## Slide 6: Classify EGI Global Tasks
Evolving EGI Workshop classifications
  Critical, Anti-degradation, Growth, External/Stop
Focus of the EGI.eu fees becomes:
  Critical activities
  Partial funding of Anti-degradation activities
    Fund: coordination, operation & maintenance
    Not funded: development
With current financial constraints this becomes the sustainable EGI Core Activities

## Slide 7: EGI-InSPIRE: 18 months
For PY4:
  Some minor EGI Global Task effort adjustment
  NGI activities continue
    Possibly with reduced effort to save for PY5
For PY5:
  All EGI Global Tasks stop
    Except those as part of the Core EGI Activities
  NGI activities continue
    Using up funds or a best effort

## Slide 8: Extension: NGI Tasks
All partners extend but no re-profiling of effort
  No funded NGI effort in PY5
All partners extend but lower effort in PY4 for PY5
  NGI activities continue at lower level until project ends
All partners extend to PY5 with best effort model
  Partners can use adapt to local needs
  Project funds while they last & then ramp down
  Complicated to describe changes

## Slide 9: Extension: EGI Tasks
Extend just the Core EGI Activities
  Other tasks continue as planned for PY4
  Other tasks stop in PY5
Extend all EGI Global Tasks
  Reduce effort in PY4 for PY5
Hybrid model
  Continue tasks into PY5
  Some non-Core tasks stop as effort runs out

## Slide 10: Priority
Keep operating the Core EGI Activities
  Need to sustain EGI and the infrastructure
Keep activities aligned to H2020 funding
  Retain the service, staff and user community