## Slide 1: Report for the EAC
Steven Newhouse
EGI-InSPIRE Project Director

## Slide 2: Background Material
EGI Keynote slides from Tuesday
Horizon 2020 project document
Project Extension proposal

## Slide 3: Follow up
EGI EC Liaison officer/person
  Passed onto Executive Board
Shaping EC thinking on H2020
  Regular meetings with EC
  New opportunities for EGI within H2020
Common cause with other e-infrastructures
  EGI initiated task forces supporting use cases

## Slide 4: Key Highlights
EGI Champions Established
  Process for selection & travel debugged
  Need to develop support material & processes
NGI International Liaisons
  Still an issue with some partners on resourcing
  But when it works it works very well
  Good vehicle for building consensus
Federated cloud task force
  Running 4 science demos
  Becoming integrated into production environment
Mini-project call from within the project’s partners
  Funded ~12 activities @ ~€55K each to do ‘new’ things
  Need to see how such a dynamic model works out

## Slide 5: Key Issues
There will be no new EC money until Nov 2014
  Project due to finish April 2014
  Certainly an issue for EGI.eu and others
The new money will go into different areas
  More of a focus on the human networks
  Shift away from operations to bringing innovation into operation
  Still discussion about charging users….

## Slide 6: Key Actions
Proposed project extension
  Reduce PY4 activity to fund activity into PY5
Develop our human networks
  NILs, Champions,
Build and develop the platform model
  Core: EUDAT & RIs (e.g. ELIXIR)
  Cloud: Improve user experience & robustness
  Collaboration: Define  Partner  New Projects