## Slide 1: Evaluation of Liferay modules EGI-InSPIRE mini-project
Gergely Sipos
EGI.eu
Technical Outreach Manager
User Community Support Team coordinator
gergely.sipos@egi.eu
EGI Community Forum, Manchester
8-12/April/2013

## Slide 2: Outline
Motivation
Liferay Social Office & Liferay Sync
  WIIF EGI
Mini-project
  goals, partners, tasks, timeline, ...

## Slide 3: Portals in EGI
Increasing number of portals in EGI
  Currently 39 are registered in AppDB http://appdb.egi.eu  Science Gateways
  Includes reusable portal frameworks!
  Recent Virtual Team project wrote a Primer https://wiki.egi.eu/wiki/VT_Science_Gateway_Primer
  In final editing, feedback is welcome!
  Workshops with EGI’s support International Workshop on Science Gateways: http://iwsg2013.org/, Zurich 3-5 June
Liferay is the prime choice for EGI portals
  Scientific portals: e.g. (WS)P-GRADE, SCI-BUS, IGI portal, Catania Science Gateway
  Project portals: e.g. EMI project site
Gartner Magic Quadrant for Horizontal Portals
http://www.liferay.com/about-us/awards

## Slide 4: Liferay Social Office http://www.liferay.com/products/liferay-social-office
An extension for Liferay portal 6.1+
For complex & distributed communities
To
  Enhance personal workflow with social tools
  Keep teams up-to-date
  Find the right people with the right knowledge
  Turn collective knowledge into collective action
  Preserve knowledge for the future
V2.0 released in late 2012

## Slide 5: Liferay Sync http://www.liferay.com/products/liferay-sync
Transforms Liferay into an easy-to-use document sharing service
Share files with a simple drag-and-drop – in real-time
Synchronizes content and documents to desktop and mobile environments (Windows, Mac OS, iOS, Android)
Versioning and revision tracking

## Slide 6: WIIF EGI
New capabilities
Enhance existing Liferay portals/portlets with collaboration capabilities
Increase integration and collaboration across countries, across groups, accross tools
Provide fully customisable and extendable websites and group management systems for EGI stakeholders (projects, VOs, VRCs, task forces, pilots, etc.)
Lower costs of operation & maint.
A hosting environment for (some of) the services of the EGI Collaboration Platform?
Alternative for some of the services that the community already uses for collaboration (e.g Wiki, Document database, Single Sign On)
Making collaborative work in EGI simpler and more fun!

## Slide 7: The mini-project
A systematic evaluation of Liferay Social Office and Sync
  April 2013  September 2013
Outcomes
  Best practices and recommendations for the EGI community (particularly for portal-community@mailman.egi.eu)
  Broader uptake of Liferay within EGI: NGIs, projects, institutes, ...
  Updated EGI portals (by mini-project members)
Members:
  EGI.eu: coordinator
  CESNET: EGI central IT services
  SZTAKI: SCI-BUS/SHIWA portal developers
  INFN: IGI portal developers

## Slide 8: Project timeline
TASK CODE | TASK NAME | EFFORT (in PM) | START | END | COMMENT
T1 | Project coordination | 1.00 | M1 (April) | M6 (Sept) | Including coordination of writing the final deliverable.
T2 | Setup of local Social Office and Sync installations | 1.00 | M1 (April) | M1 (April) | Milestone: One installation for each site. CESNET provides an installation for EGI.eu.
T3 | Refine software evaluation aspects and scenarios (both individual and integrated) | 1.00 | M1 (April) | M2 (May) | Milestone: Aspects and scenarios for evaluation. See the initial list of aspects in another table.
T4 | Perform evaluations, document initial findings | 3.75 | M2 (May) | M4 (July) | Distributed activity at each site. Milestone: Documented findings and recommendations at each site.
T5 | F2F meeting in Amsterdam | 1.50 | M4 (Around mid July) |  | To inform the consortium about the findings; to agree on integrated tests; to agree on overall documentation. 2 person/partner for 3 days including travel time.
T6 | Integrated evaluations & overall documentation | 2.00 | M5 (Aug) | M6 (Sept) | Milestone: Integrated documentation of all evaluation results, together with plans and recommendations for uptake.
 | TOTAL | 10.25 |  |  | 

## Slide 9: List of evaluation scenarios
 | PERSPECTIVE FOR EVALUATION | EFFORT | WHO DOES IT
1 | Solution for VRC, VO, NGI, project websites? | 0.25 | EGI.eu
2 | Interoperability with EGI SSO? | 0.25 | CESNET
3 | Interoperability with AAI solutions? (e.g. eduGAIN, IDEM-GARR, Umbrella) | 0.25 | INFN
4 | Interoperability with portlets from the community? (SCI-BUS and SHIWA portlets) | 1.00 | MTA SZTAKI
5 | Interoperability with portlets from the community? (IGI portlets) | 0.50 | INFN
6 | Interoperability and alternative to EGI Helpdesk? | 0.25 | CESNET
7 | Interoperability and alternative for AppDB? | 0.25 | EGI.eu
8 | Interoperability and alternative for Indico? | 0.25 | CESNET
9 | Interoperability and alternative for Wiki? | 0.25 | CESNET
10 | Interoperability and alternative for DocDB? (Liferay Sync module) | 0.25 | CESNET
11 | Interoperability and alternative for EGI Blog? | 0.25 | CESNET
 | TOTAL (effort in T4) | 3.75 | 
Notes: Possiblility to add:
Liferay supports the setup of personal profiles. This could help us finding persons with specific skills/expertise for certain tasks.

## Slide 10: Project administration
EGI-InSPIRE mini-projects website:
    https://wiki.egi.eu/wiki/Overview_of_Funded_Virtual_Team_projects
New Work package in EGI-InSPIRE (SA4)
    This project: TSA4.3: Evaluation of Liferay modules  https://wiki.egi.eu/wiki/VT_Liferay
    WP leader: Michel Drescher (EGI.eu)
    Short (few lines!) project report every Tuesday to vt-funded-leaders@mailman.egi.eu
    Project members to record effort in PPT

## Slide 11: Next steps
Setup of local Social Office and Sync installations
Refine software evaluation aspects and scenarios (both individual and integrated)
  Short document
Elect leader

## Slide 12: Questions
Email
Gergely.sipos@egi.eu