## Slide 1: E-ScienceTalk PMB
E-ScienceTalk PMB Meeting 12
18 June 2013
Telcon

## Slide 2: Open actions
ACTION | DESCRIPTION | RESPONSIBLE | DATE | STATUS
20110511:5 | Contact EUDAT and ESFRI cluster projects via PMB contacts | Catherine / PMB |  | Maintain contact during project proposal preparation OPEN
20121008:2 | Explore CMS support options with QMUL and CERN for iSGTW | Catherine Gater | 31 July 2013 | Ongoing with Xeno and Linalis. OPEN
20130110:2 | Work with QMUL, CERN and Xeno to resolve the non-responsive server issue for iSGTW during peak loading | Catherine Gater | 31 July 2013 | Server purchased, to be installed end June CLOSE
20130308:1 | Escalate the dead link on the CERN site to the GridCafe to the CERN IT management | Bob Jones | Next PMB | Link fixed CLOSE
20130308:2 | Set up an iSGTW Advisory Board meeting and arrange a further call with Indiana. | Catherine Gater | By 31 July 2013 | iSGTW meeting TBC OPEN
20130308:3 | Offer to fund an upgrade of the CMS by Xenomedia | Catherine Gater | April | No upgrade path agreed CLOSE
20130308:5 | Put together an outline project proposal for H2020 | Catherine Gater | After 31 July | Outline prepared. Further development when call opens OPEN

## Slide 3: WP1: Grid policy outreach
Progress
Zara Qadir is full time from Jan to July 2013
Contracts extended to 31 July 2013
10th e-concertation meeting report send to the EC
Paper accepted for ISGC’13, Taipei – Zara presented, Neasan assisted with GridCast (travel funded)
Training took place at CRISP in Villagen with Stefan and Andrew
Gridcasts held at CRISP, ISGC’13 and EGI Community Forum 2013
Final briefing on Horizon2020 issued in April 2013
Focus groups at the EGI Community Forum plus survey for e-ScienceCity

## Slide 4: WP1: Grid policy outreach
Next steps
D1.6 - Briefing final summary (compendium of briefings)
D2.4 - Annual upgraded version of the RTM
D2.5 - Final dissemination report on GridCafe, GridGuide, GridCast
D2.6 - Schools pack based on e-ScienceCity (mostly done)
D3.7 - Final report on iSGTW and social media
D4.5 - Final report on feedback and metrics
D1.5 - Final report on impact and sustainability
D4.6 - Guide to dissemination for the EC

## Slide 5: WP2: GridCafé, GridCast, GridGuide
Progress
e-ScienceCity / GridCafé
  Site now complete with all areas added at designated URLs
  Site now automatically caching
  Corentin left at the end of May – handover to Stefan and APO completed
GridCast
  GridCasts held at CRISP, ISGC’13, CAPRI, EGI CF’13 and ISC’13
GridGuide
  Reached 102 sites in total – milestone achieved
  Content ported across to the e-ScienceCity area, GridPort
RTM
  Science Museum to include the RTM in the LHC exhibition Nov’13. Adaptations in progress
  Working on organising the panels more intuitively ie gLite, PANDA, GEANT
  Fixed a Java problem for Mac users in the webstart version
  Upgrade to new v2 of World Wide Wind being investigated

## Slide 6: WP2: GridCafé, GridCast, GridGuide
Next steps
e-ScienceCity
  Need to trademark e-ScienceCity and e-ScienceIsland – URLs all purchased
GridCafé
  Visitor figures still fairly low but site now complete, including GridPort
GridCast
  One remaining GridCast at XSEDE’13
GridGuide / RTM
  GridGuide development now static
  RTM main development to be concentrated on Science Museum exhibition
  Data from other LHC experiments
Hosting
  All sites to be hosted by APO with support from Olivier

## Slide 7: Plan for GridGuide
Next steps
  Add any missing XSEDE, PRACE sites to bring total up to 100 - DONE
  Shrink sites to skeletons with links back to original websites - DONE
  Remove all out of date content - DONE
  Redirect www.gridguide.org to new pages in e-ScienceCity – LEAVE GridGuide and GridPort separate

## Slide 8: WP3: iSGTW
Progress
Amber Harmon US Desk Editor now providing articles, but is not engaging in social media or publishing. Meeting held with Daphne but actions still outstanding e.g. CERN visit, increased content
ASGC still committed to providing an Asia-Pacific editor, covering with existing staff for now but no articles received recently
Subscriptions have now gone up to over 8700 and should increase after ISC’13
Continuing to be active in social media and to see increases in page views and referrals to the website
Next iSGTW Advisory Board to be agreed – July 2013?
Discussions between QMUL and Xenomedia about the CMS seem to have stalled BUT useful input from Linalis
Articles commissioned from freelancers through EGI.eu
Articles in progress from the e-Concertation success stories
Extra support from Zara for June and July
Content successfully reduced to 2 features, 1 visual, 1 spotlight each week from 29 May 2013

## Slide 9: WP3: iSGTW
Next steps / Issues
Andrew to continue to source freelancers to ease issues with excessive workload BUT project funds only available til end July 2013
Zara to act as short term back up with help from Melissa at CERN after that
Call with Amber’s managers at Indiana to be followed up at a Board meeting
Chair for the iSGTW tbc – CG to step down after end of July?
CMS issues needs to be resolved – upgrade path may be easier than expected due to inactive modules

## Slide 10: WP4: Management
Progress
e-Concertation hotel invoice finally paid (18k)
Weekly meetings continuing with the project team until the end of June – then by email
Joint ESFRI meeting at EGI CF13 conference with CRISP, BioMedBridges, ENVRI and DASISH did not take place due to lack of attendance – keep projects on board during project development
DoW amendment confirmed including no-cost project extension – end date is 31 July 2013
Final Deliverables and Milestones being prepared
Date of review to be confirmed in Sep ‘13: http://doodle.com/ffevkn75577rb4m3
Team confirmed to the end of the project:
  APO: Andre-Pierre
  CERN: Andrew
  EGI.eu: Catherine
  Imperial: Janusz
  QMUL: Stefan, Zara

## Slide 11: Project issues
WP1-WP4
Support for iSGTW – editorial effort and web support – partly addressed
Protection of current and future e-ScienceTalk product names
Non reporting of effort by partners for Quarterly Reports and at year end
Very little unfunded effort reported < 20% reported
Budget underspent overall, could be as much as 100k Euros
PY2 funds payout not signed by EC in the banking system – not sent

## Slide 12: Deliverables and milestones PY3
Complete
In preparation
Months | 25 (Sep | 26 (Oct) | 27 (Nov) | 28 (Dec) | 29 (Jan) | 30 (Feb) | 31 (Mar) | 32 (Apr) | 33 (May) | 34 (June) | 35 (July)
WP1 Policy |  |  |  |  |  |  |  |  |  |  | 
T1.1 Policy | D1.2.9 |  |  | D1.2.10 |  | D1.2.11 |  | D1.2.12 |  | D1.6 | 
T1.2 Impact |  |  |  |  |  |  |  |  |  |  | D1.5
T1.3 Events |  | MS3 |  |  |  |  | MS3 |  |  |  | 
WP2 GridCafé |  |  |  |  |  |  |  |  |  |  | 
T2.1 GridCafé |  |  |  |  |  |  |  |  |  | D2.5 D2.6 | 
T2.2 GridGuide |  |  |  |  |  |  |  |  | MS6 | D2.4 | 
T2.3 GridCast |  | MS4 |  |  | MS4 |  |  | MS4 |  | MS4 | 
WP3 iSGTW |  |  |  |  |  |  |  |  |  |  | 
T3.1 Weekly |  |  |  |  |  |  |  |  | MS9 D3.6 |  | 
T3.2 New media |  |  | MS7 |  |  |  | MS7 |  |  | D3.7 | 
WP4 Mgmt |  |  |  |  |  |  |  |  |  |  | 
T4.1 | MS10 |  |  | MS10 |  | MS15 | MS10 |  |  | D4.5 MS10 | D4.6

## Slide 13: Remaining funds distribution
Pre-financing + interim payments has reached 90% ceiling
No more funds to the project from the EC
The pre-financing funding left has NOT been distributed as proposed at the January PMB
Proposed distribution according to % share – wrap up in end of project payments?

## Slide 14: Proposed PY2 payment
 |  |  |  |  | PRE-FINANCING TOTAL PAID | Y1 PAYMENTS | Funding left for Y2 payments | Proposed Y2 payments
Participant | TOTAL ELIGIBLE* | TOTAL FUNDING* | Ceiling for Funding 85% | share % |  |  |  | 
EGI.EU* | € 246,498.00 | € 219,794.00 | € 186,824.90 | 17% | € 106,234.00 | € 64,143.00 | € 14,831.90 | € 14,046.90
QMUL | € 332,398.00 | € 296,388.00 | € 251,929.80 | 23% | € 143,254.00 | € 63,487.00 | € 45,188.80 | € 45,188.80
APO | € 236,700.00 | € 211,057.00 | € 179,398.45 | 16% | € 102,011.00 | € 71,428.00 | € 5,959.45 | € 5,959.45
Imperial | € 122,054.00 | € 108,831.00 | € 92,506.35 | 8% | € 52,602.00 | € 27,244.00 | € 12,660.35 | € 12,660.35
CERN | € 518,595.00 | € 463,930.00 | € 394,340.50 | 36% | € 224,233.00 | € 170,892.50 | € - | € -
TOTAL | € 1,456,245.00 | € 1,300,000.00 | € 1,105,000.00 | 100% | € 628,334.00 | € 397,194.50 | € 78,640.50 | € 77,855.50

## Slide 15: Remaining Funds PY3
Overall costs in PY3 in Euros: per partner
Remaining:
PM 25-33
27% of project
Partner | TOTAL Funding | PY 3 Remaining | % Remaining
EGI.eu | 219,972 | 81,512 | 37%
QMUL | 296,389 | 141,249 | 48%
APO | 211,058 | 78,345 | 37%
IMPERIAL | 108,831 | 46,089 | 42%
CERN | 463,930 | 105,725 | 23%
Total | 1,300,000 | 452,576 | 35%

## Slide 16
CRISP – willing to pay for e-ScienceTalk team services post July 2013 (but will not fund core work), need to pursue this but they are VERY slow to pay
Support from other ESFRI projects is still unclear – path to communicate with them not clear
Freelancers for iSGTW established but payment after July 2013 is not clear
US funding for the iSGTW editor is for 5 years but issues to be addressed with work load
ASGC unlikely to recruit
No cost extension of e-ScienceTalk until end of July 2013 approved
Horizon2020 – earliest date for start of funding likely to be autumn 2014, with a call opening in late 2013.
Sustainability

## Slide 17: Beyond PY3
WP1: Policy and impact
  Current: 1.6 FTE QMUL – increasing to 2.0 FTE for Jan to July 2013
  In-kind after 2013: not currently foreseen
WP2: GridCafe, GridGuide and RTM
  Current: 1 FTE APO, 0.5 FTE Imperial
  In-kind after 2013: 0.1 - 0.2 FTE Imperial
  APO hosting costs for websites
WP3: iSGTW
  Current: 2 FTE CERN – dropping to 1 FTE from 14 Jan 2013
  In-kind after 2013: 1 fellow CERN editorial <1FTE, QMUL 0.1 FTE CMS and hosting.
WP4: Management
  Current: 0.5 FTE EGI.eu
  In-kind after 2013: 0.1 FTE to keep consortium together and coordinate project proposals.
In kind resources proposed on the assumption that the Commission foresees funding for these activities in Horizon2020.
Reviewers endorse e-ScienceTalk consortium is an ideal vehicle to provide communication channels for the e-Infrastructure projects, going into Horizon2020.
Long gap until first Horizon2020 project – September 2014?

## Slide 18: Future project proposals?
Need to identify the elements we want to keep e.g. e-ScienceCity, iSGTW, RTM, policy, impact
EC looking for horizontal projects across e-Infrastructures and Ris
Developing human capital is a key aim for Horizon2020 – formalise the blogging team into a network of ambassadors, with travel paid from the budget?
Training as a stronger element?
Bring in other EIROs eg EMBL?
Bring in other e-Infrastructures e.g. DANTE?
EGI.eu is prepared to coordinate, staff now available potentially