## Sheet1
ID | Name | Li | Im | Risk | Owner | Process for managing risk
R1 | Recruitment/retention difficulties | 3 | 3 | 9 | CG | 1. Advertise posts as early as possible 2. Keep close contact with staff to address any difficulties and ensure staff remain motivated
R2 | Dependency on limited number of individuals | 4 | 3 | 12 | CG | 1.Each partner has a defined ‘back-up’, to provide support if the e-ScienceTalk staff member is unable to fulfill their work 2. Close contact between all team members to provide support and oversight
R3 | Uncertain subcontracting costs | 2 | 3 | 6 | CG | 1. Close scrutiny of expenditure during the project 2. Mutual co-operation agreements with collaborating projects 3. Travel budget contributions from EGI.eu
R4 | Lack of future funding | 4 | 3 | 12 | CG | 1. Review opportunities for funding from future calls or other sources 2. Produce excellent content that is widely used, to encourage future funders
R5 | Bad publicity | 2 | 3 | 6 | CG | 1. Use the project QA mechanisms to ensure high quality products 2. Be proactive and build good relations with the media and contributors to e-ScienceTalk products 3. Monitor e-ScienceTalk outputs and respond rapidly to any bad publicity
R6 | Non-optimum working relationship between two iSGTW editors | 4 | 3 | 12 | BJ | 1. Regular exchange of emails and phone calls between the editors, early sight of articles 2. Defined editor for each issue 3. Face to face meetings to deal with strategic issues
R7 | US funding stops for iSGTW | 1 | 3 | 3 | CG/BJ | 1. Assurances have been obtained from US about future funding 2. Ensure iSGTW meets the needs of both partners and their funding agencies
R8 | Technical failure | 4 | 3 | 12 | APO | 1. Review technical options carefully before finalising 2. Leave open the possibiity to change technology choices 3. Use Open Source technologies where possible
R9 | Excessive staff stress levels | 3 | 3 | 9 | BJ | 1. This is a particular issue for iSGTW, with the pressure of producing a weekly newsletter. Make use of other writing resources available, such as in EGI-InSPIRE. 2. Keeping iSGTW duties to the core tasks and reducing administration tasks as far as possible. 3. Bring interns on board during the summer if possible, as these are also a future source of freelance work
R10 | Failing to reach the audience | 1 | 3 | 3 | CG | 1. Use the review process to ensure material is pitched at the right level 2. Work closely with collaborating projects on marketing and publicity for GridTalk products 3. Pursue feedback on the policy content from the eIRG and parties recommended by the EC
R11 | Low media coverage of GridCasts | 2 | 2 | 4 | CG | 1. Circulate press releases where appropriate 2. Ensure GridCasts are publicised within the community through posters and iSGTW 3. Invite high profile bloggers to participate where possible
R12 | Political influence on content | 2 | 2 | 4 | Chair | 1. Use e-ScienceTalk expertise to edit content into a neutral format consistent with the house style 2. Work with collaborating projects to ensure that content of high quality is provided
R13 | Overlap with other projects | 2 | 1 | 2 | CG | 1. Work with projects to ensure synergy rather than overlap 2. Focus e-ScienceTalk's products on specific audiences
R14 | Failure of other projects to circulate material | 2 | 3 | 6 | CG | 1. Produce interesting, timely and relevant material 2.Establish formal and informal agreements with projects about what they will circulate and when
R15 | Website taken offline at short notice | 2 | 1 | 2 | CG | 1. Ensure that all sites have backups and archived content 2. Rationalise ownership of URLs to minimise legal challenges
R16 | Legal challenges to the use of product names | 2 | 3 | 6 | CG | 1. Due diligence checks of any renamed products or new names for products 2. Legal advice on any potential conflicts with existing companies or sites 3. Register trademarks where appropriate