## Slide 1: NA2.5 – Technical Outreach to New Communities
Gergely Sipos
Technical Outreach Manager EGI.eu

## Slide 2: Outline
Objectives, partners
Areas of work
    Outreach with technical focus
    Joint activities with new communities
    Support for Virtual Research Environments (VREs)
    Providing Technical Services
Plans for PY4

## Slide 3: Objectives
Coordination and support to enable research communities to evolve into routine EGI users:
  Technical engagements  technical requirements
  Identify and mobilise resources from EGI
  Integrating applications with EGI platforms
  Develop and deploy new services
  Arrange training and consultancy
Support the development and deployment of innovative, collaborative VREs

## Slide 4: NA2.5 Partners
EGI.eu ‘Technical Outreach to New Communities’ team (3 FTE)
Providers of technical services (2 FTE)
  Applications Database
    IASA (Greece 0.9 FTE)
  Training Marketplace
    STFC (UK 0.6 FTE)
  Client Relationship Management system (from PM19)
    Ibergrid (0.5 FTE) - CSIC (Spain 0.2 FTE) & LIP (Portugal 0.3 FTE)
NGI International Liaisons - NILs
Members of related Virtual Teams & other projects

## Slide 5: Technical Outreach areas
Outreach with technical focus | Support for Virtual Research Environments
Joint activities with new communities | Providing technical services

## Slide 6: Technical Outreach areas
Outreach with technical focus | Support for Virtual Research Environments
Joint activities with new communities | Providing technical services

## Slide 7: Outreach with technical focus
Teleconferences with scientific projects
  e.g. DRIHM, ELI, EISCAT_3D, Euro-Argo
Face-to-face presentations and discussions
  Embedded into community events
  Focus topics: Federated identity, workflows, science gateways, cloud technologies
EGI Webinar programme (go.egi.eu/webinars)
  Service specific presentations
  Introductory level
  EGI.eu and guest speakers

## Slide 8: Technical Outreach areas
Outreach with technical focus | Support for Virtual Research Environments
Joint activities with new communities | Providing technical services

## Slide 9: Activities with new communities https://wiki.egi.eu/wiki  Projects
Activity | Discipline | Delivered output (so far)
EGI-EUDAT-PRACE pilots | Earthquake and seismology (VERCE); Life sciences (VPH) | Tools and best practices for complex workflows
EISCAT_3D and EURO-ARGO study cases | Environmental sciences (ESFRI cluster) | Architecture for a data systems based on EGI tools
EGI-DRIHM collaboration | Hydrometeorology | Architecture for a workflow portal based on EGI tools
NGI-ELIXIR collaboration | Life sciences (ESFRI) | Social network (Recommended next steps)
Technology study for CTA | Astrophysics (ESFRI) | Requirements from CTA to EGI
Towards a CMMST VRC | Chemistry, Molecular & Material Sciences | Identified EGI services and applications that could support the VRC
Speech on the Grid | Speech processing | Contacts to fragmented community
B & E community | Biodiversity and Environmental sciences | Feedback on CRM system
Fire and Smoke simulation | Fire and smoke simulation | Contacts to a small and fragmented community
V i r t u a l
T e a m
S
Notes: Points to make:
We engage through VTs but also through other mechanisms (pilots, use cases, case studies)
We work with various new scientific disciplines
We work with many ESFRIs
Not all projects are successful - reason of failure in the three projects: Project were organised from inside EGI, with no/little representation of the scientific community.

## Slide 10: Technical Outreach areas
Outreach with technical focus | Support for Virtual Research Environments
Joint activities with new communities | Providing technical services

## Slide 11: Support for Virtual Research Environments
Categorise and promote software for VREs
  Science gateway frameworks, workflow tools, middleware services (in AppDB)
  Blog posts, articles, training slides (in TMP)
Support uptake of the EGI Federated Cloud
  Entry page for new users (go.egi.eu/cloud)
  Investigative work for federated cloud use cases
Support the setup of central services for EGI VOs
  GlobusOnline.eu
Follow-up user community requirements (go.egi.eu/requirements)
  Helpdesk (NGIs), projects, TCB
  Solved 19, Endorsed but returned 8

## Slide 12: Technical Outreach areas
Outreach with technical focus | Support for Virtual Research Environments
Joint activities with new communities | Providing technical services

## Slide 13: Technical services
To facilitate information exchange among
  NGI support and outreach teams
  Community-specific support teams
  Project-specific support teams
  User communities and individual users
  EGI.eu staff
Services from EGI-InSPIRE
  Applications Database
  Training Marketplace
  Client Relationship Management system

## Slide 14: Technical services 1: Applications Database
Purpose:
  Facilitate software reuse: Recognition to applications, tools and their developers
New features in PY3:
  Content quality management
    Broken link notification (~20/month)
    Outdated entries notification (12 month)
  New categories
    Science gateways, Workflows, Middleware products
  Repository features
    Primarily for Community Technology Providers
  Dissemination tool
    Messaging groups of developers/users
  Write API
    Third party integration (+ gadget)
  Redesigned front-end
    Top, latest, recently updated, ...
By discipline
By type
http://appdb.egi.eu

## Slide 15: Technical Services 2: Training Marketplace
Purpose:
  Recognition to training related activities and resources
New features in PY3:
  Improved gadgets
    Local events, auto-resize, look&feel
  Usability improvements
    Permalinks to events
    Built-in descriptions
  Spam protection
    ReCAPTCHA module integrated
  Promotion
    ‘As a service’ for external projects
    A tool in EGI
Webinars
http://training.egi.eu

## Slide 16: Technical Services 3: Client Relationship Management system
Purpose:
  Database to capture interactions with and needs of potential user communities
  Launched in PM19
New features in PY3:
  Customisations
    Data fields and associations
    Pre-defined searches, ...
  Metrics monitoring module
    Leads and discussions per NGI
    Projects without leads
    Leads to be interviewed, ...
  Promotion to NILs
http://crm.egi.eu

## Slide 17: Uptake
Applications Database:
  45 new software entries (~slightly less additions than in PY2)
  Continuously growing and geographically dispersed visits
  Further increase in the use expected
    Repository and middleware support features (done)
    Support for Virtualised software (planned)
Training Marketplace:
  Events part is heavily used (more than in EGEE)
Client Relationship Management system:
  Use so far only in a few NGIs  Still needs to demonstrate value at a European level

## Slide 18: Community services Use of resources
Slight under reporting for IASA
  Difference will be compensated in PY4
Slight over reporting for STFC
  Difference will be compensated in PY4
Over reporting for CSIC
  Maintenance and support will need less effort in PY4
 |  | Project Year 1 |  |  | Project Year 2 |  |  | Project Year 3 |  |  | Project Year 1-3 |  | 
Service | Partner | Worked PM Funded | Committed PM | Achieved PM % | Worked PM Funded | Committed PM | Achieved PM % | Worked PM Funded | Committed PM | Achieved PM % | Worked PM Funded | Committed PM | Achieved PM %
Applications Database | IASA + GRNET | 14.6 | 11.8 | 124% | 8.4 | 11.8 | 71% | 10.6 | 11.5 | 92% | 33.6 | 35.1 | 96%
Training Marketplace | STFC | 5.6 | 5.8 | 107% | 3.9 | 3.6 | 107% | 7.7 | 7.3 | 105% | 17.2 | 16.7 | 103%
CRM | CSIC + LIP | 7.6 | 6.0 | 127% | 9.1 | 6.1 | 149% | 4.9 | 5.7 | 86% | 21.6 | 17.8 | 121%

## Slide 19: Plans for next year
High priority activities at EGI.eu:
  Joint activities with new communities
  Enable community contributions in the EGI Collaboration Platform
  Technical contributions to scientific events
  Intense work with the NIL, Champion and Technologist networks
Technical services – functional features:
  AppDB: Support for virtualised services
  TMP: Rich filtering and customisation in all gadgets
  CRM: Further promotion and focus on user support
Notes: Software quality programme:
The programme will invite the developers and providers of user facing services from the EGI ecosystem to contribute to the EGI Collaboration Platform with services that meet the ‘5-star criteria’:
User-centric: The service is connected the EGI production infrastructure (core, cloud or community) and simplifies the use of the production infrastructure by scientific communities.
Generic: The service is discipline neutral, i.e. it can be used by scientists from any discipline.
Open: The service can be configured for any EGI Virtual Organisation (grid or cloud or both types of Virtual Organisations).
Online: At least one, centrally provided and production quality installation of the service exists for EGI.
Supported: Up to date information, support contacts and materials are available about the service through the EGI Applications Database.
The first ‘EGI 5-star services’ are expected to be Globus Online and some of the generic portal services, such as the SHIWA Simulation Platform, IGI Portal and DIRAC Portal. Because the EGI-InSPIRE project does not have budget to support the operation of 5-star services, these will have to be provided as external contributions.

## Slide 20: Summary
Technical support for open, innovative, user-centric VREs:
Intense work with many new communities
  These projects remain in the focus during PY4
Support for Virtual Research Environments
  New programme will define ‘quality standards’ for contributed software
Outreach
  Webinar programme & contributions to scientific events
Technical services
  Continued growth in use
  Development funding beyond EGI-InSPIRE still has to be secured