## Foglio1
TJRA1.1
|  | Project Period 1 | [5 empty] | Project Period 2 |  |  |  |  | Project Period 3 (QR9 -QR12) |  |  |  |  | 12
Task | Partner | Worked PM Funded | Committed PM | Achieved PM % |  |  | Task | Worked PM Funded | Committed PM | Achieved PM % |  | Task | Worked PM Funded | Committed PM | Achieved PM %
TJRA1.1 | 21A-INFN | 6.8571 | 6 | 114.3% |  |  | TJRA1.1 | 6.5159 | 6 | 108.6% |  | TJRA1.1 | 6.2 | 6 | 103.3%
PY1+PY2+PY3
Task | Worked PM Funded | Committed PM | Achieved PM % | Remaining PM | PM/Month foreseen
TJRA1.1 | 19.573 | 18 | 108.7% | 4.427 | 0.36892
TJRA1.2
|  | Project Period 1 | [6 empty] | Project Period 2 | [5 empty] | Project Period 3 (QR9-QR12)
Task | Partner | Worked PM Funded | Committed PM | Achieved PM % |  |  | Task | Partner | Worked PM Funded | Committed PM | Achieved PM % |  | Task | Partner | Worked PM Funded | Committed PM | Achieved PM %
TJRA1.2 | 10B-KIT-G | 9.6117 | 11.75 | 81.8% |  |  | TJRA1.2 | 10B-KIT-G | 13.3762 | 11.75 | 113.8% |  | TJRA1.2 | 10B-KIT-G | 12.2 | 11.75 | 103.8%
TJRA1.2 | 12B-FCTSG | 5.6 | 3 | 186.7% |  |  | TJRA1.2 | 12B-FCTSG | 4.3721 | 3 | 145.7% |  | TJRA1.2 | 12B-FCTSG | 2.3 | 3 | 76.67%
TJRA1.2 | 14A-CNRS | 3.0594 | 3 | 102% |  |  | TJRA1.2 | 14A-CNRS | 3.0019 | 3 | 100.1% |  | TJRA1.2 | 14A-CNRS | 2.2 | 3 | 73.33%
TJRA1.2 | 16A-GRNET | 0.91429 | 3 | 30.48% |  |  | TJRA1.2 | 16A-GRNET | 1.9011 | 3 | 63.37% |  | TJRA1.2 | 16A-GRNET | 2.1 | 3 | 70%
TJRA1.2 | 17-SRCE | 3.2903 | 3 | 109.7% |  |  | TJRA1.2 | 17-SRCE | 3.47 | 3 | 115.7% |  | TJRA1.2 | 17-SRCE | 3.5 | 3 | 116.7%
TJRA1.2 | 34A-STFC | 5.2693 | 6 | 87.82% |  |  | TJRA1.2 | 34A-STFC | 5.2722 | 6 | 87.87% |  | TJRA1.2 | 34A-STFC | 6 | 6 | 100%
TJRA1.2 | 35-CERN | 0.53271 | 3 | 17.76% |  |  | TJRA1.2 | 35-CERN | 5.6636 | 3 | 188.8% |  | TJRA1.2 | 35-CERN | 2.5 | 3 | 83.33%
TOTAL PY1 |  | 28.2777 | 32.75 | 86.34% |  |  | Total: |  | 37.0571 | 32.75 | 113.2% |  | Total: |  | 30.8 | 32.75 | 94.05%
PY1+PY2+PY3
Task | Partner | Worked PM Funded | Committed PM | Achieved PM % | Remaining PM | PM/Month foreseen
TJRA1.2 | 10B-KIT-G | 35.1879 | 35.25 | 99.82% | 11.8121 | 0.98434
TJRA1.2 | 12B-FCTSG | 12.2721 | 9 | 136.4% | -0.27215 | -0.022679
TJRA1.2 | 14A-CNRS | 8.2613 | 9 | 91.79% | 3.7387 | 0.31155
TJRA1.2 | 16A-GRNET | 4.9154 | 9 | 54.62% | 7.0846 | 0.59038
TJRA1.2 | 17-SRCE | 10.2604 | 9 | 114% | 1.7396 | 0.14497
TJRA1.2 | 34A-STFC | 16.5414 | 18 | 91.9% | 7.4586 | 0.62155
TJRA1.2 | 35-CERN | 8.6963 | 9 | 96.63% | 3.3037 | 0.27531
Total: |  | 96.1348 | 98.25 | 97.85%
TJRA1.3
|  | Project Period 1 | [7 empty] | Project Period 2
Task | Partner | Worked PM Funded | Originally Committed PM | New Committed PM | Achieved PM % |  |  | Task | Partner | Worked PM Funded | Committed PM | Achieved PM %
TJRA1.3 | 12B-FCTSG | 0.632 | 3 | 1.5 | 42.13% |  |  | TJRA1.3 | 12B-FCTSG | 2.2401 | 1.5 | 149.3%
TJRA1.3 | 14A-CNRS | 1.2882 | 3 | 1.5 | 85.88% |  |  | TJRA1.3 | 14A-CNRS | 2.1776 | 1.5 | 145.2%
TJRA1.3 | 17-SRCE | 3.5668 | 3 | 1.5 | 237.8% |  |  | TJRA1.3 | 17-SRCE | 0 | 1.5 | 0%
TJRA1.3 | 34A-STFC | 1.4394 | 3 | 1.5 | 95.96% |  |  | TJRA1.3 | 34A-STFC | 1.433 | 1.5 | 95.53%
TJRA1.3 | 35-CERN | 4.3458 | 6 | 3 | 144.9% |  |  | TJRA1.3 | 35-CERN | 0 | 3 | 0%
| TOTAL | 11.2722 | 18 | 9 | 125.2% |  |  |  | TOTAL | 5.8507 | 9 | 65.01%
PY1+PY2
Task | Partner | Worked PM Funded | Committed PM | Achieved PM %
TJRA1.3 | 12B-FCTSG | 2.8721 | 3 | 95.74%
TJRA1.3 | 14A-CNRS | 3.4658 | 3 | 115.5%
TJRA1.3 | 17-SRCE | 3.5668 | 3 | 118.9%
TJRA1.3 | 34A-STFC | 2.8724 | 3 | 95.75%
TJRA1.3 | 35-CERN | 4.3458 | 6 | 72.43%
| total | 17.1229 | 18 | 95.13%
TJRA1.4
|  | Project Period 2 | [6 empty] | Project Period 3 (QR9-QR12)
Task | Partner | Worked PM Funded | Committed PM | Achieved PM % |  |  | Task | Partner | Worked PM Funded | Committed PM | Achieved PM %
TJRA1.4 | 10H-LUH | 6.6335 | 6 | 110.6% |  |  | TJRA1.4 | 10H-LUH | 4.835 | 6 | 80.58%
TJRA1.4 | 12B-FCTSG | 0.73469 | 6 | 12.24% |  |  | TJRA1.4 | 12B-FCTSG | 4.7539 | 6 | 79.23%
TJRA1.4 | 21A-INFN | 1.2381 | 8.6667 | 14.29% |  |  | TJRA1.4 | 21A-INFN | 3.9365 | 8.66 | 45.46%
TJRA1.4 | 34A-STFC | 6.9147 | 9 | 76.83% |  |  | TJRA1.4 | 34A-STFC | 6.6871 | 9 | 74.3%
Total: |  | 15.521 | 29.6667 | 52.32% |  |  | Total: |  | 20.2125 | 29.66 | 68.15%
PY1+PY2+PY3
Task | Partner | Worked PM Funded | Committed PM | Achieved PM % | Remaining PM | PM/Month foreseen
TJRA1.4 | 10H-LUH | 11.4684 | 12 | 95.57% | 6.5316 | 0.5443
TJRA1.4 | 12B-FCTSG | 5.4886 | 12 | 45.74% | 12.5114 | 1.0426
TJRA1.4 | 21A-INFN | 5.1746 | 17.3267 | 29.86% | 20.8254 | 1.7354
TJRA1.4 | 34A-STFC | 13.6018 | 18 | 75.57% | 13.3982 | 1.1165
Total: |  | 35.7334 | 59.3267 | 60.23%
TJRA1.5
|  | Project Period 1 | [6 empty] | Project Period 2 | [5 empty] | Project Period 3 (QR9-QR12)
Task | Partner | Worked PM Funded | Committed PM | Achieved PM % |  |  | Task | Partner | Worked PM Funded | Committed PM | Achieved PM % |  | Task | Partner | Worked PM Funded | Committed PM | Achieved PM %
TJRA1.5 | 14A-CNRS | 13.4875 | 17.6667 | 76.34% |  |  | TJRA1.5 | 14A-CNRS | 17.4824 | 17.6667 | 98.96% |  | TJRA1.5 | 14A-CNRS | 21.6 | 17.66 | 122.3%
PY1+Py2
Task | Partner | Worked PM Funded | Committed PM | Achieved PM % | Remaining PM | PM/Month foreseen
TJRA1.5 | 14A-CNRS | 52.57 | 52.9933 | 99.2% | 0.43003 | 0.14334
Tool | PY1 |  | PY2 |  | PY3 |  | PY4 forecast
| Maint | Dev | Maint | Dev | Maint | Dev | Maint | Dev
GOCDB | 50% | 50% | 50% | 50% | 50% | %0% | 50% | 50%
Ops Portal | 20% | 80% | 20% | 80% | 45% | 55% | 50% | 50%
GGUS | 45% | 55% | 45% | 55% | 50% | 50% | 50% | 50%
SAM | 55% | 45% | 65% | 35% | 70% | 30% | 70% | 30%
Accounting Repository | 25% | 75% | 25% | 75% | 25% | 75% | 50% | 50%
Accounting Portal | 80% | 20% | 70% | 30% | 20% | 80% | 20% | 80%
Metrics Portal | 10% | 90% | 10% | 90% | 20% | 80% | 20% | 80%