## Feuille 1
Module | Note | Drupal 7 | Estimation
Admin |  | Admin | 0.5 |  | Hours | 441
Administration theme |  | Admin_theme | 0.5 |  | Days | 55.125 | 46856.25
Content Permissions |  | field_permissions (upgrade path) | 1
Content Taxonomy |  | D7 core (upgrade path) | 1
Content Taxonomy Autocomplete |  | D7 core
Content Taxonomy Options |  | D7 core
Document Cloud |  | Media ? | 8
Embedded Audio Field |  | Emfield | 2
Embedded Image Field |  | Emfield
Embedded Media Field |  | Emfield
Embedded Video Field |  | Emfield
Fieldgroup |  | fieldgroup D7 (upgrade path with patch) - http://drupal.org/node/1804840
FileField |  | CCK (upgrade path) | 1
FileField Sources |  | filefield_sources (upgrade path ?) | 2
ImageField |  | CCK (upgrade path) | 1
Link |  | Link (upgrade possible with some issues - http://drupal.org/node/970392) | 2
Multiselect |  | Multiselect - some issues in issue queue on Drupal.org | 2
Node Reference |  | CCK (upgrade path) | 1
Node Relationships |  | Not ported to D7 - rebuilding with one of these "References dialog", "inline entity form" or "references" | 24
Number |  | CCK (upgrade path) | 1
Option Widgets |  | CCK (upgrade path) | 1
Text |  | CCK (upgrade path) | 1
User Reference |  | Reference (upgrade path) | 2
Boost |  | Boost | 1
Chaos tools |  | Chaos tools | 1
Custom content panes |  | Panels - with rebuilding | 16
Page manager |  | Chaos tools | 1
Views content panes |  | Panels | 1
Content Profile |  | Manual - https://drupal.org/node/560324 or CCK upgrade path with "profile_lite" | 24
Content Profile Tokens |  | Manual - https://drupal.org/node/560324 or CCK upgrade path with "profile_lite"
Content Profile User Registration |  | Manual - https://drupal.org/node/560324 or CCK upgrade path with "profile_lite"
Context |  | Context (upgrade path) - some rebuilding ? | 4
Context UI |  | Context
Core optional
Blog |  | core + rebuilding | 4
Comment |  | core | 0.5
Content translation |  | core | 0.5
Database logging |  | core | 0.5
Help |  | core | 0.5
Locale |  | core | 0.5
Menu |  | core | 0.5
OpenID |  | core | 0.5
Path |  | core | 0.5
PHP filter |  | core | 0.5
Poll |  | core | 0.5
Search |  | core | 0.5
Statistics |  | core | 0.5
Taxonomy |  | core | 0.5
Trigger |  | core | 0.5
Update status |  | core | 0.5
Upload |  | core | 0.5
Calendar |  | Calendar with some unresolved issues on Drupal.org | 4
Date |  | Date - upgrade path with some issues | 4
Date API |  | Date - upgrade path with some issues
Date Popup |  | Date - upgrade path with some issues
Date Timezone |  | Date - upgrade path with some issues
Devel |  | Devel | 0.5
Devel generate |  | Devel
Devel Memory |  | Devel
IE CSS Optimizer |  | Not needed for D7
CCK Facets |  | Not ported - Solr ?
CCK Reference Facets |  | Not ported - Solr ?
Content Type Facet |  | Not ported - Solr ?
Faceted Search |  | Not ported - Solr ?
Faceted Search UI |  | Not ported - Solr ?
Faceted Search Views |  | Not ported - Solr ?
Features - StrongArm
iSGTW Twitter | iSGTW | Views + twitter configuration | 4
OP Author | OpenPublish | Upgrade path not stable - https://drupal.org/node/1014522 | 4
OP Author Layout | OpenPublish | Upgrade path not stable - https://drupal.org/node/1014522 | 4
OP Author Panels | OpenPublish | Upgrade path not stable - https://drupal.org/node/1014522 | 4
OP Blog | OpenPublish | Upgrade path not stable - https://drupal.org/node/1014522 | 4
OP Contexts | OpenPublish | Upgrade path not stable - https://drupal.org/node/1014522 | 4
OP Defaults | OpenPublish | Upgrade path not stable - https://drupal.org/node/1014522 | 4
OP Event | OpenPublish | Upgrade path not stable - https://drupal.org/node/1014522 | 4
OP Image | OpenPublish | Upgrade path not stable - https://drupal.org/node/1014522 | 4
OP imagecrop Config | OpenPublish | Upgrade path not stable - https://drupal.org/node/1014522 | 4
OP IMCE Config | OpenPublish | Upgrade path not stable - https://drupal.org/node/1014522 | 4
OP Misc | OpenPublish | Upgrade path not stable - https://drupal.org/node/1014522 | 4
OP Package | OpenPublish | Upgrade path not stable - https://drupal.org/node/1014522 | 4
OP Slideshow | OpenPublish | Upgrade path not stable - https://drupal.org/node/1014522 | 1
FeedAPI Inherit | Feeds | https://github.com/developmentseed/feedapi2feeds | 4
FeedAPI Mapper | Feeds | https://github.com/developmentseed/feedapi2feeds
FeedAPI | Feeds | https://github.com/developmentseed/feedapi2feeds
FeedAPI Node | Feeds | https://github.com/developmentseed/feedapi2feeds
SimplePie parser | Feeds XML parser | https://github.com/developmentseed/feedapi2feeds
Flag |  | Flag (some issues on Drupal.org with patches) | 2
Flag abuse |  | Flag abuse (not tested) | 2
Flickr |  | https://drupal.org/node/778628 | 4
Flickr Block
Flickr Filter
Flickr Rippr |  | https://drupal.org/project/flickrrippr - a lot of features are not working on D7 and no migration path provided ? | 24 | Estimation for all the Flickr related modules
Flickr Rippr - Shadow Box
Flickr Rippr - Tags
Flickr Sets
Flickr Tags |  | https://drupal.org/project/flickrapi
FlickrAPI
ImageAPI |  | core
ImageAPI GD2 |  | core
ImageCache |  | core
Imagecache javascript crop |  | https://drupal.org/project/Imagecrop | 2
ImageCache UI |  | core
Mime Mail |  | https://drupal.org/project/mimemail | 2
Simplenews |  | Simplenews + iSGTW patches ? | 4
Simplenews Statistics |  | A very limited DEV version is available
Simplenews Template |  | Not needed with D7 version: https://drupal.org/node/1450250 but maybe some work is needed to port template files | 2
Modal Frame API |  | Not ported: https://drupal.org/node/491224
Localization update |  | Localization update
OAuth |  | https://drupal.org/project/oauth - no upgrade path | 2
OpenPublish Administration |  | Rebuilding some parts | 10 | 2 to estimate parts that need to be ported and 8 to build
OpenPublish Core |  | Rebuilding some parts
OpenPublish Menu |  | Rebuilding some parts
Advanced User Management |  | https://drupal.org/node/67084 - or rebuilding | 1
Autoload |  | not needed with D7
Better Formats |  | Some of the features are in D7 core now but a D7 version is available: https://drupal.org/project/better_formats | 1 | If needed
Browscap |  | https://drupal.org/project/browscap | 1
CKEditor |  | CKEditor | 1
Custom Page |  | Rebuilding - https://drupal.org/project/custompage | 16 | 8 ? 16 ?
Custom Page Admin UI |  | Rebuilding - https://drupal.org/project/custompage
Diff |  | https://drupal.org/project/diff | 0.5
Global Redirect |  | Global redirect | 0.5
IMCE |  | IMCE (upgrade path) | 1
IMCE Mkdir |  | https://drupal.org/project/imce_mkdir | 1
Install Profile API |  | Not ported but not needed
jCarousel |  | Rebuilding | 4
Job queue |  | core - not needed with D7
JS Mobile |  | https://drupal.org/project/browscap | 0
Libraries |  | Libraries | 0.5
Login destination |  | Login destination - some issues: https://drupal.org/node/1665956 | 1
Mollom |  | Mollom | 0.5
Nice Menus |  | Nice Menus - maybe some tests and fixes | 2
Node Embed |  | https://drupal.org/project/node_embed | 1
Nodeblock |  | Nodeblock - no migration path ? | 2
OpenID Admin |  | core
Paging |  | Not fully ported to D7 (GIT branch) and no migration path yet | 16
Path Filter |  | Not ported, should be replaced by Pathologic - https://drupal.org/project/pathologic | 8
Pathauto |  | Pathauto | 1
Premium |  | Not ported - https://drupal.org/project/premium_content | 8
Premium Views Field |  | Not ported - https://drupal.org/project/premium_content
Scheduler |  | Scheduler | 0.5
Session API |  | https://drupal.org/project/session_api - if there are any API changes, will have to find dependencies and to fix them ! | 4 | If there are some API changed, I will have to find dependencies and to fix them
Shadowbox |  | Shadowbox | 0.5
Site map |  | Site map | 0.5
Statistics advanced settings |  | Not ported - alternatives ? (https://drupal.org/node/816040)
Strongarm |  | Strongarm - will be migrated when upgrading features | 0
Tabs |  | Depreceted - https://drupal.org/node/1056562 should be replaced by elements: https://drupal.org/project/elements | 4
Taxonomy Role |  | https://drupal.org/node/908430 - Not ported, rebuilding | 4
Token |  | Token | 0.5
Twitter |  | Twitter | 0.5
Mini panels |  | Panels | 1
Panel nodes |  | Panels | 1
Panels |  | Panels
View Unpublished Content |  | https://drupal.org/project/view_unpublished | 1
Rules |  | Rules (upgrade path) | 2
Rules Administration UI
1 Pixel Out |  | Part of swftools which is not ported - need to be replaced
FlowPlayer |  | https://drupal.org/project/flowplayer | 1
SWF Tools |  | Part of swftools which is not ported - should be replaced
SWFObject2 |  | Not ported - alternative: https://drupal.org/project/swfembed | 2
Google Analytics |  | Google Analytics | 0.5
Tagadelic |  | Tagadelic | 0.5
Custom modules
TDS Announcement Generation | Provides a checkbox on Event submission form that allows for a corresponding Announcement to also be generated. |  | 16 | Need access to source code for a correct estimation
TDS Calendar | Calendar Tweak |  | 8 | Need access to source code for a correct estimation
TDS Content Type Mover | Content Type Moving Functionality |  | 8 | Need access to source code for a correct estimation
TDS Mail Filter | Adds the ability to insert panelset into node body, used for sending newsletter. |  | 24 | Need access to source code for a correct estimation
TDS Redirect | Redirects known PIDs from iSGTW to their corresponding pages within The Digital Scientist |  | 4 | Need access to source code for a correct estimation
TDS Search | Adds block with form for advanced search capabilities. |  | 8 | Need access to source code for a correct estimation
TDS Search Forms | Forms for use with TDS Advanced Search. |  | 8 | Need access to source code for a correct estimation
TDS Simplenews Export | Ability to export detailed statistics from Simplenews. |  | 16 | Need access to source code for a correct estimation
TDS Topic Hub | Topic Hub for TDS Right Sidebar |  | 8 | Need access to source code for a correct estimation
TDS User Registration | TDS Tweaks to User Registration Form |  | 4 | Need access to source code for a correct estimation
CKEditor SWF |  | https://drupal.org/project/ckeditor_swf | 0.5
jQuery UI |  | Not needed in D7 - provided by jquery_update
jQuery Update |  | jQuery Update | 0.5
Views |  | Views - maybe some rebuilding | 4
Views Bulk Operations |  | VBO | 1
Views Carousel |  | Not ported - rebuilding | 4
Views RSS |  | https://drupal.org/project/views_rss | 1
Views RSS: Core Elements
Views RSS: DC Elements
Views RSS: iSGTW | Provides a views plugin that allows for fields specific to iSGTW's user profiles feed. |  | 16 | Need access to code for a correct estimation
Views UI
Fivestar |  | Fivestar | 1
Voting API |  | https://drupal.org/project/votingapi | 0.5
Webform |  | Webform (upgrade path with some issues: https://drupal.org/node/1069424) | 2
Workflow |  | workflow (upgrade path) | 1
XML sitemap |  | https://drupal.org/project/xmlsitemap (upgrade path) | 1
XML sitemap engines
XML sitemap node