## Slide 1: JRA1 tasks effort used versus plan (updated until PY3)
Diego Scardaci – INFN
JRA1 Manager

## Slide 2: Effort Reporting Analysis
Main issues:
  Over Reporting in RED
  Under Reporting in YELLOW
Minor issues are being tracked but not critical

## Slide 3: INFN
Task | Worked PM Funded | Achieved PM (PY1-PY3) | Committed PM (PY1-PY4) | Remaining PM | PM/Month foreseen
TJRA1.1 | 19,6 | 109% | 24 | 4,4 | 0,37
TJRA1.4 | 5,2 | 30% | 26 | 20,8 | 1,73
TOTAL | 24,8 | 70,25% | 50 | 25,2 | 2,1

## Slide 4: KIT
Task | Worked PM Funded | Achieved PM (PY1-PY3) | Committed PM (PY1-PY4) | Remaining PM | PM/Month foreseen
TJRA1.2 | 35,2 | 100% | 47 | 11,8 | 0,98
TOTAL | 35,2 | 100% | 47 | 11,8 | 0,98

## Slide 5: FCTSG/CESGA
Task | Worked PM Funded | Achieved PM (PY1-PY3) | Committed PM (PY1-PY4) | Remaining PM | PM/Month foreseen
TJRA1.2 | 12,3 | 136% | 12 | -0,3 | N.A.
TJRA1.3 | 2,9 | 96% | 3 | 0,1 | Task Ended
TJRA1.4 | 5,5 | 46% | 18 | 12,5 | 1,04
TOTAL | 20,7 | 86,25% | 33 | 12,3 | 1,025

## Slide 6: CNRS
Task | Worked PM Funded | Achieved PM (PY1-PY3) | Committed PM (PY1-PY4) | Remaining PM | PM/Month foreseen
TJRA1.2 | 8,3 | 92% | 12 | 3,7 | 0,31
TJRA1.3 | 3,5 | 116% | 3 | -0,5 | Task Ended
TJRA1.5 | 52,6 | 99% | 53 | 0,4 | Task Ended
TOTAL | 64,4 | 99% | 68 | 3,6 | 0,3

## Slide 7: GRNET
Task | Worked PM Funded | Achieved PM (PY1-PY3) | Committed PM (PY1-PY4) | Remaining PM | PM/Month foreseen
TJRA1.2 | 4,9 | 55% | 12 | 7,1 | 0,59
TOTAL | 4,9 | 55% | 12 | 7,1 | 0,59

## Slide 8: SRCE
Task | Worked PM Funded | Achieved PM (PY1-PY3) | Committed PM (PY1-PY4) | Remaining PM | PM/Month foreseen
TJRA1.2 | 10,3 | 114% | 12 | 1,7 | 0,14
TJRA1.3 | 3,6 | 119% | 3 | -0,6 | Task Ended
TOTAL | 13,9 | 115,83% | 15 | 1,1 | 0,09

## Slide 9: STFC
Task | Worked PM Funded | Achieved PM (PY1-PY3) | Committed PM (PY1-PY4) | Remaining PM | PM/Month foreseen
TJRA1.2 | 16,5 | 92% | 24 | 7,5 | 0,63
TJRA1.3 | 2,9 | 96% | 3 | 0,1 | Task Ended
TJRA1.4 | 13,6 | 76% | 27 | 13,4 | 1,12
TOTAL | 33 | 84,62% | 54 | 21 | 1,75

## Slide 10: CERN
Task | Worked PM Funded | Achieved PM (PY1-PY3) | Committed PM (PY1-PY4) | Remaining PM | PM/Month foreseen
TJRA1.2 | 8,7 | 97% | 12 | 3,3 | 0,28
TJRA1.3 | 4,3 | 72% | 6 | 1,7 | Task Ended
TOTAL | 13 | 86,67% | 18 | 5 | 0,42

## Slide 11: LUH
Task | Worked PM Funded | Achieved PM (PY1-PY3) | Committed PM (PY1-PY4) | Remaining PM | PM/Month foreseen
TJRA1.4 | 11,5 | 96% | 18 | 6,5 | 0,54
TOTAL | 11,5 | 96% | 18 | 6,5 | 0,54

## Slide 12: Conclusion
Discuss with your manager to define a plan to fix big deviations
Please, inform me about critical issues that not allow you to fix deviations
All the big deviations must be fixed and/or managed by the end of the project