## Slide 1
www.e-sciencetalk.eu
WP4: Project and Consortium Management
Catherine Gater
e-ScienceTalk Project Coordinator, EGI.eu
PY3 Review, 13 Sep 2013

## Slide 2: Content
Consumption of effort and resources
Deliverables and milestones
Project metrics
WP4 achievements
Project issues
Summary

## Slide 3
www.e-sciencetalk.eu
Consumption of effort and resources

## Slide 4: WP overview
WP No. | Work package title | Type of activity | Lead partic no. | Lead partic. short name | Personmonths*
1 | Policy, impact and sustainability | SUPP | 2 | QMUL | 46
2 | GridCafé, GridCast and GridGuide | SUPP | 3 | APO | 72
3 | International Science Grid This Week | SUPP | 5 | CERN | 52
4 | Management | MGT | 1 | EGI.eu | 22
 | TOTAL |  |  |  | 192
*Include unfunded PMs (13)

## Slide 5: Effort consumed Y3
PLANNED Y3
CONSUMED Y3
Chart: 
| WP1 Policy | WP2 GridCafe | WP3 iSGTW | WP4-Management
Project plan Y3 | 46 | 64 | 52 | 17
Chart: 
| WP1 Policy | WP2 GridCafe | WP3 iSGTW | WP4-Management
Consumed Y3 | 15.53 | 18.67 | 17.47 | 5.08
Chart: EFFORT TOTAL PROJECT
| CERN | APO | QMUL | Imperial | EGI.eu
Effort planned Total project | 67 | 34 | 47 | 26 | 18
Effort used Total project | 59.64 | 34.31 | 51.81 | 17.97 | 16.65

## Slide 6: Y3 achieved effort
Per work package
Workpackage | Total plan (PM) | Total Y3 (PM) | YEAR3 % achieved | YEAR 2 % achieved | YEAR 1 % achieved
WP1 | 46 | 15.5 | 93% | 92% | 92%
WP2 | 64 | 18.7 | 80% | 89% | 75%
WP3 | 52 | 17.5 | 92% | 93% | 121%
WP4-M | 17 | 5.1 | 82% | 85% | 113%
WP2-UNF | 8 | 0.0 | 0% | 0% | 0%
WP4-UNF | 5 | 0.6 | 31% | 39% | 18%
Total | 192 | 57.3 | 82% | 86% | 90%
Overall at 82% of planned effort for WP1-4
Funded effort at 87% of planned effort for WP1-4
Unfunded effort under-reported in Year 3 but activities done (eg: events participation)
Under reporting in WP2 at 80% - no impact on M&D
Under reporting in WP3 and WP4 to balance against PY1; some efforts in WP4-M not reported in the period (preparation of the final report + review Aug-Sept -0.9PMs)

## Slide 7: Y1-Y2-Y3 achieved efforts
Per Partner
Chart: Total PMs planned vs PMs used Y1-Y2-Y3
| CERN | APO | QMUL | Imperial | EGI.eu
Effort planned Total project | 67 | 34 | 47 | 26 | 18
PMs Used Y1 | 24 | 13 | 13.8 | 6.5 | 6
PMs Used Y2 | 20 | 10.65 | 17.15 | 6.5 | 5.5
PMs Used Y3 | 15.64 | 10.66 | 20.86 | 4.97 | 5.15
% | 0.89015 | 1.0091 | 1.1023 | 0.69115 | 0.925
QMUL: catching up underspent previous year
CERN: personnel end of temporary contract early 2013
Imperial: lack of resource already identified
EGI.eu: 0.9 PMs effort dedicated to Final report and Financial report preparation not reported (period Aug/Sept)

## Slide 8: Project Y3–Total expenditure
Subcontracting budget exhausted (CERN)
Budget indirect costs initially miscalculated @ 20% for STFC partner
ALL PARTNERS | Y3 plan | Y3 used | % used
PMs | 56 | 59 | 105%
Personnel Costs | 323,399 | 330,607 | 102%
Travel | 26,220 | 35,404 | 135%
Other including e-concertation meeting | 76,366 | 25,389 | 33%
Subcontracting | 0 | 4,335 | exhausted
Total Direct Costs | 422,880 | 395,735 | 94%
Indirect costs | 87,227 | 139,497 | 160%
Total Eligible Costs | 510,079 | 535,231 | 105%
Max. EC Requested Contribution | 452,574 | 420,233 | 93%
Per cost category
ALL PARTNERS | Total Project | Total used | % Total used
PMs | 179 | 182 | 102%
Personnel Costs | 995,325 | 1,002,533 | 101%
Travel | 87,546 | 96,728 | 110%
Other including e-concertation meeting | 119,000 | 68,023 | 57%
Subcontracting | 14,000 | 21,441 | 153%
Total Direct Costs | 1,215,872 | 1,188,725 | 98%
Indirect costs | 240,374 | 294,644 | 123%
Total Eligible Costs | 1,456,245 | 1,483,398 | 102%
Max. EC Requested Contribution | 1,300,000 | 1,267,658 | 98%
Total project
Total project:
Personnel & travel costs linear with plan
Other costs reconsidered as subcontracting
Total budget balanced
Note: travel costs for EC review participation not claimed yet. Amended costs claimed will be submitted after the review.

## Slide 9: Partners Y3-Total expenditure
Overall at 93% of planned spend for PY3
Per Partner
Overall at 98% of funding planned for the total project
Chart: Total Project Use of Budget per partner
| EGI.eu | QMUL | APO | Imperial | CERN
Total Funding Planned (Amendment N2) | 230494 | 285688 | 211057 | 108831 | 463930
Total Funding Used | 220525 | 262341 | 196634 | 104603 | 483554
% | 0.95675 | 0.91828 | 0.93166 | 0.96115 | 1.0423
Chart: PY3 actual costs per partner
| EGI.eu | QMUL | APO | Imperial | CERN
Funding planned Y3 | 92212 | 130548 | 78344 | 46088 | 105384
Funding requested Y3 | 82243 | 107201 | 63921 | 41860 | 125008
Y3 % | 0.89189 | 0.82116 | 0.8159 | 0.90826 | 1.1862

## Slide 10: Expenditure e-Concertation meetings
€40K is allocated in the DoW for the e-Infrastructure concertation events to fund logistical costs such as catering, travel and venue costs.
This is allocated as €35K to EGI.eu under WP4 and €5K to QMUL under WP1. (DoW version1/03/2013)
Costs for 10th Concertation meeting, 6-7 March 2013 met by EGI.eu as organisers of the event
Description | Cost (Euros) | 
Day Delegate Package include Wi-Fi, security, cleaning catering (85€) | 10,200 € | based 120 attendees
Venue main room | 2,850 € | based 2 days
Audio-visual equipment | 865 € | based 120 attendees
Breaks 10€ | 1,200 € | based 120 attendees
Cocktail | 3,660 € | based 120 attendees
TOTAL | 18,775 € | Of which VAT not eligible 2,689€
10th CONCERTATION MEETING
TOTAL COSTS OF THE 3 EVENTS:
8th CONCERTATION MEETING costs: 6,809 €
9th CONCERTATION MEETING costs: 18,043 €
10th CONCERTATION MEETING costs: 16,086 €
Total costs: 40,938 € (exc. VAT)

## Slide 11
www.e-sciencetalk.eu
Deliverables and Milestones

## Slide 12: Review process
Internal draft ready by day 1 of the PM the report is due
Document internally reviewed by the e-ScienceTalk team – 2 weeks
Document reviewed by the PMB – 1 week
Document submitted at the end of the PM the report is due

## Slide 13: Deliverables
Del. no. | Deliverable name | WP no. | Lead beneficiary |  | Delivery date (PM) | Actual delivery date | Status | Comments
D3.1 | Weekly issues of iSGTW | 3 | CERN | R | 1-33 | 25-35 | Submitted | 
D1.2.9 | e-ScienceBriefings | 1, 2 | QMUL | R | 25 | 25 | Submitted | 
D1.2.10 | e-ScienceBriefings | 1, 2 | QMUL | R | 28 | 28 | Submitted | 
D1.2.11 | e-ScienceBriefings | 1, 2 | QMUL | R | 30 | 30 | Submitted | 
D1.2.12 | e-ScienceBriefings | 1, 2 | QMUL | R | 32 | 32 | Submitted | 
D3.6 | Report on survey of iSGTW readers and annual metrics | 3 | CERN | R | 33 | 33 | Submitted | 
D1.6 | Briefing final summary | 1,2 | QMUL | R | 34 | 34 | Submitted | 
D2.4 | Annual upgraded version of the RTM | 2 | APO | O | 34 | 34 | Submitted | 
D2.5 | Final dissemination report on GridCafe, GridGuide and GridCast | 2 | APO | R | 34 | 34 | Submitted | 
D2.6 | Schools pack based on e-ScienceCity | 1,2 | QMUL | R | 34 | 34 | Submitted | 
D3.7 | Final report on iSGTW marketing | 3 | CERN | R | 34 | 34 | Submitted | 
D4.5 | Final report on feedback and metrics | 4 | EGI.eu | R | 34 | 36 | Submitted | Moved to include final figures
D1.5 | Final report on impact and sustainability | 1 | QMUL | R | 35 | 36 | Submitted | End of project report
D4.6 | Guide to dissemination for EU projects | 4 | EGI.eu | R | 35 | 36 | Submitted | End of project report

## Slide 14: Milestones
Milestone no. | Milestone name | Work package no | Lead beneficiary | Delivery date from Annex I PM | Achieved Yes/No | Actual / achievement date | Comments
MS10.7 | PMB meetings | 4 | EGI.eu | 25 | Yes | 26 | 
MS4 | GridCast | 2 | APO | 26 | Yes | 26 | 
MS7 | Posters and marketing materials | 3, 2 | APO | 27 | Yes | 27 | 
MS10.10 | PMB meetings | 4 | EGI.eu | 28 | Yes | 29 | Diary issue
MS4 | GridCasts | 2 | APO | 29 | Yes | 30 | Event calendar
MS15 | Dissemination materials | 4 | EGI.eu | 30 | Yes | 30 | 
MS3 | 10th e-Concertation meeting | 1,2,3 | EGI.eu | 31 | Yes | 31 | 
MS7 | Posters and marketing materials | 3,2 | APO | 31 | Yes | 31 | 
MS10.11 | PMB meeting | 4 | EGI.eu | 31 | Yes | 31 | 
MS4 | GridCasts | 2 | APO | 32 | Yes | 32 | 
MS6 | GridGuide expanded to 100 sites | 2 | APO | 33 | Yes | 33 | 
MS10.12 | PMB meeting | 4 | EGI.eu | 34 | Yes | 34 | 
MS4 | GridCasts | 2 | APO | 35 | Yes | 35 | 
MS7 | Posters and marketing materials | 3,2 | APO | 35 | Yes | 35 | 
MS9 | Increase iSGTW readership by 15% | 3 | CERN | 35 | Yes | 35 | Achieved PM28

## Slide 15
www.e-sciencetalk.eu
Project metrics

## Slide 16: Project metrics
Recommendations from reviewers:
  Define what constitutes impact
  Include more detail on the outcomes and outputs of the products
  Track cross fertilisation amongst the e-ScienceTalk products
  Report metrics based on activities at events
Final Deliverables on Impact (D1.5) and Metrics (D4.5)
Project and work package level metrics gathered quarterly
Small changes to the metrics for PY3 were included in D4.4

## Slide 17: Project metrics PY3
Work Package | Metric no. | Description | Target Metric | Comments
WP1 | 1.1 | Projects covered | 40 per year | Increased from 30
 | 1.2 | Reports and briefings published | 4 per year | Adjusted to number of reports published not printed
 | 1.3 | Countries where reports or briefings are distributed | 30 per year | Unchanged
WP2 | 2.1 | Sites on GridGuide | 75 | Unchanged
 | 2.2 | Bloggers contributing to GridCasts | 5 per GridCast | Unchanged
 | 2.3 | GridCasts per year | 4 in Europe per year, 1 outside Europe | Unchanged
 | 2.4 | New areas in GridCafé | 3, one new area per year | Unchanged
WP3 | 3.1 | iSGTW subscribers | 30% increase | Including social media followers
 | 3.2 | Articles on European projects | 50 per year | Unchanged
 | 3.3 | Projects in the iSGTW/GridCafé resources section | 150 in total | Unchanged
 | 3.4 | iSGTW printed materials distributed | 1000 in total | Unchanged

## Slide 18: Project Metrics PY3
WP | No. | Description | PY3 Target | PY1 | PY2 | PY3
WP1 | 1.1 | Projects covered | 40 per year | 38 (190%) | 74 (250%) | 59 (148%)
 | 1.2 | Reports and briefings circulated | 4 per year | 300 (75%) | 4 (100%) | 4 (100%)
 | 1.3 | Countries where reports or briefings are distributed | 30 per year | 36 (120%) | 32 (107%) | 37 (123%)
WP2 | 2.1 | Sites on GridGuide | 75 | 38 (50%) | 59 (78%) | 102 (102%)
 | 2.2 | Bloggers contributing to GridCasts | 5 per GridCast | 5 (100%) | 6 (120%) | 6 (120%)
 | 2.3 | GridCasts per year | 4 in Europe per year, 1 outside Europe | 16 (533%) | 16 (250%) | 16 (250%)
 | 2.4 | New areas in eScienceCity | 3, one per year | 1 (100%) | 2 (200) | 1 (100%)
WP3 | 3.1 | iSGTW subscribers | 30% increase | 21% (70%) | 28% (95%) | 30% (100%)
 | 3.2 | Articles on European projects | 50 per year | 108 (216%) | 131 (261) | 71 (142%)
 | 3.3 | Projects in the iSGTW/GridCafé resources | 150 in total | 134 (134%) | 134 (89%) | 64 (43%)
 | 3.4 | iSGTW printed materials distributed | 1000 in total | 330 (33%) | 610 (61%) | 616 (62%)

## Slide 19: Project Metrics PY3
WP | No. | Description | PY3 Target | PY1 | PY2 | PY3
WP1 | 1.1 | Projects covered | 30 per year | 38 (190%) | 74 (250%) | 59 (148%)
 | 1.2 | Reports and briefings circulated | 4 per year | 300 (75%) | 4 (100%) | 4 (100%)
 | 1.3 | Countries where reports or briefings are distributed | 30 per year | 36 (120%) | 32 (107%) | 37 (123%)
WP2 | 2.1 | Sites on GridGuide | 75 | 38 (50%) | 59 (78%) | 102 (102%)
 | 2.2 | Bloggers contributing to GridCasts | 5 per GridCast | 5 (100%) | 6 (120%) | 6 (120%)
 | 2.3 | GridCasts per year | 4 in Europe per year, 1 outside Europe | 16 (533%) | 16 (250%) | 16 (250%)
 | 2.4 | New areas in eScienceCity | 3, one per year | 1 (100%) | 2 (200) | 1 (100%)
WP3 | 3.1 | iSGTW subscribers | 30% increase | 21% (70%) | 28% (95%) | 30% (100%)
 | 3.2 | Articles on European projects | 50 per year | 108 (216%) | 131 (261) | 71 (142%)
 | 3.3 | Projects in the iSGTW/GridCafé resources | 150 in total | 134 (134%) | 134 (89%) | 64 (43%)
 | 3.4 | iSGTW printed materials distributed | 1000 in total | 330 (33%) | 610 (61%) | 616 (62%)

## Slide 20
www.e-sciencetalk.eu
WP4 achievements and project issues

## Slide 21: WP4: Major achievements
Administration:
  PY3 DoW amendment completed in April 2013
  PY2 costs accepted and remaining payments processed
  PMB meetings held, risk register monitored
  Project team changed, including recruitment of iSGTW US Editor (Indiana) and departure of Science Writer (CERN)
  Project closure activities, including final cost claims and final reports
Presentations about the project at:
  EGI Technical Forum 2012 - Prague, eChallenges2012 - Lisbon, 10th e-Infrastructure Concertation Meeting – Brussels, ISGC’13 - Taipei
Additional activities:
  Quarterly Reports prepared for Q9-11 in addition to agreed Deliverables and Milestones
  Media training carried out at EUDAT 1st Conference, ESRF, CRISP meeting
  Training materials added to the Guide to Dissemination for EC projects (D1.6)

## Slide 22: WP4: Major achievements
MoUs signed with 3 collaborating projects:
  Outreach: iMENTORS
  Regional infrastructures: Ubuntunet
  Policy: BlogForever
International collaborations:
  Project Coordinator is current Chair of EU/US/Asia iSGTW Advisory Board
  Programme Committee for the 12th International Symposium on Grids and Clouds 2013, Taipei
  Media partner for XSEDE’13, ISC’13, SC’13 (under discussion)
  Networking session at ICT’13 in November 2013 with CHAIN-REDS, iMENTORS, e4AFRICA, EGI-InSPIRE on the future of Big Data
Events organisation:
  Logistics for 10th e-Infrastructure Concertation event in Brussels, March 2013
  FP7 Success Story competition
  Preparation of event budgets, registration, costs
Notes: Highlight MoU projects GlobalExcursion, Virtus, CRISP

## Slide 23: Project issues - resolved
Ensuring a good balance of information and contributions from collaborating projects eg for e-ScienceBriefings – many projects covered
Slow addition of new sites for the GridGuide – target achieved, added to eScienceCity
Sustainability of iSGTW US funding and recruitment of US Editors – funding in place for 3 years, new Editor up to speed
High travel costs for all work packages due to late booking of travel – on budget
iSGTW subscriber numbers are not representative of the wider readership achieved – social media and web stats give a more accurate picture
Euro/CHF exchange rate for WP3 – on budget with costs balanced
Redistribution of underspent funds in final 9 months - achieved

## Slide 24: Project issues - ongoing
Sustainability of iSGTW EU funding and recruitment of AP Editors
New name for iSGTW could be considered for another project
Identification of funding for the costs of day to day maintenance of the iSGTW website by Xenomedia, once Fermilab funding ceases.
Relationship management within the iSGTW team across the US and EU Editorial desks
Adding Russian, Chinese and other non-Roman languages to the GridCafé database.
Displaying jobs from other, non-gLite sources in the RTM.

## Slide 25: Summary
Close of PY2 achieved successfully, including final DoW amendment
Recruitment to US iSGTW Editor
Overall at 82% of planned effort for WP1-4
Funded effort at 87% of planned effort for WP1-4
Final costs at 98% of planned levels
Most Deliverables and Milestones submitted on time, or early
MoUs signed in PY3 and ongoing international collaborations
Project level metrics largely met or exceeded
High impact for the project in PY3
Sustainability plan beyond PY3 now in action

## Slide 26
www.e-sciencetalk.eu
Additional slides

## Slide 27: Metrics for WP1
Metric no. | Description | Comments | Q9 | Q10 | Q11 | TOTAL
1.1 | Projects covered | In the e-ScienceBriefings | 12 | 30 (19+11) | 17 | 59
1.2 | Reports and briefings published | In print or by email | 1 | 2 | 1 | 4
1.3 | Countries where reports or briefings are distributed | In print or by email | 13 | 46 | 10 | 37
1.4 | Policy articles published | In print or online | 2 | 4 | 2 | 8
1.5 | Printed policy reports circulated per briefing | To policy makers | 100 | 200 | 100 | 400
1.6 | Policy events organised | Number organised | 0 | 1 | 0 | 1
1.7 | Attendees at e-ScienceTalk organised policy events | Number of delegates | 0 | 132 | 0 | 132
1.8 | Policy events attended by e-ScienceTalk | Number attended, physically or virtually | 3 | 3 | 2 | 8
1.9 | Delegates at policy events attended by e-ScienceTalk | Number of delegates at events attended. | 500 | 400 | 350 | 1250
1.10 | Downloads of policy documents (cumulative) | Measured from the e-ScienceTalk web site | 9128 | 11054 | 13119 | 13119
1.11 | Training sessions / talks delivered | New metric | 2 | 1 | 1 | 4

## Slide 28: Metrics for WP2
Metric no. | Description | Comments | Q9 | Q10 | Q11 | TOTAL
2.1 | Sites on GridGuide | Number of sites included | 0 | 10 | 17 | 102
2.2 | Bloggers contributing to GridCasts | Average number of bloggers on GridCast | 6 | 3 (mini) | 5 | 6
2.3 | GridCasts per year | Including major and mini GridCasts | 4 | 5 | 7 | 16
2.4 | New areas of GridCafé | Covering topics other than grid computing | 0 | 1 | 0 | 1
2.5 | Change in unique visitors to the GridCafé website | From Google Analytics | 3608 (+86% from 1935) | 3357 (-7%) | 4324 (+29%) | 3763 average (+69% from 2224)
2.6 | Ratio of page views to visitors for the GridCafé website | From Google Analytics | 3.13 | 2.79 | 2.58 | 2.83
2.7 | Number of bloggers for GridCast | Total number of bloggers | 7 | 5 | 8 | 20
2.8 | Blog entries on GridCast | Total number | 44 | 32 | 39 | 115
2.9 | Podcasts on GridCasts | Total number | 7 | 5 | 19 | 31
2.10 | Unique visitors to the GridCast (% new) | From Google Analytics | 75.3 | 82.3 | 76.7 | 78%
2.11 | Length of time spent on the GridCast | From Google Analytics | 1:17 | 1:11 | 1:42 | 1:23
2.12 | EU sites on GridGuide | European based sites | 36 | 45 | 53 | 53
2.13 | Non-EU sites on GridGuide | Non-European located sites | 23 | 26 | 49 | 49

## Slide 29: Metrics for WP2
Metric no. | Description | Comments | Q9 | Q10 | Q11 | TOTAL
2.14 | Unique visitors to the GridGuide | From Google Analytics | 296 | 114 | 149 | 559
2.15 | Page views of the GridGuide | From Google Analytics | 403 | 157 | 383 | 943
2.16 | GridGuide sites on RTM | Total number | 59 | 59 | 59 | 59
2.17 | Countries in the RTM | Total number | 54 | 54 | 54 | 54
2.18 | Numbers of delegates at events demo-ing the RTM | Including events attended by collaborating projects demo-ing the RTM | 300 | 10400 | 40 | 10740

## Slide 30: Metrics for WP3
Metric no. | Description | Comments | Q9 | Q10 | Q11 | TOTAL
3.1 | iSGTW subscribers | Registered in the database | 8249 | 8706 | 8770 | 8770
3.2 | Articles on European projects | Based on EU funded projects | 27 | 18 | 26 | 71
3.3 | Projects in the iSGTW/GridCafé resources section | Total number | 64 (non added this quarter) | 64 | 64 | 64
3.4 | iSGTW printed materials distributed | At events attended by e-ScienceTalk or by collaborating projects | Total of 616 (up 6 this quarter) | 616 | 616 | 616
3.5 | Issues published | Issued by email to subscribers each week and posted on the website | 13 | 11 | 13 | 37
3.6 | US articles published | Based on US projects | 44 | 18 | 23 | 85
3.7 | Worldwide articles published | Based on non US or EU projects | 12 | 4 | 8 | 24
3.8 | Unique visitors to the website | From Google Analytics | 43,235 | 54,038 | 54,011 | 50,428
3.9 | Page views of the website | From Google Analytics | 88,752 | 141,325 | 207,247 | 145,775 average
3.10 | Countries visiting the iSGTW website | From Google Analytics | 179 | 176 | 182 | 179 average
3.11 | Marketing materials distributed | In print or by email or at events | 4 | 5 | 7 | 16
3.12 | Survey responses | Through Zoomerang survey tool | 0 | 113 | 0 | 113

## Slide 31: Metrics for WP3
Metric no. | Description | Comments | Q9 | Q10 | Q11 | TOTAL
3.13 | Social media subscribers | On Twitter and Facebook | 1394 Twitter + 709 Facebook | 1545 Twitter + 925 Facebook | 1724 Twitter + 1152 Facebook | 1724, 1152
3.14 | Time spent on the site per visit (minutes) | From Google Analytics | 1:55 | 2:11 | 3:20 | 2:29 average
3.15 | Stories shared on social media | Via all social media channels | 495 | 494 | 327 | 1316

## Slide 32: Metrics for WP4
Metric no. | Description | Comments | Q9 | Q10 | Q11 | TOTAL
4.1 | Deliverables submitted | By email and online | 1 | 3 | 1 | 4
4.2 | Milestones agreed | By email and online | 4 | 3 | 0 | 7
4.3 | Late Deliverable and Milestones | Submitted or agreed after the date agreed with the EC | 0 | 0 | 0 | 0
4.4 | e-ScienceTalk materials produced | Included printed materials, pens, banners etc | 500 pens 200 badges | 0 | 300 lanyards | 1000 items
4.5 | Unique visitors to the e-ScienceTalk website | From Google Analytics | 409 | 357 | 447 | 1213
4.6 | Referrals from the e-ScienceTalk website to other e-ScienceTalk sites | From Google Analytics | 145 | 115 | 133 | 393
4.7 | Media releases issued | Issued via Alphagalileo and by email | 0 | 0 | 0 | 0
4.8 | Press cuttings | Measured by Google Alerts | 1 | 0 | 1 | 2
4.9 | Events attended | By e-ScienceTalk project team | 6 | 3 | 6 | 15
4.10 | Social media subscribers | On Twitter | 2059 | 2143 | 2217 | 2217
4.11 | Media partnerships at events | Number of events with e-ScienceTalk as media partners | 3 | 1 | 3 | 7
4.12 | Number of MoUs signed | With collaborating projects | 0 | 1 | 1 | 3