## Slide 1: NIL meeting EGI Engagement Strategy https://documents.egi.eu/document/2079
Update – 19/March/2014
Gergely Sipos
gergely.sipos@egi.eu

## Slide 2: Goals
Engagement with new users
  Research Infrastructures
  ‘Smaller’ research collaborations/projects
Support and coordinate our human networks
  NGIs (NILs)
  Existing communities (UCB)
  New communities (Champions)
  Technology teams (DCC)
Intensify engagement activities in 2014

## Slide 3: Strategy document
https://documents.egi.eu/document/2079
  Was presented to the Council on the 27th of February
Not only a strategy, but also
  Description of responsibilities and support tools
  Specific plans for a three months period
  Metrics
New issue every three months
  First issue: January 2014
  Next issue: Second half of April
  Continuous updates in between
Update through the EGI Engagement Advisory Board
  NILs, UCB, Champions, EGI.eu members, EAB, NA2 managers

## Slide 4: Engagement Process
Increased and diversified use of EGI (VOs, applications, users)
time
Communication, Marketing, Proactive outreach
Virtual Team project formulation
Virtual Team project execution
Outreach
Scoping
Implementation
What
How
Outcome
Who
NILs, Champions, UCB, DCC, EGI.eu, council, NGIs
DCC, NILs, EGI.eu
DCC, NGIs, EGI.eu
Interested new users
Endorsed project plans
Formalised support projects
Awareness and interest in EGI services
Feedback (success cases, new champions, etc.)

## Slide 5: Document updates since last meeting
Updates based on feedback from Genevieve Romier
Several new entries in the NGI engagement tables (both to the ESFRI and the Community tables)

## Slide 6: Specific goals for the Feb-April period
In four areas:
  Outreach (Neasan)
  Scoping (Nuno)
  Implementation (Gergely)
  Cross-cutting (Gergely, Diego)

## Slide 7: Progress with Outreach goals (Neasan)
Full portfolio of materials around the 5 EGI Solutions.
Re-scope the 5 solutions as text that can be “plugged into” H2020 proposals.
Run two webinars based on EGI services and solutions.
Prepare two webinars for May and June.
Prepare materials for the European Geological Union General Assembly.
Prepare materials for European Conference on Computational Biology, the 18th European Bioenergetics Conference and the Federation of European Biochemical Societies.
Prepare a requirements capturing form to support the collection of requirements during face-to-face interviews.
LSGC to prepare for the organisation of the 'Workshop on Clusters, Clouds and Grids for Health (with CCGrid) in Chicago on May 26, 2014.

## Slide 8: Progress with Scoping goals (Nuno)
By the middle of February teleconferences to discuss possible VTs for:
    CLARIN, ICOS, LifeWatch
    Astro, Sequencing & proteine folding, Env. Sci.
By the end of February teleconferences to discuss possible VTs for:
    EMSO, EPOS, EuroBioImaging, IAGOS, Instruct, SKA
    Agriculture, Manufacturing
Define at least 4 VTs from #1 and #2.
Define at least one other VT from the DIRAC-community engagement

## Slide 9: Progress with Implementation goals (Gergely)
Formally close the CTA VT (SCI-BUS MoU, Portal setup from SCI-BUS-InSilicoLab)
  MoU will not be signed (at the moment) between CTA and SCI-BUS
Formally close the ELIXIR VT and agree on follow-up actions
  Two ‘pathfinder’ pilots with support of EGI, linked to ‘EnlightYourReearch Global’ call:
Finish the CMMST VT, setup an action plan for VRC implementation
  Document has been finished, setup of VRC started. Sessions in Asia, US, Helsinki
Finish the Desktop Grid VT
  Hear later
Continue the ENVRI Study and DRIHM collaborations
  Successful demonstration at ENVRI meeting in Helsinki
  Teleconference next week for a status update on the DRIHM gateway and workflow setups
Obtain status on EGI-EUDAT-PRACE pilots and agree on next steps
  Portal setup by SCI-BUS for CMMST and DRIHM jointly with XSEDE
Start implementing new VTs (received from Scoping)

## Slide 10: Cross-cutting (Gergely, Diego)
New ‘user-focussed’ EGI web portal
Identify a method to account for the usage of robot and short-lived certificates
Identify (setup?) tools and processes to recognise and collect NGI/EGI-related publications.
Identify additional targets for the Outreach process
  Proposed new VT: Business Engagement Programme for SMEs

## Slide 11: Other updates: Business Engagement Programme for SMEs
Javier

## Slide 12: Other updates: Report from the BioMedBridges AGM (Gergely)
10+3 RIs from the BMS domain
‘E-infrastructure advisory board’
  DANTE+GEANT, CSC, EGI, CERN
Developments:
  RI contact points towards e-infrastructures
  E-infrastructure awareness raising workshop
    Intros; ELIXIR technical topics; ‘Common challenges in data…’ cluster paper topics
    Identify topics and next steps in awareness raising and collaboration
  Importance of national linkage between RIs and e-infras
  ELIXIR technical stream
    list of topics for e-infrastructure collaboration
    ‘Cloud task force’ with EGI’s involvement
    Session at EGI Community Forum
  Managerial leads to BBMRI and Euro-BioImaging

## Slide 13: Other updates: DG VT (Robert)

## Slide 14: NIL reports

## Slide 15: EGI CF
Overview (Sara)
NIL meeting - EGI Engagement (Monday afternoon)
User training (90 minutes on Monday afternoon – not yet in the programme)
  Structure – similar to 2010 TF: https://indico.egi.eu/indico/sessionDisplay.py?sessionId=124&confId=48#20100914
  Grid and Cloud
  Trainers?

## Slide 16: AOB

## Slide 17: Next meetings https://indico.egi.eu/indico/categoryDisplay.py?categId=36
Apr 16 - Webex
Community Forum
  Engagement (NIL meeting), Helsinki (May 19)
Project final review (July 2-3)
  F2F NIL meeting July 1st
Dates proposed for after the summer
  all 2pm Ams
  17 Sep, 22 Oct, 19 Nov, 17 Dec