## Slide 1: e-Connecting Scientists
EGI – DIRAC Collaboration
(R. Graciani)
Jan 14th 2014

## Slide 2: Summary
Target:
  Connect researches to e-Infrastructure: single entry point
How:
  Provide a service for anyone interested (VOs and SSO) connecting to grid, cloud, hpc, desktop grid,.. Not forgetting to integrate Storage
  Provide support to users and communities for the integration, helping them to break the gap
  Help others to help themselves and, thus, yourself
Impact:
  Integrate all fields of research
  Avoid digital-divide in Europe Research

## Slide 3: WorkPlan
DIRAC Pilot Service:
  Work in progress
  Report from: Gilles Mathieu
Integrate Communities:
  1 day meeting (Jan 13th 2014), thanks
  Report from: R. G.
Move into Production:
  Define activity, tasks, impact, … (VT / DCC / MP)
  Some tasks identified
  Report by: R. G.
Disseminate:
  Important dates

## Slide 4: DIRAC 4 EGI Dissemination
EGI News letter (dead line Jan 17th )
  Report activity, raise awareness and look for new contributions
EGI Community Forum (F2F meeting) 19-23 May
  F2F with new interested users
    Hackathons (deadline Feb 15th)
  Dedicated Session (requested)
    Report on activity and discuss next steps
    Contributions welcomed (deadline Feb 16th)
  Tutorial (requested)
    For end users
ISGC Taiwan, March (accepted) 23-28 Mar
  Connect DIRAC – EGI activity with Asian-Pacific

## Slide 6: Identified Tasks
Integrate into EGI Accounting
  Report multi user usage inside pilots and VMs
  CESGA/RAL will provide support
  1-2 month, 25-50 %
Monitoring
  Service End points/Full chain Probes
  EGI will provide support (?)
  1-2 month, 25-50 %
Software Assurance
  Vulnerability
  UAB will provide support
  6-12 month, 50-100 %
Collaborate with communities
  User support / contact with Resource Providers
  TBD
Run the DIRAC services
  Monitoring shifts/contact
  France-Grilles / DIRAC will provide support
  Team of 5-6 people with 25 %

## Slide 7: Next meetings
Dedicated meetings with communities
  Continuation of F2F meeting
  Details later
February Follow up (virtual ): 1 hour
  Feb 10-12
March F2F Follow up (Barcelona?): 1 day
  Mar 13-14
April Follow up (virtual): 1 hour
  Apr 10-11
May Follow up
  EGI CF