| Meeting | PMB |
| --- | --- |
| Editor | Catherine Gater |
| Meeting date | 1 September, 2010 |
| Attendees | EGI.eu: Steven Newhouse, Catherine Gater QMUL: Sarah Pearce APO: Andre-Pierre Olivier Imperial: David Colling CERN: Bob Jones |
| Apologies |  |
| Absent |  |
| Distribution | PMB members |

1. Election of PMB Chair

CG proposed Sarah Pearce as Chair, Sarah unanimously elected as Chair for the first year of e-ScienceTalk.

2. Minutes of the last meeting

No previous minutes to review

3. Report from PM

WP1

- GridBriefings. First one should be about the evolution of e-Infrastructure in Europe - view of the landscape, where are we going etc.

- Joint DCI deliverable from EGI-InSPIRE, EMI etc due at the end of September, could use this as a basis for the technical information.

- Blue Paper from e-IRG also due, covering more strategic picture.

- Combine the two into the GridBriefing

- Get feedback from the EC/PERT members about GridBriefings to inform future issues.

- DEISA/PRACE GridBriefing is one that can kept for later eg for ISC in June 2011

- PERT should keep continuity with those members still involved in the area.

- For e-IRG clarify what is happening with the e-iRG chairmanship with start of eIRG_SP. Leif or Patrick Aerts? Bob to confirm at EGITF

- Add other DCI projects such as EMI and EGI-InSPIRE to the PERT.

- Do one to one feedback interviews at EGITF2010.

WP2

- Add a partners page to the website

- Respond to the reviewers’ recommendation on making the project website more prominent

- Should look like the website for a professional communications project

- Could federate other feeds ie iSGTW headlines, GridCafe news

- Should also feature project news eg launch of new Gridbriefing, new Gridcast etc.

- Add links to e-ScienceTalk social media sites

- First step is to move across existing content then evolve the site.

- GridGuide site of the month is now NIKHEF. Review depending on status of Tier 1 site.

WP3

- Recruitment to iSGTW editor post is underway, replacing Dan at the end of April 2011.

- Deadline for CERN committee recruitment of fellows is 7 September.

- Too soon to advertise properly among our contacts, recruit outside committee with our own CERN panel.

- Review iSGTW board membership

US

Katie Yukowicz - confirm that she is US side

Ruth Pordes

[Judy Jackson (retiring)]

Dave Richie

Paul Avery

EU

Sarah

Catherine

Bob

James Gillies

- Propose to replace Sara as PM and QMUL rep with Steven as rep of the coordinating partner EGI.eu.

- CG no longer represents EGI.eu as she is PM

- CG to draft an email introducing the project to the iSGTW Board members and circulate to the PMB for comments.

- First step towards proposing new board member and announcing Dan's departure.

WP4

- CA close to signature, just need to iron out small remaining comments from CERN and Imperial.

- Suggest phone meeting if this can't be done by email.

- Budget- can IC confirm the exchange rate that will be used? Probably 1.2 which may lead to an underspend as for GridTalk.

- Exchange rate should be reviewed each year

4. Status of Deliverables and Milestones

Covered in the PMs report.

5. Review of risk register

Part reviewed at the end of the meeting, comments to be sent to CG offline.

6. Project Issues

iSGTW revamp

- Dan to send the technical  specification to the PMB for final comments before sharing with Miriam

- Should agree the top priorities in case not everything can be done with the time/budget available.

3D report

- APO would like to redistribute this, need to ask EC as it is a formal deliverable with restricted access to consortium members.

REvamps of other products

- All plans ie new areas of GridCafe etc should be reviewed by the PMB before implementation.

- Bob to send Emilie's report on IP to CG- contains recommendations for implementing the copyright report proposals

- Should distinguish between branding elements (which should not be edited or changed), content created by the eST consortium (Creative Commons) and content provided by others (should be protected)

- CG to produce firm proposal on Creative Commons issues to next PMB

- CG to produce dissemination plan that contains firmer schedules on rebranding items eg Gridbriefings, cloud lounge in GridCafe.

- SP requests fairly immediate review of content to remove obviously out of date elements ie refer to EGEE in past tense.

BELIEF Digital Library

- BJ recommends to fill this requirement in the DoW as quickly as possible.

- BJ to speak to Tim Smith from OPENAire project to find out if their orphans datebase based on CDS Invenio (used by CERN library) could be used.

- OPENAire could use digital library as a case study for the training at the concertation event for example

GLOBAL

- Concertation meeting will use CERN webcasting system.

- Other meetings should look at other options not necessarily GLOBAL.

Press release

- For release during CCC on Friday 3 Sep to announce project launch

- CG to check if the Project Officer is happy with this, what approval is needed.

- PMB to send comments on text by Thursday lunchtime

- SP to provide a quote about the GT review

- DC to provide RTM text

7. AOB

No other business

8. Date of next meeting

4th November 2010, 9-11am, CERN (before Concertation Meeting)