## Slide 1: EGI-Engage
T. Ferrari/EGI.eu

## Slide 2: EGI-Engage
Project proposal name: EGI-Engage
Duration: 30 months
Call: WP 2014-2015, EINFRA-1 topic, activity 6
Expected start: 01 January 2015
Maximum budget: 8 MEuro

## Slide 3: EGI-Engage
March. Consultation with council members  objectives agreed
  Coordination of operations, software provisioning, tool development, user engagement
  User-driven innovation for provisioning of new services (compute and data)
    Development of the grid and cloud platforms, development of the core infrastructure platform, integration of Virtual research Environments to the EGI services  Competence Centres
    Design  development  testing and validation  pre-deployment  service provisioning and sustainability
  EGI market place and business development
  International cooperation with other e-Infrastructures
Consortium
  Strong user community participation, service providers (NGIs, EIROs), technology providers

## Slide 4: Not included
EGI central operations services
  No longer supported through EC funding as of 01 May
  Relying on EGI council fees (40%) and NGI in-kind contributions (total cost: 1.5 MEuro) https://wiki.egi.eu/wiki/Core_EGI_Activities
  Letters of agreement with the partners being prepared
NGI operations
  35% EC funding in EGI-InSPIRE, until end of April 2014

## Slide 5: Timeline
01/05/2014 – 08/06/2014 Open call for EGI Competence Centres
22/05: Concertation meeting at Community Forum 2014, hosted by the EGI Council Workshop, presentation of CC projects and discussion
09-30/06: Peer Review
Proposal preparation
  I draft for council discussion at the May meeting (CF2014)
  30/06: II draft for council review
  31/07: III draft + budget