## Slide 1: EGI-InSPIRE: Overview, Finance and Results
Tiziana Ferrari
EGI.eu Technical Director
Tiziana.Ferrari@egi.eu
EGI-InSPIRE Final Review
Amsterdam, 13 February 2015

## Slide 2: Outline
Project and financial overview
Progress in PY5
Results and impact

## Slide 3: Project effort and financial overview
Celine Bitoune
Chief Finance Officer/EGI.eu

## Slide 4: PY5 at a glance
PY5 participants: 30
PY5 PMs reported = 417PMs / 52 FTEs
PY5 estimate funding planned: 1,988,800 €
PY5 Provisional Financial status: 1,573,193 € requested
  Missing costs for GRNET (175k), CNRS (71k), CYFRONET (90k), STFC (190k)
Financial session deadline: 28-02-15 (60 days after the end of the project 31-12-14)
Over reporting partners: Proposal for redistribution if funding left
Advance payments:
  95% of advance received has been distributed (20,253,817 €)
  PY4 Payment submitted to EC – Nov 14: 1,000,514 €
  Final payment in 2015: 3,749,778 €
Final deliverable: Final distribution to the grant 30 days after release of final payment

## Slide 5: PY5 Consumed Effort
Type | Work Package | Worked PM Funded | Committed PM | Achieved PM%
MGT | WP1-M | 33 | 35 | 93%
COORD | WP9 | 197 | 207 | 95%
COORD | WP10 | 38 | 39 | 96%
OTHER | WP11 | 83 | 116 | 72%
RTD | WP12 | 66 | 59 | 112%
Total: |  | 417 | 456 | 91%
Chart: 
| WP1-M | WP9-NA4 | WP10-NA5 | WP11-SA5 | WP12-JRA2
PY5 planned efforts | 35 | 207 | 39 | 116 | 59
PY5 efforts used | 33 | 197 | 38 | 83 | 66
WP1  NA1 Management
PMs left used for report and costs
preparation
WP9  NA4 Community management
WP10  NA5 Strategy, Policy and Business
Development
WP11  SA5 Federated Cloud
WP12 JRA2 Tool Development

## Slide 6: PY5 funding per activity
Type | Work Package | Worked PM Funded | PY5 Eligible Cost Estimate | PY5 Estimated Funding
MGT | WP1-M | 33 | 293,040 | 293,040
COORD | WP9 | 197 | 1,470,945 | 735,473
COORD | WP10 | 38 | 295,305 | 147,652
OTHER | WP11 | 83 | 599,018 | 299,509
RTD | WP12 | 66 | 505,942 | 252,971
Total: |  | 417 | 3,164,250 | 1,728,645
WP1  NA1 Management 100%
WP9  NA4 Community management 50%
WP10  NA5 Strategy, Policy and Business
Development 50%
WP11  SA5 Federated Cloud 50%
WP12  JRA2 Tool Development 50%
Chart: 
| WP1-M | WP9 | WP10 | WP11 | WP12
PY5 Estimated Funding | 293040 | 735472 | 147652 | 299509 | 252971
 | 0.16952 | 0.42546 | 0.085415 | 0.17326 | 0.14634

## Slide 7: PY5 Deviations to plan
EGI.eu: few efforts left for preparation of the reports and FS (Jan-Feb 2015)
For partners who have submitted their Form C the project office has checked the deviation with the efforts declared and has reconciled costs and efforts:
  Task carried out consuming less efforts than planned
  Efforts not declared (new administrator at the partners’ level)
  Additional efforts to the initial plan were not charged in the costs;
  Reasonable overspending.
For inactive partners (no efforts reported), no Form C is expected (EMBL and JINR); payments were released up to PY1-PY3 costs accepted, thus there is no advance payment to reclaim
For two partners not participating in PY5 and underspending in PY4 have been reclaimed funding: UOBL-B&H (BE11) 771 € and ICI-Romania (BE51) 3,337 €

## Slide 8: PY1-PY5 use of funding
Participants including JRU members: 141 of which 95 funded
PMs: 9,463 / 168 FTE
Eligible costs: 71,039,803
Funding: 25,000,000 (35%)
Chart: Funding Y1-Y5
| Y1 | Y2 | Y3 | Y4 | Y5 requested | missing costs
Funding | 5275882 | 6978609 | 6186410 | 4463042 | 1573193 | 522866
#REF! | 1
PERIOD | FUNDING
PY1 | 5,275,882
PY2 | 6,978,609
PY3 | 6,186,410
PY4 | 4,463,042
PY5 requested | 1,573,193
PY5 missing costs | 522,866

## Slide 9: Progress in PY5

## Slide 10: Policy
REC 1. Develop and promote the Open Science Commons Vision
Researchers from all disciplines have easy, integrated and open access to the advanced digital services, scientific instruments, data, knowledge and expertise they need to collaborate to achieve excellence in science, research and innovation
www.opensciencecommons.org

## Slide 11
A new approach to digital research, tackling policy challenges and coupling the “open science” and the “commons” economy as a new paradigm for knowledge creation and collaboration in research
Requiring the involvement of
  E-Infrastructures
  Data providers
  Research Infrastructures
  Competence Centres
Digital services
Knowledge & Expertise
Data
Instruments

## Slide 12: Strategy
REC 2. Continue to develop the EGI Strategy
REC 4. KPI Metrics should be measured and evaluated in a wider context, in order to determine whether the organisation is heading in the right direction
Development of a new EGI strategy in progress
  Based on the Open Science Commons vision
  Participatory leadership
Increase skills among EGI.eu staff
Increase maturity of the strategic planning process
Improve quality of conversation on strategy
Improve communication of strategy
  Both internally and externally

## Slide 13: Timeline EGI strategy development
2.2010
5.2010
EGI-InSPIRE Kick-start
EGI.eu was born
4.2012
First EGI Strategy document: “Seeking new Horizons: EGI’s role in 2020”
10.2013
Update on the EGI strategy: “Secure, federated data-analysis capability for the European Research Area
4.2014
Full draft new EGI Strategy based on OSC vision & strategy workshop
11.2014
2.2015
Open Science Commons vision
Full draft new EGI Strategy based on OSC vision and workshop

## Slide 14: Sustainability 1/3
Recommendations from Pay-for-Use initiative
  43 individual participants and observers
    EGI.eu (Lead), Resource Centers, NGIs, Commercial Company
  Publishing Pricing Information
    30 Providers across 12 Countries
1st Business Engagement Programme
EGI and ESFRI RI: cross-border service procurement
  Collaboration with DARIAH, EPOS and LifeWatch
REC 7. Test business cases in commercial contexts as well as in ESFRI RI contexts

## Slide 15: Sustainability 2/3
New governance approved in Oct 2014
  Full participant and associate participant
  Revised simpler fee scheme (GDP-based)
  Extended full membership
    Europe and beyond
    ERICs and EIROs
REC 3. Sustainability planning needs more development, especially in respect of achieving longer-term sustainability

## Slide 16: Sustainability 3/4
EGI-InSPIRE
Core Activities
Plus NGI international tasks (65% NGI funding)
Plus funding of the running of the infrastructure (100% NGI funding)
New projects

## Slide 17: Sustainability of technical development
Chart: 
| 2004.0 | 2005.0 | 2006.0 | 2007.0 | 2008.0 | 2009.0 | 2010.0 | 2011.0 | 2012.0 | 2013.0 | 2014.0 | 2015.0 | 2016.0 | 2017.0
Core Platform Development | 7680000 | 7680000 | 5180000 | 5180000 | 4993562.7081 | 4993562.7081 | 2830000 | 2830000 | 2830000 | 852180.4999 | 252300 | 1539500 | 1539500 | 1539500
External Developments | 12000000 | 12000000 | 12000000 | 11100000 | 11100000 | 11100000
EGI-InSPIRE
New projects
EGI.eu-lead project
Non-lead projects (e.g. EMI, IGE, H2020)

## Slide 18: Status
NGI International tasks (operations, user engagement)
  no longer funded as of 01 May 2014
  But need of sustained support to human networks, especially user engagement, especially in countries with international user community not yet established
EGI Core Services
  Partly sustainable  Council fees and in-kind contributions
  https://wiki.egi.eu/wiki/Core_EGI_Activities

## Slide 19: Strategy
REC 5. Examine the planned Big Data SRIA and its relation to EGI and Open Science
Commons Big Data plans
Big Data Value Association
  (a) strengthening competitiveness and ensuring industrial leadership of providers and end users of BIG DATA VALUE technology
  (b) promoting the widest and best uptake of BIG DATA VALUE technologies and services for professional and private use;
  (c) establishing the excellence of the science base of creation of value from BIG DATA
Membership under evaluation in the context of the strategy being defined

## Slide 20: Results and impact

## Slide 21: All researchers
All researchers from all disciplines have access to the Commons

## Slide 22: Excellence in science
Collaborate to achieve
excellence in science, research and innovation

## Slide 23: Open access
Percentage of resources used by users from another country
Researchers from all disciplines have easy, integrated and open access  24 of transnational access
Notes: Researchers from all disciplines have easy, integrated and open access

## Slide 24: Digital services
Open access to the advanced
digital services, scientific instruments, data, knowledge and expertise
3600 service end-points (grid, cloud, storage and data management)
Registered applications  620
Natural Sciences 353
Medical and Health Sciences 124
Agricultural Sciences 9
Engineering and Technology 9
Other 126

## Slide 25: Outlook
The Open Science Commons are not yet a reality
  Technical integration barriers
  Fragmented landscape
    No governance and consistent access models
  Digital divide
  …
EGI-InSPIRE already allowed EGI to advance towards an Open Science Commons