## Slide 1: Disaster Mitigation Competence Centre Project Meeting Coordinator: Simon Lin
March 31, 2015

## Slide 2: Agenda
Partners Contributions & Refined Project Plan
  M12: Tsunami and Weather Simulation
Environmental Computing Workshop
Future Events and Next Meeting
AOB

## Slide 3: Goals: e-Science for the Masses
Objectives: improving strategy of prevention and reduction of disasters
  By better knowledge of the Earth’s physical phenomena, we can mitigate the consequences of similar disasters in the future.
  Advancement of prediction accuracy on target disasters
Approaches
  By estimating the natural hazards at a given site or by means of early warning systems, or forecasting the occurrence of the eventually generated disaster after the next strong events.
  Buildup the close collaboration of domain experts, e-Science service providers and e-infrastructure resource centers.
  Construct fast and accurate simulation by taking advantage of the domain knowledge and the e-Sciences
  Conduct simulation of combined disasters scenarios to verify the effectiveness of our design on potential cases

## Slide 4: 1. Earthquake & Tsunami (I)
Background
  Knowledge of past tsunamis is critical in identifying potential tsunami sources, understanding the focal mechanism, and developing mitigation plans
  Tsunami wave propagation simulation is essential to disaster warning and estimation
Tasks
  Potential tsunami scenarios identification: Manila Trench, Sunda Trench: PH, ID, VN, TW
  Tsunami Wave Propagation Simulation Web Portal: ASGC
  Historical Tsunami Records Collection and Inversion Simulation to identify potential tsunami sources: PH, ID, VN, TW
  Immersive visualization: LMU
Simulation Web Portal
  iCOMCOT web portal Services: http://icomcot.twgrid.org
Milestone

## Slide 5: 1. Earthquake & Tsunami (II)
Excellence
  Towards Real and Complex Disaster Scenario simulation
    Earthquake tsunami
  Spotting potential tsunami sources for better preparedness
    Correlation analysis between initial surface and the earthquake rupture characteristics from historical tsunamis
Milestone
  M4:
    Collect historical tsunami records: PH, VN, ID, TW
    Find local earthquake/tsunami scientists to design the disaster scenario and try the iCOMCOT system: PH, VN, ID, TW
  M10:
    Finish at least one forward simulation by the designed scenario.
    Finish at least one inversion simulation by the collected historical tsunami event.
    Result evaluation: functionality, workflow, performance, accessibility, etc.
  M12: iCOMCOT system revision based on the evaluation
  M18: finish two high risk tsunami subduction zones scenario analysis

## Slide 6: 2. Extreme Weather (I)
Background
  Understanding and simulating mesoscale weather processes such as typhoon, dynamic interactions between typhoon circulation and monsoonal flow at different scales
  Enhance the forecasting capability in precipitation events brought by similar events
Tasks
  Investigate historical extreme weather event: KR, PH, VN, TH, MY, ID, TW
  WRF (Weather Research and Forecast) simulation web portal: TW
  Immersive Visualization: LMU

## Slide 7: 2. Extreme Weather (II)
Excellence
  Improve the understanding of multi-scale nature of tropical cyclones for generating local heavy rainfall events
  Fast and accurate simulation could enhance the early warning
Milestone
  M3: Collect data of at least one target extreme weather event by engaging local user communities
  M6: Investigate the first simulations of the mesoscale processes: e.g., water vapor, moisture flux, etc.
  M9: Result evaluation
  M12: Refine the WRF web portal

## Slide 8: 3. UHI and Asian Dust Transportation (I)
Background
  Understanding the impacts of long-range dust transportation in Asia Pacific region
  Understanding the impacts of urbanization to the local weather
Tasks
  Finish at least one case study of long-range dust transportation in Asia (either volcanic ashes dispersion or biomass burning): PH, MY, TH, ID, TW
  Finish at least one case study of urban heat island among partners: KR, PH, MY, TH, ID, TW
  Buildup the modeling and simulation capability of UHI and dust transportation
  Immersive Visualization: LMU

## Slide 9: 3. UHI and Asian Dust Transportation (II)
Excellence
  Provide seasonal variations analysis of CO, O3 and PM10, including the concentration, transportation path and climate impacts, etc.
  Buildup impact analysis capability of the Urban Heat Island effect on precipitation over a complex geographic environment
Milestone
  M13: confirm the target case and review the data collected (at least one event for ADT and UHI respectively)
  M16: first simulation investigation
  M20: case analysis and refined simulation
  M24: finish the workflow, data analysis, simulation and the web portal

## Slide 10: Next Meeting & Future Events
April 14: Progress Checking
April 28: Progress Checking
May 12: Progress Checking
May 18-22, EGI Conference, Lisbon, PT
Aug. ?, APAN ?, Kuala Lumpur, MY
Environmental Computing Workshop, ISGC 2016