## Slide 1: Disaster Mitigation Competence Centre Project Meeting Coordinator: Simon Lin
April 14, 2015

## Slide 2: Agenda
From Previous Meeting
Progress Report
  Data set and Format Requirements for historical tsunami and WRF
  Partner Contributions and local user community engagement (All Partners)
Proposal Update
  Milestones Update
  Open DMCC to non-members, such as VN, IN, AU, NZ, SG, JP, and European partners, etc.
Future Meetings
AOB

## Slide 3: From Previous Meeting (March 31, 2015)
Participants: John (ASTI, PH), Rafael (AMU, PH), Sornthep (NECTEC, TH), Rahim (MY), Simon, Eric, Stella, Angelina (ASGC, TW),
  Apology: Soonwook (KISTI, KR), Basuki (ITB, ID)
Briefing of DMCC Tasks with Milestones (Eric)
  Partners will confirm their contributions according to the design
Data set and Format Requirements for simulations of tsunami and extreme weather should be provided
Environmental Computing Workshop is planned to be collocated with ISGC2016
  Workshop is proposed by LMU
Schedule of Future Meetings is arranged

## Slide 4: Excellence Strategy: Capacity Building and Shaping the Sustainable Society
 | Earthquake & Tsunami | Extreme Weather | Asia Dust Transportation | UHI & Urbanization
What Happened | Rebuild the event processes together with observation data |  |  | 
Why did it happen | Explained by refined models and verified by observation data thru simulations |  |  | 
What will happen | Buildup predictive analysis capability or estimate the impact of potential hazard sources |  |  | 
How can we reduce the impact | Moving towards early warning based on fast re-modeling, simulation and feedback cycle. Domain knowledge from |  |  | 

## Slide 5: Deliverables
D-Day = March 1st, 2015 | PM3 | PM6 | PM9 | PM12 | PM15 | PM18 | PM21 | PM24 | PM27 | PM30
Earthquake & Tsunami | PM12: Provide tsunami wave propagation simulation web portal to the public |  |  |  |  |  |  |  |  | 
 | PM19: Finish two high risk tsunami subduction zones scenario analysis in Asia Pacific region |  |  |  |  |  |  |  |  | 
Extreme Weather | PM12: Release gWRF weather simulation web portal |  |  |  |  |  |  |  |  | 
Asia Dust Transportation | PM24: Apply WRF/chem tracer modelling study to demonstrate the biomass-burning transport mechanism and its impact on air quality. |  |  |  |  |  |  |  |  | 
UHI & Urbanization | PM24: Release the prototype of WRF-Noah-UCM on UHI simulation of a city in a partner country |  |  |  |  |  |  |  |  | 
 | PM29: Finish the design larger scale multi-hazards simulation attempting to reduce the uncertainty of climate change assessment |  |  |  |  |  |  |  |  | 

## Slide 6: Milestones for Deliverables
D-Day = March 1st, 2015 | PM3 | PM6 | PM9 | PM12 | PM15 | PM18 | PM21 | PM24 | PM27 | PM30
Earthquake & Tsunami | M4, M10, M12, M18 |  |  |  |  |  |  |  |  | 
Extreme Weather | M3, M6, M9, M12 |  |  |  |  |  |  |  |  | 
Asia Dust Transportation | M13, M16, M20, M24 |  |  |  |  |  |  |  |  | 
UHI & Urbanization |  |  |  |  |  |  |  |  |  | 
 | PM29: Finish the design larger scale multi-hazards simulation attempting to reduce the uncertainty of climate change assessment |  |  |  |  |  |  |  |  | 

## Slide 7: Milestones for Earthquake & Tsunami
Tasks
  Potential tsunami scenarios identification: Manila Trench, Sunda Trench: PH, ID, VN, TW
  Tsunami Wave Propagation Simulation Web Portal: ASGC
  Historical Tsunami Records Collection and Inversion Simulation to identify potential tsunami sources: PH, ID, VN, TW
  Immersive visualization: LMU
Milestone
  M4:
    Collect historical tsunami records: PH, VN, ID, TW
    Find local earthquake/tsunami scientists to design the disaster scenario and try the iCOMCOT system: PH, VN, ID, TW
  M10:
    Finish at least one forward simulation by the designed scenario.
    Finish at least one inversion simulation by the collected historical tsunami event.
    Result evaluation: functionality, workflow, performance, accessibility, etc.
  M12: iCOMCOT system revision based on the evaluation
  M18: finish two high risk tsunami subduction zones scenario analysis

## Slide 8: Milestones for Extreme Weather
Tasks
  Investigate historical extreme weather event: KR, PH, VN, TH, MY, ID, TW
  WRF (Weather Research and Forecast) simulation web portal: TW
  Immersive Visualization: LMU
Milestone
  M3: Collect data of at least one target extreme weather event by engaging local user communities
  M6: Investigate the first simulations of the mesoscale processes: e.g., water vapor, moisture flux, etc.
  M9: Result evaluation
  M12: Refine the WRF web portal

## Slide 9: Milestones for UHI and Asian Dust Transportation
Tasks
  Finish at least one case study of long-range dust transportation in Asia (either volcanic ashes dispersion or biomass burning): PH, MY, TH, ID, TW
  Finish at least one case study of urban heat island among partners: KR, PH, MY, TH, ID, TW
  Buildup the modeling and simulation capability of UHI and dust transportation
  Immersive Visualization: LMU
Milestone
  M13: confirm the target case and review the data collected (at least one event for ADT and UHI respectively)
  M16: first simulation investigation
  M20: case analysis and refined simulation
  M24: finish the workflow, data analysis, simulation and the web portal

## Slide 10: Presentation at EGI Conference
Title: e-Science for the Masses: Asia Pacific Regional Collaboration on Disaster Mitigation
Eric Yen and Simon Lin, on behalf of DMCC
Abstract
  By means of e-Science resources and collaboration framework, the Disaster Mitigation Competence Centre (DMCC) is aiming to improve strategy of prevention and reduction of disasters. Three categories of regional focused hazards are targeted, which include the earthquake and tsunami, extreme weather and environmental changes. DMCC will create virtual research environments with embedded services and simulations that enable the sharing of disaster-related data, tools, applications and knowledge among field-workers, scientists, and e-infrastructure experts, shortening the time to respond to natural disasters. Through the DMCC, for example, potential tsunami sources would be spotted for better preparedness. Understanding of multi-scale nature of tropical cyclones for generating local heavy rainfall events is improved. Impact analysis capability of urban heat island effect on precipitation will be built up. In the end, the regional e-Infrastructure offerings to data and knowledge services and simulation services for disaster mitigation are much enhanced.

## Slide 11: Next Meeting & Future Events
April 28: Progress Checking
May 12: Progress Checking
May 18-22, EGI Conference, Lisbon, PT
May 26, Progress Checking
Aug. 10-14, APAN40, Kuala Lumpur, MY
  DMCC face-to-face meeting ?
Environmental Computing Workshop, ISGC 2016