## Slide 1
EGI DARIAH Competence Centre
Project logistics and activity plan
Karolj Skala, Davor Davidović
skala@irb.hr, ddavid@irb.hr
Ruđer Bošković Institute, Croatia
Notes: 1

## Slide 2
Partners

## Slide 3
Partner contacts
Ruđer Bošković Institute (RBI):
Karolj Skala (skala@irb.hr), Davor Davidović (ddavid@irb.hr)
MTA SZTAKI:
Zoltan Farkás (zoltan.farkas@sztaki.mta.hu)
Instituto Nazionale di Fisica Nucleare (INFN):
Roberto Barbera (roberto.barbera@ct.infn.it),
Giuseppe La Roca (giuseppe.larocca@ct.infn.it)
Data Archiving and Networked Services (DANS):
Maarten Hoogerwerf (maarten.hoogerwerf@dans.knaw.nl)
Gesellschaft für wisseenschaftliche Datenverarbeitung Göttinger (QWDG):
Tibor Kalman (tibor.kalman@gwdg.de)
Austria Academy of Science:
Eveline Wandl-Vogl (Eveline.Wandl-Vogt@oeaw.ac.at)
European Grid Infrastructure (EGI):
Gergely Sipos (gergely.sipos@egi.eu)

## Slide 4
CC coordinator: Karolj Skala (skala@irb.hr)
Activity coordinator: Davor Davidović (ddavid@irb.hr)
Technical coordinator: Zoltan Farkás
(zoltan.farkas@sztaki.mta.hu)
Dissemination coordinator: Eveline Wandl-Vogl
(Eveline.Wandl-Vogt@oeaw.ac.at)
EGI contact point: Gergely Sipos (gergely.sipos@egi.eu)
Project coordination

## Slide 5
Tasks
T1: User Support and Training (RBI)
T2: DARIAH eScience Gateway on EGI (SZTAKI)
T3: Storing and Accessing DARIAH contents on EGI (SADE) (INFN)
T4: Multi-source distributed real-time search and information retrieval (SIR) (GDWG)
T5: Exploitation (DANS)
Notes: Exploitation – transfer of the CC results (applications, repositories) to its targeted user communities and reasearchers
Increase applicability and impact of the mini-projectss – increase awareness of EGI infra in A&H, define usage policy, dissaminate mini-projects
5

## Slide 6
Task interaction

## Slide 7
Deliverables
Upcoming deliverables(M2): D2.1, D3.1, D4.1
Requirements collection and analysis

## Slide 8
F2F meetings
  Every 6 months in the first year
  1 per/year in the following years
  In conjunction with EGI meetings (User forums, EGI conference, NGI events)
  At least one meeting in conjunction with DARIAH-EU
Online meetings (skype, indico,…)
  1 every month
    Coordination actions, follow-up
    Report on mini-project status
Meetings

## Slide 9
Starting date: M6
Develop training plan (A1.1, D1.1 – M9)
Training plan (to be defined by M9)
Tentative plan:
  Each partner organize at least one training event (specially those involved in mini-projects)
  At least one training event / workshop organized in conjunction with DARIAH-EU
Dissemination activities

## Slide 10
Starting date: M7
Define per mini-project exploitation actions
  SADE, SIR, eScience Gateway
Activities (to be redefined):
User involvement per mini-project (D5.1)
  Sustainability plan (D5.2)
  Mini-project dissemination activities (D5.3)
  Roadmap to user community enlargement in EGI (D5.4)
Exploitation activities

## Slide 11
Consulting (starting M6)
Technical support (starting M13)
Decide on how to provide support
  Will resulted with deliverable: D1.1 (M9)
Support staff (ticketing – maybe through existing EGI ticketing?)
Populate DARIAH CC wiki pages: (wiki.egi.eu/wiki/Competence_centre_DARIAH)
Support activities

## Slide 12
Start building wiki pages:
https://wiki.egi.eu/wiki/Competence_centre_DARIAH
Questionnaire
  survey about DARIAH users e-Infrastructural requirements (e.g. storage capacities, computational power, authN, etc...)
  Define the target group
  To be discussed via teleconferencing (end of April)
Establish EGI Virtual Organization for A&H (DARIAH community)?
Start-up activities

## Slide 13
Useful information
Mailing list: cc-dariah@mailman.egi.eu
Meetings, webinars, agendas:
http://indico.egi.eu/indico/categoryDisplay.py?categId=141
Wiki pages:
https://wiki.egi.eu/wiki/Competence_centre_DARIAH