## Slide 1: Disaster Mitigation Competence Centre Project Meeting Coordinator: Simon Lin
April 28, 2015

## Slide 2: Agenda
Introduction (Simon Lin)
From Previous Meeting on April 14, 2015 (Eric Yen)
Progress Report (Eric Yen)
Partner Report, especially on confirmation of role and contribution
Discussion
Future Events
AOB

## Slide 3: From Previous Meeting (April 14, 2015)
Participants: Gergely (EGI-Engage), Peter and Jane (ASTI, PH), Rafael (AMU, PH), Rahim (MY), Basuki (ITB, ID), Simon, Stella, Vicky, Angelina, Eric (ASGC), Alex (UStA)
Partners have to confirm their contributions and roles to which task, deliverable and milestone by next meeting (April 28, 2015).
  Local data, local user community, local scenario/requirements are the focus. And then achieve knowledge commons through regional collaborations.
  Trainings for simulation tools should be arranged
Collaborations with EGI and EGI-Engage WPs
  Such as WRF  model of collaboration has to be identified
EGI Conference in May
  Invitation letter requirements please send to Vicky.
  Should have the DMCC meeting (during 1700-1800 everyday) together with EGI-Engage headquarter
Survey will be conducted to understand the current status of partner countries related to disaster mitigation
  Partners are welcomed to provide questions to be included
Publicity: Wiki page will be established first and then the DMCC webpage
Broadening the participations of more Asia Pacific countries (e.g., VN, AU, NZ, IN, JP, etc.) and European partners were suggested.
Next Meeting: 1600-1730 (Taiwan Time), April 28, 2015

## Slide 4: Progress Report

## Slide 5: Accelerating the implementation of the OSC vision
Researchers from all disciplines have easy, integrated and open access to the advanced digital services, scientific instruments, data, knowledge and expertise they need to collaborate to achieve excellence in science, research and innovation.
EGI-Engage
30 months, Start: 1/March/2015
43 partners
8 m Euro EC contribution
www.opensciencecommons.org
E-infrastr. Commons
Data Commons
Knowledge Commons
WP6-SA2:
Competence Centres
Training on generic topics
Support for new communities
Scientific Instruments
Notes: Relationship of the Three COMMONS and collaborations within EGI-Engage

## Slide 6: Competence Centres in EGI-Engage
Technical support for 8 Competence Centres
  7 RIs from the ESFRI roadmap: BBMRI, DARIAH, EISCAT_3D, ELIXIR, EPOS, INSTRUCT, LifeWatch
  1 Competence Centre from Asia-Pacific for Disaster mitigation
Goals
  Foster the establishment of sustainable Knowledge Commons
  Foster the adoption and harmonisation of e-infrastructure services
  Evolve infrastructure and data services through co-development
  Dissemination, training, exploitation of the Commons within the RIs
Implementation
  Building on EGI solutions and on other WPs
    Cloud, Data federation, Operations, Business models, etc.
  Groups of scientific institutes, technology providers, EGI members
  Few core partners + Open membership

## Slide 7: Collaborations
EUDAT2020  4 pilot activities for the interoperability of technical services
  BBMRI
  EISCAT-3D
  ELIXIR
  ICOS
Indigo Datacloud  technology provisioning, user and service provider requirements gathering
AARC  federated IdM adoption (policies, services, requirements)

## Slide 8: To Do List
Partners
  Confirm role and contributions to the CC
  Work with your local user community and identify the application scenarios or target questions
  Support your user community to make use of the iCOMCOT and WRF
    Feedback is essential to refine the web portal, system design, resource arrangement, and workflow
Collaborations: regional, infrastructure+service+User, EGI-Engage WPs, other EU projects, etc.
Infrastructure Enabling
  HW, Web Portal and User Interface, Workflow, AAI, etc.
Survey will be conducted

## Slide 9: DMCC Wiki Is Online
https://wiki.egi.eu/wiki/EGI-Engage:Competence_centre_Disaster_Mitigation
Please provide your comment to Eric Yen and Vicky Huang

## Slide 10: The Survey
If no time to update the questions, put them on the wiki for comment first

## Slide 11: Partners Report

## Slide 12: Next Meeting & Future Events
April 28: Progress Checking
May 12: Progress Checking
May 18-22, EGI Conference, Lisbon, PT
May 26, Progress Checking
June 9, Progress Checking
June 23, Progress Checking
Aug. 10-14, APAN40, Kuala Lumpur, MY
  DMCC face-to-face meeting ?
Environmental Computing Workshop, ISGC 2016