## Slide 1: Disaster Mitigation Competence Centre Project Meeting Coordinator: Simon Lin
May 12, 2015

## Slide 2: Agenda
Introduction (Simon Lin)
From Previous Meeting on April 28, 2015 (Eric Yen)
Progress Report (Eric Yen)
Partner Status Report
Discussion
Future Events
AOB

## Slide 3: From Previous Meeting (April 28, 2015) Agenda & Meeting Materials: https://indico.egi.eu/indico/conferenceDisplay.py?confId=2522
Participants: Rafael (AMU, PH), Rahim (MY), Basuki (ITB, ID), Simon, Stella, Vicky, Angelina, Eric (ASGC)
  Apology: TH, PH, UK and DE
Progress Report (Eric)
  Introduction to the role of competence centers, implementation of open science commons, and collaborations under the umbrella of EGI-Engage
  Reminder of partners contributions confirmation
  Survey will be conducted:
    To further understand the requirements and status of user communities in partner country
    Please contribute your questions to be included
  DMCC wiki has been online
Partner Status Report:
  ID: targeting on earthquake & tsunami, dusk transportation and is engaging local scientists
  TH: case study -- The severe flooding event in 2011 caused by tropical storm
Future Events
  DMCC meeting at 1700 (CEST) of May 17 at EGI Conference in Lisbon
  DMCC face-to-face meeting at APAN40 (10-14 Aug. 2015) in Kuala Lumpur, Malaysia
Next Meeting: 1600-1730 (Taiwan Time), May 12, 2015

## Slide 4: Partner Contributions
 | Earthquake & Tsunami | Extreme Weather | Long Distance Dust Transportation | Urban Heat Island Impact
Web Portal | TW | TW | TW | TW
Case Study | ID, TW | MY, TH, TW | ID, TW | TW
Resource Center | TW |  |  | 
Visualization | DE |  |  | 
Service & Support | TW | TW | TW | TW
Other Collaborations |  |  |  | 

## Slide 5: Proposed Targets
Earthquake and Tsunami
  Tsunami Source Characterization for Western Pacific Subduction Zones
Extreme Weather
  Typhoons in PH, VN and TW area
  Storm Surge
  Tropical Storms: Thailand Flooding
Long Distance Dust Transportation
  Volcano ashes, Biomass burning
Urban Heat Island Imact
  Urbanization effects on Sea-Land Circulation in Taiwan

## Slide 6: Requirements Analysis and Scenario Design
Identify and Work with User Communities
Scenario-based Requirement Analysis
  Objectives
  Workflow, data source, result analysis, information integration and sharing, etc.
  Simulation portal customization to meet user needs and take advantage of e-infrastructure
  Case study
Demands for the e-Infrastructure
  AAI, data management, toolkits, computing resource, visualization, application integration, etc.

## Slide 7: Simulation Portal Status
Tsunami Wave Propagation
  http://icomcot.twgrid.org
  Need to apply user account first by click “Login” and choose “New User Registration”
gWRF Weather Simulation
  http://gwrf.twgrid.org
Dust Transportation and Urban Heat Island Effect simulation are under development

## Slide 8: To Do List
Open and Widening Collaboration
  Invite APGI and any Asia partners to join the DMCC and bring their projects
  Partner with EGI-Engage and EGI and EU related projects and leverage existing technology and expertise
  Other related efforts
Survey: will rely on Alex
Soundscape: understand characteristics of soundscape across spatial-temporal scale by studying impact of soundscape on human and organism and vice versa
  PH, VN, MY, TH and TW had been collecting data
  Partnership is opening

## Slide 9: Next Meeting & Future Events
May 12: Progress Checking
May 18-22, EGI Conference, Lisbon, PT
  DMCC Meeting at 1700 (CEST), May 18
May 26, Progress Checking
June 9, Progress Checking
June 23, Progress Checking
Aug. 10-14, APAN40, Kuala Lumpur, MY
  DMCC face-to-face meeting
Environmental Computing Workshop, ISGC 2016