## Slide 1: Disaster Mitigation Competence Centre Project Meeting Coordinator: Simon Lin
May 18, 2015

## Slide 2: Agenda
Introduction (Simon Lin)
From Previous Meeting on April 28, 2015 (Eric Yen)
Progress Report (Eric Yen)
Partner Status Report
Discussion
Future Events
AOB

## Slide 3: From Previous Meeting (May 12, 2015) Agenda & Meeting Materials: https://indico.egi.eu/indico/conferenceDisplay.py?confId=2533
Participants: Rafael (AMU, PH), John (ASTI, PH), Rahim (MY), Sornthep (NECTEC, TH), Cerlane (LRZ, DE), Simon, Stella, Vicky, Angelina, Eric (ASGC)
  Apology: ID
Progress Report (Eric)
  Summary of partner contributions plan
  Designed target and scenario-oriented case studies
  Simulation portal status
  Open collaboration approaches
  Soundscape welcomes regional participations
Partner Status Report:
  MY: started from the flooding cases happened in 15 Dec ‘14 – 3 Jan ‘15.
  PH: tsunami (AMU), earthquake and tsunami (ASTI)
  TH: case study -- The severe flooding event in 2011 caused by tropical storm
Future Events
  DMCC meeting at 1700 (CEST) of May 18 at EGI Conference in Lisbon
  DMCC face-to-face meeting at APAN40 (10-14 Aug. 2015) in Kuala Lumpur, Malaysia
Next Meeting: 1600-1730 (Taiwan Time), May 18, 2015

## Slide 4: Partner Contributions
 | Earthquake & Tsunami | Extreme Weather | Long Distance Dust Transportation | Urban Heat Island Impact
Web Portal | TW | TW | TW | TW
Case Study | ID, PH, TW | MY, PH, TH, TW | ID, TW | TW
Resource Center | TW |  |  | 
Visualization | DE |  |  | 
Service & Support | TW | TW | TW | TW
Other Collaborations | EGI: infrastructure, AAI, etc. |  |  | 

## Slide 5: To Do List
Open and Widening Collaboration
  Invite APGI and any Asia partners to join the DMCC and bring their projects
  Partner with EGI-Engage and EGI and EU related projects and leverage existing technology and expertise
  Other related efforts
Survey: will rely on Alex
Soundscape: understand characteristics of soundscape across spatial-temporal scale by studying impact of soundscape on human and organism and vice versa
  PH, VN, MY, TH and TW had been collecting data
  Partnership is opening

## Slide 6: Next Meeting & Future Events
May 18-22, EGI Conference, Lisbon, PT
  DMCC Meeting at 1700 (CEST), May 18
May 26, Progress Checking
June 9, Progress Checking
June 23, Progress Checking
Aug. 10-14, APAN40, Kuala Lumpur, MY
  DMCC face-to-face meeting
Environmental Computing Workshop, ISGC 2016