## Slide 1: Disaster Mitigation Competence Centre Project Meeting Coordinator: Simon Lin
September 22, 2015

## Slide 2: Agenda
Introduction
From Previous Meeting on Aug. 25, 2015 (Eric Yen)
Progress Report (Eric Yen)
Partner Status Report
Discussion
Future Events
AOB

## Slide 3: Minute of Routine Meeting on Aug. 25
Date & Time: 1700-1730, Aug. 25, 2015
Participants: Peter (PH) Cerlane (DE), Simon, Stella, Vicky, Eric (TW)
Agenda and Materials:
  https://indico.egi.eu/indico/conferenceDisplay.py?confId=2632
Action Item
  As concluded from the F2F meeting in Kuala Lumpur, the identified case studies will be conducted by the DMCC coordinator and the partners in separate meetings. Progress will be reported at the routine DMCC meeting.
  Simon and Prof. TR Wu will visit the V2C Centre of LRZ during the week of e-Science Conference in Much, and discuss about the integration with advanced visualization facility.
  DMCC routine work meeting will be scheduled once every month from September 2015.

## Slide 4: DMCC Strategy
Deeper understanding of Natural Disasters rather than just hazard map. This is an opportunity that atmospheric and oceanic scientists can work together, taking advantage of the state of art of computer simulations, supplemented the local data such that the most accurate simulation such as Haiyan inundation.
Theory, Methodology, Examples of the simulation on Tsunami, Storm Surge, Local Scouring, Weather, Flooding and Environmental Changes could be found at the F2F meeting materials.
  https://indico.egi.eu/indico/conferenceDisplay.py?confId=2625

## Slide 5: Progress Summary of Case Studies
Reconstruct the whole process of target event
Mechanism review
Integration with Advanced Visualization (LRZ)
Towards early warning for future hazardous events
Partners | Topics | Required Data Sets | Status | Check Point | Simulation Framework
PH, TW | Typhoon Haiyan | Doppler Radar, Tidal gauge, air pressure, wind speed, typhoon path; hourly resolution | Sep. 9; Aug. 25 | Demo @ APAN41 | gWRF, COMCOT
ID, TW | tsunami cave in Lhong-Aceh Besar |  |  |  | COMCOT
MY, TW | Flooding 2014-15 |  | Sep. 14 |  | gWRF, Scouring
TH | Flooding 2011 |  |  |  | 
Nepal | Flooding 2008 | High altitude and geographical features need to consider | Sep. 11 |  | 
TW | Tsunami Impact Analysis in South China Sea |  |  | Demo @ ISGC2016 | iCOMCOT

## Slide 6: DMCC Future Plan
In original plan, we will focus on impacts of Urban Heat Island, dust transportation in the 2nd year of DMCC.
Any new topics are welcomed if required data sets are available.
Advanced visualization for disaster mitigation would be distinguishing features of DMCC
A separate project on integration of WRF and GIS is undergoing at ASGC which would be available for DMCC after Summer 2016.

## Slide 7: Future Meetings and Events
Future Routine Project Meeting (last Tuesday of each month)
  16:30-17:30, 27 October, 2015
  16:30-17:30, 1 December, 2015
  16:30-17:30, 29 December, 2015
DMCC face-to-face Meeting at EGI Community Forum, Nov. 10-13, Bari, Italy
DMCC face-to-face Meeting at APAN41, Jan. 25-29, 2016, Manila, Philippine
DMCC Face-to-Face Meeting and the Environmental Computing Workshop, March 13-18, ISGC 2016, Taipei, Taiwan