## Slide 1: Disaster Mitigation Competence Centre Project Meeting Coordinator: Simon Lin
October 27, 2015

## Slide 2: Agenda
Introduction
From Previous Meeting on Sep. 22, 2015 (Eric Yen)
Progress Report (Eric Yen)
Partner Status Report
Discussion
Future Events
AOB

## Slide 3: Minute of Routine Meeting on Sep. 22
Date & Time: 1630-1700, Sep. 22, 2015
Participants: Peter (PH), Cerlane (DE), Vicky, Eric (TW) and Gergely (EGI-Engage)
Agenda and Materials:
  https://indico.egi.eu/indico/conferenceDisplay.py?confId=2663
Action Item
  Update progress and case studies status on the project wiki (Eric)
  Partners please provide observation data (from rain gauge, radar, weather station, etc., as well as the bathymetry data) according to the requirements of case studies
  Comment and requirement on simulation portal please send to Eric

## Slide 4: Progress Summary of Case Studies I
Reconstruct the whole process of target events
Mechanism review
Integration with Advanced Visualization (LRZ)
Towards early warning for future hazardous events

## Slide 5
Partner | Selected Case | Required Data Sets | Status | Check Point | Simulation Framework
PH, TW | Typhoon Haiyan | Doppler Radar, Tidal gauge, air pressure, wind speed, typhoon path; hourly resolution | Having bilateral discussion on : Oct. 16, Sep. 9, Aug. 25 | Demo @ APAN41 | gWRF, COMCOT
ID, TW | Tsunami cave in Lhong-Aceh Besar |  |  | Demo @ ISGC2016 ? | COMCOT
MY, TW | Flooding 2014-15 |  | Simulation by AS (global data) was done. Bilateral Meeting: Sep. 14 | Demo @ ISGC2016 ? | gWRF, Scouring
TH, TW | Flooding 2011 |  | Simulation by NECTEC and AS (global data) were done. Aim to improve the accuracy and EWS. | Demo @ ISGC2016 ? | gWRF, Scouring
Nepal, TW | Flooding 2008 | High altitude and geographical features need to consider | Oct. 12 Sep. 11 |  | 
TW, PH | Tsunami Impact Analysis in South China Sea |  | In progress | Demo @ ISGC2016 | iCOMCOT

## Slide 6: Progress Summary of Case Studies II
Advanced Visualization on Scouring Case of Taiwan by NCU and LRZ
  Kick-off at the visit to V-Lab at LRZ in early Sep.
  Follow-up phone meeting was held on Oct. 6
  Simulation data had been delivered to LRZ for verification and further processing
  …
Typhoon Haiyen visualization is also one of the priority case

## Slide 7: Discussion
DMCC Session at EGI Community Forum on Nov. 9-13
  Agenda
    DMCC Collaboration and Status (Eric Yen, ASGC)
    e-Science for the Masses (Simon Lin, ASGC)
    Advanced Visualization Case Study (Cerlane, LRZ)
    Discussion
  Participation is encouraged
  Any remote participant ?
Case Studies

## Slide 8: Future Meetings and Events
Future Routine Project Meeting (last Tuesday of each month)
  16:30-17:30, 1 December, 2015
  16:30-17:30, 29 December, 2015
DMCC face-to-face Meeting at EGI Community Forum, Nov. 10-13, Bari, Italy
DMCC face-to-face Meeting at APAN41, Jan. 25-29, 2016, Manila, Philippine
DMCC Face-to-Face Meeting and the Environmental Computing Workshop, March 13-18, ISGC 2016, Taipei, Taiwan