## Slide 1: EGI Engagement Report to OMB 2016. May Engagement cases https://go.egi.eu/technicalsupportcases
Customer and Technical Outreach Manager
EGI-Engage SA2 coordinator
Gergely Sipos

## Slide 2: Outline
CCs, RIs & projects
Long-tail users
Infrastructure improvements
SLAs-OLAs
Events, training
RED TEXT ON THESE SLIDES MEANS:
CALL FOR EGI SITES TO GET INVOLVED

## Slide 3: Competence Centres: Diverse interests, different timelines
Pilot exploration of e-infra services
Production e-infra services
Number of relevant EGI service areas
One/two areas
Several, interlinked areas
Few, independent areas
EISCAT_3D
BBMRI
DARIAH
LifeWatch
Disaster Mitigation
EPOS
ELIXIR
MoBrain
Data catalogue
HTC
Private clouds
Controlled data sharing
DataHub
Real-time search application
Compute apps
Data-intensive computing
Federated cloud
Community portals
R and citizen tools
Federated cloud
Community VREs
AAI
Federated cloud
Federated Open Data
Application porting
Core platform (AAI, Service registry)
Federated Cloud
VM Marketplace
Application/tool porting
GPGPUs
Federated cloud
Community platform
Application porting
Service maturity target (by end of EGI-Engage)
Notes: RIs on the right are more strongly connected to NGIs, RIs in the left are much less

## Slide 4: Competence Centres: Current status
ELIXIR | Compute Platform with AAI 5 use cases (M6.3) | ECP: D6.10 nearly complete: DocDB/2802  ELIXIR VO |  |  | 
BBMRI | Private clouds (M6.2) | BioBankCloud-Karamel integration nearly done |  |  | 
 | Data workflows |  |  |  | 
MoBrain | Community portal | Done | Done (D6.4) | Started (ISGC, Utrecht, etc.) | SLA-OLA signed in Q1 2016
 | Cryo-EM in the cloud (SCIPION) | Done | Ongoing |  | 
 | GPGPU application gateways | Ongoing |  |  | 
DARIAH | Data repository | Done (D6.2) | User exploitation plan ongoing |  | 
 | Real-time search | Done/Ongoing (D6.5) |  |  | 
 | Application gateway | WS-PGRADE + DH VO + IdP |  |  | 
LifeWatch | GPGPU, Cloud infra. Services | Ongoing within Task Forces |  |  | 
 | Apps. for citizen science | Done | Done (D6.1) | Ongoing | 
EISCAT_3D | Data Portal | Done–Proof-of-concept (D6.3) | UserMeetingDemo |  | 
 | Data & Compute Portal | COMPUTE VO |  |  | 
EPOS | 3 use cases (M6.4) | Ongoing (WSPGRADE & cloud) |  |  | 
Disaster Mitigat. ELIXIR | 2 simulation gateways | gWRF and iCOMCOT gateways | Ongoing |  | 
 | 3 core use cases | Typhoons (Haiyan, Morakot) | Ongoing | Ongoing | 
 |  | 2014 rainfall in Malaysia |  |  | 
 |  | Thailand flood in 2011 |  |  | 
 | 2 external use cases (NE, VT) |  |  |  | 
Requirement collection & system design
Co-development
Tests, evaluation
Dissemin./
Exploitation
SLAs, operation

## Slide 5: PY2 plans – Competence Centres
ELIXIR | Compute Platform with AAI 5 use cases (M6.3) | Operates in 5 ELIXIR nodes | Completed (D6.10, D6.15) | EXCELERATE | Jointly by ELIXIR and EGI
BBMRI | Private clouds (M6.2) | Operated in 3 biobanks | Completed (D6.11) | Common IT serv. | 
 | Data workflows (D6.8) | Ongoing |  |  | 
MoBrain | Community portal | Done | Done (D6.4) | Ongoing | SLA-OLA signed in Q1 2016
 | Cryo-EM in the cloud (SCIPION) | Done | Done (D6.14) | Ongoing | 
 | GPGPU application gateways | Completed (D6.7, D6.12) | Completed | Ongoing | 
DARIAH | Data repository | Done (D6.2) | Completed | Ongoing | 
 | Real-time search | Done/Ongoing (D6.5) |  |  | 
 | Application gateway | Completed (D6.17 |  |  | 
LifeWatch | GPGPU, Cloud infra. Services | GPGPU apps in production | Completed | Ongoing | 
 | Apps. for citizen science | Done | Done (D6.1, D6.18) | Ongoing | Ongoing
EISCAT_3D | Data Portal | Done–Proof-of-concept (D6.3) | Completed |  | 
 | Data & Compute Portal | Ongoing |  |  | 
EPOS | 3 use cases (M6.4) | Completed (D6.13, D6.19) | Ongoing(Compute) | Ongoing (Data) | 
Disaster Mitigat. ELIXIR | 2 simulation gateways | gWRF and iCOMCOT gateways | Completed (D6.9) | Ongoing | Ongoing
 | 3 core use cases | Typhoons (Haiyan, Morakot) | Completed (D6.20) | Ongoing | 
 |  | 2014 rainfall in Malaysia |  |  | 
 |  | Thailand flood in 2011 |  |  | 
 | 2 external use cases (NE, VT) | Completed (Nepal, Vietnam) | Completed | Ongoing | 
Requirement collection & system design
Co-development
Tests, evaluation
Dissemin./
Exploitation
SLAs, operation
Notes: SA2.3-10: 13 deliverables in next 12 months

## Slide 6: Other RI activities
Euro-Argo (follow-up from Design workshop)
  1st phase: complete (Cataloguing in EUDAT B2Find instance in Germany)
  2nd phase: investigation ongoing (Replicate 500GB set to a cloud site, enable filtering for users into personal cloud account)
ICOS (follow-up from Design workshop)
  Data sharing by multiple VMs and Docker containers  EGI ODP?
  Access EUDAT storage from EGI VM  B2Stage API?
  High level app frameworks to simplify development  DIRAC or WS-PGRADE?  Webinars

## Slide 7: Other RI activities 2
LOFAR and SKA (Spain):
  Ongoing infra performance tests (CPU and memory use; Time of completion)
  Supported by BSC (Daniele Lezzi, COMPs)
EMSO (EMSO-Dev project)
  Setting up MoU with EGI immediately after ERIC is established (expected in June with IT, FR, UK, GR, PT, IE. Observers: DE, NL)
  Focus on enabling and sustaining the EMSO data management platform on EGI resources

## Slide 8: Ris, projects – other discussions
Big Data Europe
  Platform based on Docker and Docker Swarm
  Setup a proof-of-concept instance on fedcloud VO  Start around summer, finish by end of 2016
ELI (ELI-Trans)
  Supporting and monitoring their data architecture requirement document (D10.1 of ELI-Trans)
X-FEL, Parthenos, Ariadne, CORBEL, NOMAD, Agriculture, ESS, Ibercivis,
  Joint pilots in EOSC project?

## Slide 9: Recent long tail users (reaching EGI)
BIOISI – Bioinformatics institute in Lisbon
  Compute apps, 100s cores, big RAM, 50 TB storage
  Followed-up by LIP
Molecular modelling group of Uni of Catania
  Need for large compute for job expected to run for 4 months. Yet to fully understand the app. (Better fit to a PRACE site?)
NeuroImage Research group in Erasmus
  Instructions were sent on how to engage with SURFsara HPC cloud, or to start on EGI FedCloud

## Slide 10: Infrastructure improvements
fedcloud.egi.eu VO:
  3 sites with faulty image replication left  Quality improvement!
  Site suspensions to start in June
  Soon to establish OLAs. Sites can choose level of support:
    Support only EGI VMs (created by EGI)
    Manual support for user VMs (user needs to ask deployment directly)
    Automated support for user VMs (VMCatcher to replicate every VM)
  Storage tests, improvements  SWIFT and CDMI for big-data
    User Guide under development (e.g. for EuroArgo use case)
    Need for more endpoints. Please enable!
  Merging FCTF and FedCloud User Support meetings
Long-tail platform (access.egi.eu VO):
  Still lacking cloud resources (2 site so far)
  Please, please join!
  Merging fedcloud and access VOs?

## Slide 11: Ongoing SLA – OLA negotiations
Use Case | Description | Supporters (so far) | Status | Requirements
HBP | IPython/Jupyter notebooks for human brain: cloud-based virtual collaborative workspace | FZJ, DESY and CYFRONET | Cloud testing and SLA negotiation in progress | 20 Large VMs with 100 GB of local disk Permanent storage: 10 TB
ESA TEPs | Thematic platforms for Satellite Data exploitation | 100%IT, GRNET GWDG, CESGA RECAS-BARI and CYFRONET | Cloud tests and SLA negotiation in progress | 60-80 VMs: each VM with at least 2 cores, 4-8 GB RAM (some with 32 GB), 120 GB disk Permanent storage: 40 TB
Nanotechnology | Quantum Chemistry/Monte Carlo codes | INFN-ROMA3. IISAS-BRATISLAVA, UNINA-EGEE and PSNC | HTC testing and SLA neg. in progress | HTC cluster with MPI: InfiniBand >=32 CPU cores
EXTraS | Harvest unexplored temporal domain information from serendipitous data collected by the European Photon Camera. | RECAS-BARI and CYFRONET | Cloud testing and SLA negotiation in progress | Number of VM: 50 Number of cores: 2 core per VM Memory: 8 GB per VM = total 40 GB Scratch/ephemeral storage: 50 GB per VM
LSGC | Goal is to secure HTC resources for bioinformatics, genomics, bio-banking, medical image, etc. The VRC is to serve the European Life Science community in its exploitation of grid services | IN2P3-IRES, OBSPM, INFN-FERRARA, UKI-LT2-Brunel, EFDA-JET, PSNC | Assigned (HTC) SLA negotiation in progress | HTC: 100,000h * X HEPSPEC-hours (X year) 5,000h * X HEPSPEC-hours (X year) X = 1,3 10 TB of storage Cloud: VM with 4GB of RAM and 100 GB of disk storage SLA negotiation in progress

## Slide 12: Events, training, etc.
Training plan for next 16 months – Nearly complete:
  https://documents.egi.eu/document/2810
  Training modules, relevant events, joint activities with CCs and projects
    FedCloud through APIs, GPGPU, Docker, ODP, AAI proxy,…
  Up-to-date list of community events: https://wiki.egi.eu/wiki/Community_events
Webinars TODAY:
  13:00: Cloud service procurement: http://www.hnscicloud.eu/events/lecture-building-the-european-open-science-cloud-procuring-cloud-services-in-public-research
  14:00: WS-PGRADE on EGI FedCloud: https://indico.egi.eu/indico/event/2977/
  15:00: EUDAT-OpenAire: http://eudat.eu/events/webinar/research-data-management-an-introductory-webinar-from-openaire-and-eudat
DI4R – Submit abstract by 3rd of June!!!

## Slide 13: Thank you