# 8th DARIAH CC teleconference meeting

MINUTES

09th February 2016

Meeting's chair: Davor Davidović (ddavid@irb.hr)

Meeting agenda and presentation materials:

https://indico.egi.eu/indico/event/2885/

Attended:

- Roberto Barbera

- Giuseppe La Rocca

- Zoltán Farkas

- Eva Cetinić

- Davor Davidović

Agenda:

- Status of the DARIAH CC

- Status of VO and AAI integration

- Training and dissemination

- Collaborative actions

- Future plans

- Status of the DARIAH CC

- DARIAH WG - All VCC-heads responded positive to the WG proposal. I expect a final positive decision any moment.

- VO – Zoltan will provide the status of the VO later and collect resources/sites that support vo.dariah.eu

- Upcoming public deliverables

- D6.2 (Repository deliverable)

  - The deliverable passed internal review and submitted to the EC

- D6.5 (CDSTAR-SIR deliverable)

  - No concrete feedbacks, Philipp is actively working on it.

Action required: Davor and Gergely will contact Philipp, ask for the draft version, 	provide help if needed

- Sustainability and user engagement plan (sent by Maarten via email):

- Link to draft version: here

- The document structure is updated to better reflect the focus on the demonstrators.

- Gergely – will align the document with the service design documents (https://documents.egi.eu/public/ShowDocument?docid=2550). To have all demonstrators described using section 1 and 2. These would unveil the relevant stakeholders and the added value, as input for looking into user involvement and sustainability.

- Dissemination

- 4 community related events recognized:

  - DHBenelux conference (http://www.dhbenelux.org/), Luxembourg, June 2016

  - Digital Humanities 2016 (http://dh2016.adho.org/cfp/), Krakow, July 2016

    - The largest DH conference and thus will be good to be presented there

    - Eveline submitted a long paper (accepted for a poster session)

    - Another proposition is to submit a workshop proposal for the conference

    - Deadline for workshop proposals: 14th Feb 2016

Action required: The final decision on the workshop program by Wed, 10th Feb 2016. Produce a workshop proposal (up to 1500 words). Davor will open google docs and start editing.

  - EURALEX 2016 (http://euralex2016.tsu.ge/), Tbilisi, Georgia, Sep 2016

    - Eveline submitted a proposal  for a poster and workshop (both accepted)

    - No further notice

Action: Davor will contact Eveline on the status and the further actions required for this conference

- Roberto gave a short presentation of the e-Infrastructure forum (outcome of the EU project done by INFN)

  - Link: http://discourse.sci-gaia.eu/

  - 100 registered users, possible to create external (public) and internal (private) discussion section, easier to follow multiple conversations than by using email

  - All participants has to be registered (by their home IdP, EduGain)

Action: Roberto will create two new categories (one external and one internal) for DARIAH CC

- Collaboration actions

- READ – Recognition and Enrichment of Archival Documents

- OpenMinTed (http://openminted.eu/)

- Eveline is involved in one and have a strong collaboration with a partner involved in other project.

- No discussion on the meeting (Eveline was missing)

Action: Davor will circulate an email and start discussion with Eveline.

- Mini-projects

- DARIAH e-Science portal – https://dariah-guse.lpds.sztaki.hu/

  - the portal will be Service Provider inside the DARIAH AAI

  - Roberto suggested to provide access to the portal for non-DARIAH members as well

- Integration of mini-projects

  - Action: Giuseppe will send to Zolan the configuration file and the guidelines how to integrate gLibrary and PSSE into e-Science portal

- gLibrary

  - pending status: waiting for the relations between the databases from Eveline in order to complete the repository

  - A new person (Antonio Calanducci) from INFN will work on gLibrary and DARIAH CC (starting in March 2016).

- AAI

- Zoltan and Peter (DARIAH AAI) decided on the work plan

  - First step: make DARIAH eScience gateway a Service Provider inside DARIAH AAI

- Next action → integrate SAML auth

- AAI workshop for Service and Resource Providers (http://anenadic.github.io/2016-03-15-elixir-aai-workshop-manchester/)

  - co-organized by the DARIAH-DE, Peter (contact for DARIAH AAI in organization committee)

Action: Zoltan will contact Peter to collect more info on this workshop

- Upcoming internal milestones

- Wed, 10th Feb 2016 – Final decision on proposing a workshop for Digital Humanities 2016 conference (Krakow, July 2016)

  - decide on the scope and topic of the workshop. An idea is to demonstrate the DARIAH e-Science portal functionality and 3m mini-projects (gLibrary, CDSTAR and PSEE)

- 14th Feb 2016 – deadline for sumitting the workshop proposal

- Integration of gLibrary/SSE with WS-PGRADE portal

  - Giuseppe – send configuration and war files to Zoltan to integrate gLibrary and eScience portal

- Next meeting

  - In the week starting 7th March, Davor will send doodle poll one week in advance