## Slide 1: e-Infrastructure commons Updates
Technical Outreach Expert
Diego Scardaci

## Slide 2: Outline
Milestones & Deliverables
Periodic Report
First project review
EGI Conference

## Slide 3: WP3 Milestones & Deliverables

## Slide 4: Completed Deliverables and Milestones
M3.2 - User requirements on data accounting collected (R) (PM12)
D3.2 - Design of the EGI Service Registry and Marketplace (R) (PM12) (will be sent to the EC today)
D3.3 - Accounting Repository release (OTHER) (PM12)
D3.4 - First release of the Operational tools (OTHER) (PM12)
D3.5 - Analysis on techniques to manage big data on the EGI accounting system (R) (PM12)

## Slide 5: Next WP3 Deliverables and Milestones
D3.6 - First release of the new Accounting Portal deployed in production (OTHER) (PM14) (CESGA)
M3.3 - Operational tools development roadmap revised (R) (PM16) (EGI.eu)
M3.4 - Pilot services and best practices to enable federated AAI solutions released (DEM) (PM16) (GRNET)
D3.7 - First release of the EGI Service Registry and Marketplace prototype (DEM) (PM18) (FMI)
M3.5 - The first version of the EGI Marketplace is demonstrated (DEM) (PM18) (FMI)
D3.8 - First data accounting prototype (DEM) (PM20) (STFC)

## Slide 6: Important dates for PM14 deliverable
New Accounting Portal
Start External Review: 1.04
At AMB and PMB: 15.04
At QM: 22.04
At EC: 30.04
External review will include the testing of the portal

## Slide 7: Periodic Report

## Slide 8: Periodic Report
JRA1 contribution completed:
  https://docs.google.com/document/d/18N2LONbe69Wtd0P9dR8MER-vM1ehCo4Ib5qwZ4gwv0A/edit#
Activity metrics to be finalised

## Slide 9: First project review

## Slide 10: Project review
21° of April – Bruxelles
Rehearsals:
  1° of April
  12° of April
  15° of April
Slides printed the 18° of April

## Slide 11: EGI Conference

## Slide 12: EGI Conference
6° - 8° of April – Amsterdam
  https://indico.egi.eu/indico/event/2875/
Tools and services for federated distributed services session:
  8° April 11:00-12:30
  Programme to be published soon
  Talks: Accounting repo & portal, ARGO, Ops Portal