Fortnightly meeting of NA3 task and subtask leaders, 12/01/2011:

Participants:

  - Steve Brewer EGI.eu (chair)

  - Gergely Sipos EGI.eu (minutes)

  - Claire Devereux STFC

  - William Vassilis Karageorgos, Marios Chatziangelou, Alex Nakos IASA

  - Goncalo Borges LIP

  - Karolis Eigelis, Nuno Ferreira, Richard Mclennan EGI.eu

Review of Tasks with decided actions:

- TNA3.1:

  - Activity input to QR3 is due on the 10th of Feb.

  - No QR4, but annual report. Due and of March

  - 1st year project review

    - Input to NA3 review presentation is expected from every task leader

    - Some of the task leaders may need to be present. This will be known closer to the event.

    - Dates:

      - June 8: Telephone rehearsal

      - June 15: F2F dress rehearsal in Amsterdam

      - Jun 30-Jul 1: Review in Amsterdam

  - Key event we have to focus on is UF

    - Review of abstracts is ongoing

  - NA3 (sub-)task leaders F2F meeting

    - Mar 3, Amsterdam – arrange travel

  - Open, F2F InSPIRE AMB meeting

    - Mar 2, Amsterdam.  (Day before NA3 meeting!)

    - Task leaders are invited to join, but not compulsory

- TNA3.2:

  - First VRC MoUs are expected during the next weeks

  - Requirements from VRCs will drive the evolution of NA3 technical services

- TNA3.3:

  - NGI user support contact list is available in Wiki: https://wiki.egi.eu/wiki/TNA3.3_NGI_User_Support_Teams

  - Ongoing activity - Expanding this contact list to cover every NGI (not just NA3 members)

  - Blog and “Requirement marketplace” are expected to provide mechanisms for NGIs to better integrate into the user support community and to user communities

  - Discussions about an EGI knowledge base to make the activities and achievements of NGIs more visible and searchable for VRCs

- TNA3.4:

  - Community repository (Marios)

    - AppDB as a front-end to submit new releases

    - AppDB stores metadata and link to physical releases

    - Quality control mechanism should be used, but should be more lightweight than for software for SA2

  - AppDB (William)

    - converted the features that are planned for the next 6 months to EGI RT tickets (https://wiki.egi.eu/wiki/USAG - These tickets are stored in the

    - filed a savanna ticket to the GOCDB for NGI/ROC API enhancements

    - contacted the CIC people for VO API clarifications

    - drafted prototype NGI/VO support in the development branch

    - communicated with people from the GISELA project about porting app entries

    - addressed some bugs in the production branch

    - supported "newcomer" write-access requests and issues

    - Over the next two weeks, we will be mainly working on further development of

    - the NGI/VO integration support in the development branch, while addressing

    - bugs and requests in the production branch.

  - VO services (Goncalo)

    - FAQ about “VO support group” is available, linked to NA3 wiki: https://wiki.egi.eu/wiki/VO_Managment_FAQS

    - We are now deploying/testing a VO catch-all version for NAGIOS. This is something which the developers were not aiming to have since the beginning, and they do not have documentation for it, so we are working with them as the work evolves.

    - We have clarified the question raised in GGUS ticket raised to VO Services (https://gus.fzk.de/ws/ticket_info.php?ticket=63564) with SA1 which gave origin to an RT ticket for middleware enhancement:https://rt.egi.eu/rt/Ticket/Display.html?id=881

    - GGUS groups (Action for Goncalo):

      - RAG group can be closed

      - VO support group: ask Cyril whether they are still using it. If not close it, if yes discuss how the usage relates to the VO services unit. Consider merging the two units (keep the VO services name)

  - RT (Gergely)

    - Two new queues for Feature tickets:

      - user-tools-roadmap: Features of future releases of Operational Tools (developed by JRA1) Queue is managed by Daniele Cesini (JRA1 leader)

      - ops-tools-roadmap: Features of future releases of NA3 Technical Tools (developed within TNA3.4) Queue is managed by Marios

    - UCST is working on documentations about the usage of the RT system

  - Web pages (Steve)

    - Review and update of user support section of EGI webpage: Meeting with Dissemination team on next Tuesday to discuss content update

    - ACTION: Your input about the Website is welcome: What should be visible about your activity/tool?