## Slide 1: TSA1.5 Accounting Workplan 2011
John Gordon
Planning Workshop 19/1/2011
Updated 20/1

## Slide 2
This plan combines developments
  to the APEL server infrastructure done in EGI-Inspire JRA1 and
  matching developments to the apel parsers and client in EMI
It is the deployment of both of these that is relevant to EGI-Inspire SA1.
A simple deployment plan would be dull without explaining what will change so I list all of them to put the SA1 work in context.

## Slide 3
Design of regional apel system has necessitated several redesigns.
A –Schema
  Simplification – removed unused or duplicate fields
  Add new fields for MPI
  Rename fields to align with OGF UR
  Integrity – new RecordID
B - Message Format and Infrastructure
  Use STOMP on production infrastructure
  Requires a new encryption and authorisation model.
C – change job record database to reflect A and B.

## Slide 4: Milestone Summary
1 | Complete migration from R-GMA to ActiveMQ | 31—Jan-11 | SA1
2 | Design new DB schema and Message Format for jobs and summary | 21-jan-11 | JRA1+EMI
3 | Pre-production version of summary infrastructure | 11-feb-11 | JRA1
4 | Summary Infrastructure deployed at RAL | 25-feb-11 | JRA1
5 | New Central Infrastructure in Production | 02-apr-11 | SA1
6 | Central Server ready to receive new format input | 15-Apr-11 | SA1
7 | New APEL Publisher (stomp-based) released | 16-Apr-11 | SA1+EMI
8 | Regional Accounting Server packaged and released to NGIs. | 01-Jun-11 | SA1
9 | Regional Deployment and Migration | June onwards | SA1

## Slide 5: Milestone 1
Migrate all sites from glite-MON to glite-APEL and close down R-GMA infrastructure.
Original target 31/12/2010. Extended to 31/1/2011
Sites who do not migrate by due date will continue to accumulate their accounting data and can publish it whenever they migrate.

## Slide 6: Milestone 2
Design new DB schema for Job Records and Summary Job Records
Design new message format for JR and SJR
21 Jan 2011

## Slide 7: Milestone 3
Summary Consumer (SJR) deployed in pre-production
Stomp consumer + record loader (SJR) + SJR database + SJR to legacy publisher
Pre-requisite for regional instances to publish summaries to central repository
And for the latter to receive them.
11th Feb 2011

## Slide 8: Milestone 4
Summary Publisher deployed at RAL
Summary Publisher distributed as source to Region Cs
SGAS, OSG, DGAS, etc can develop and test their own publisher to publish summaries directly to APEL.
25th Feb 2011

## Slide 9: Milestone 5
New DB schema for JR deployed at RAL
Legacy DB to new DB publisher deployed
Old DB to new DB migrated
Summariser from JR to SJR deployed
Summariser (to Portal tables) deployed
2 April 2011

## Slide 10: Milestone 6
Job Record Consumer (JR) deployed
Record Loader (JR+SJR) deployed
15th April 2011
Central Server ready to receive new format input

## Slide 11: Milestone 7
New APEL Publisher (stomp-based) released
15th April 2011

## Slide 12: Milestone 8
Regional Accounting Server packaged and released to NGIs.
1 June 2011

## Slide 13: Milestone 9
Regional Deployment and Migration
1st June onwards

## Slide 14: Testing
At most stages we will have a test infrastructure for people to test against.

## Slide 15: Other Work
OGF-RUS Interface – would integrate Globus sites.
After Milestone 3 we will be able to develop other accounting record types in parallel with milestone 3. (eg storage, clouds)
  And publish them after milestone 6
Local Job Accounting
  This is schema semantics, not a change to the infrastructure.
Integrating other accounting systems to make sure all sites/NGIs are covered.
  No firm plan. Complete requirements capture and draft solutions by end of April 11.
  Outstanding issue of ARC outside Scandinavia. i.e. those without SGAS.