## Slide 1: TSA1.8 Roadmap for 2011
Christos Kanellopoulos (AUTH/GRNET)
Dimitris Zilaskos (AUTH/GRNET) Vera Hansper (CSC/FINLAND)

## Slide 2: Providing a reliable grid infrastructure
EGI Operations Level Agreements
Availability/Reliability results and procedures
Operations tools proposals
EGI catch all central services

## Slide 3: OLA s
Continue adaptations to the OLA between NGI and sites (January 2011)
Produce OLA between EGI and NGIs (February 2011), as well as a Core services OLA (Spring 2011)
Propose an OLA amendment procedure (Spring 2011)
Evaluate the impact of increased availability suspension threshold to establish if it is sensible to enforce the increased thershold from the second year of the project (Ongoing, finish on May 2011)
Reconvent with the OLA task force at least once per 2 months
Availability/Reliability
  Continue adding useful material to the wiki (ongoing)
  Investigate if Operational tools advances can simplify the procedure (ongoing)
  Determine the prime causes of sites failing to meet OLA targets ( May 2011)

## Slide 4: Operations Tools
Propose Changes for Operations tools (January 2011)
Data more readily available to NGIs (Spring 2011)
Follow-up with developers for issues that affect accuracy (Ongoing)

## Slide 5: Catch all Central Services
EGI catch all central services
  EGI VOMS service: migrate dteam from VOMRS/gLite VOMS to new VOMS versions which implements VOMRS functionality
    Provide feedback for improvements in the workflows to the developers given the experience obtained so far (February 2011).
  EGI catch all CA: continue operations for countries without CA collaborating with EGI
  WMS/VOMS available to international VOs approved by EGI

## Slide 6: Operational documentation subtasks
Site Certification Manual (due for release in Jan. 2011 at the OMB)
Operational Procedures Manuals (ongoing)
Best Practices (ongoing)
Training Guides (ongoing)
GOC WIKI transfer (terminal)
Documentation relocation (terminal)
2 Face to Face meetings / year co-located with the EGI conferences.

## Slide 7: Sub task roadmaps
Operational Procedures Manuals – Lead: Peter Slizik
  1st Version of EGI manuals END MARCH
  ROD Procedure Manual
  NGIs and Sites Procedure Manual
  COD Procedure Manual
  (This first release is a fairly major endeavor.)
  Phone conferences biweekly for the first 4 months of 2011
  Aim for 3 releases / year - MARCH, JULY, NOVEMBER
  NOTE: COD procedure manual will need major input from COD.
Best Practices – Lead: Roger Oscarsson
  Monthly phone conferences
  Wiki structure will be upgraded in the next coming months
  This topic is fluid, and relies on input/content from NGIs

## Slide 8: Sub task roadmaps
Training Guides – Lead: David Bouvet
  Monthly phone conferences (or as needed.)
  1st release due (possibly) end February.
  Dashboard HOWTO
  Training Guide (beginners)
  Quick Sheets (will commence these in March.)
  Aim for 3 releases / year – with minor updates if there are major tool changes.
GOCWIKI transfer – Lead: Vera Hansper
  This is a complex task, but needs to be completed within the next 6 months.
  Currently, some of the GOCDB info has been moved over to the EGI WIKI
  Jan. 2011 : WIKI structure discussions with Tiziana (encompasses general wiki structure for
  the overall task.
  Feb. 2011 : Ensure that place holders and structures are set up and working
  Mar. - Jun. 2011 : Moving data.
  Phone conferences every 3 to 4 weeks.

## Slide 9: Sub task roadmaps
Documentation relocation – Lead: Vera Hansper
  This task has not started yet.
  The task involves indentifying and co-ordinating all documentation relevant to EGI
  Operations, and ensuring that this is properly accessible from either the WIKI or the document server.
  Task will start in Apil/May 2011