## Slide 1: e-Infrastructure commons Updates
Technical Outreach Expert
Diego Scardaci

## Slide 2: Outline
First project review
Milestones & Deliverables
DI4R Conference

## Slide 3: First project review

## Slide 4: General Comments
Very positive feedback
Refinements needed to increase the impact of the project
  KPIs to be improved
  Better communication
Business Engagement plan: work with SMEs and industry
Simple and unified access mechanism to visualise all software produced by the project  EGI GitHub for all the tools?

## Slide 5: Feedback on WP3
Experts satisfied of WP3 work
  Services developed in a user-driven way
AAI:
  Requirements for AARC to fix the granularity issues of the current 4-layer domain model for LoA
  Consider prior art in the field of IdP discovery and its impact on the Uis
  Accounting linking: educate users on its implication
  EIDAS

## Slide 6: Feedback on WP3
Marketplace:
  Service discovery in function of the different type of users
  Additional tools to be analysed: AppCara, App Marketplace, Juiu, Alien4Cloud and Cloudify
  Recomments to take into account tools for open source cloud orchestration
  Architecture still in a very conceptual stage  to be improved in D3.16

## Slide 7: Feedback on WP3
For all tools:
  Installation and user guides

## Slide 8: Feedback on WP3 Deliverables
D3.1 Accounting Portal design:
  Revise to include a glossary
D3.2 Marketplace design:
  Accepted
D3.3 Accounting repository
  Accepted
D3.4 Ops tools
  Revise  formatting issue
D3.6 Big data tools for the EGI Accounting
  Revise to include a glossary

## Slide 9: WP3 Milestones & Deliverables

## Slide 10: Next WP3 Deliverables and Milestones
June 2016: M3.3 - Operational tools development roadmap revised (R) (EGI.eu)
June 2016: M3.4 - Pilot services and best practices to enable federated AAI solutions released (DEM) (GRNET)
August 2016: D3.7 - First release of the EGI Service Registry and Marketplace prototype (DEM)(FMI)
August 2016: M3.5 - The first version of the EGI Marketplace is demonstrated (DEM) (FMI)
October 2016: D3.8 - First data accounting prototype (DEM) (STFC)

## Slide 11: Important dates for PM16 deliverable
M3.3 (EGI.eu) & M3.4 (GRNET)
Start External Review: 1.06
At AMB and PMB: 15.06
At QM: 22.06
At EC: 30.06

## Slide 12: M3.3 Roadmap - Status
Waiting contributions from Marketplace, AAI, ARGO & Messaging

## Slide 13: M3.4 AAI - Status
?

## Slide 14: DI4R 2016

## Slide 15: DI4R 2016 Conference Digital Infrastructures for Research
Krakow, Poland
2016, September 28-30.
Co-organised by EGI, EUDAT, GEANT, OpenAIRE and RDA Europe
Call for participation (deadline 3 June!)
http://www.digitalinfrastructures.eu/

## Slide 16: DI4R 2016
WP3 Contributions ?
Session on tools for e-infrastructures ?