# 11th DARIAH CC teleconference meeting

MINUTES

9th June 2016

Meeting's chair: Davor Davidović (ddavid@irb.hr)

Meeting agenda and presentation materials:

https://indico.egi.eu/indico/event/3014/

Attended:

- Gergely Sipos

- Giuseppe la Roca

- Antonio Calanducci

- Eveline Wandl-Vogt

- Zoltan Farkas

- Davor Davidovic

Agenda:

- Cloud resources

- Status of the demonstrators and services

- DARIAH portal status

- User invol.&sust. Plan

- Upcoming events

- Euralex workshop

Cloud resource in vo.dariah.eu

- IRB

  - setting up ceph storage – waiting to finish the procurement of some equipment – in process

  - solution: provide compute resources without block storage

    - compute resources are not urgent for now, the storage infra is critical

- GWDG → need to configure the VO → Giuseppe will send email to Philipp

- SZTAKI

  - Still missing a system admin, don't know when it will be resolved

  - work that has to be done: install OCCI

  - solution: Access SZTAKI cloud site directly from the WS-PGRADE portal

WS-PGRADE (DARIAH science portal)

- Portal support DARIAH VO

- Zoltan is still working on registering the portal as service provider in EduGain

- New portal web-page:  https://dariah-gateway.lpds.sztaki.hu/

- Glassfish integration (a requirement for PSSE) is postponed

- Actions: Zoltan to finish with portal registration in EduGain as service provider

CDSTAR

- Waiting for the status report

- Official release is expected by the end of July

- Actions: Davor will contact Philipp on the status of the CDSTAR and OCR use case

gLibrary and Bavarian dialects dataset use case

- Antonio is finishing the portlet for the Bavarian dataset

  - will be finished by the end of June 2016

  - Once the portlet is finished Antonio will integrate it into Catania Science Gateway → Antonio will send email and link to test the installation

  - The access to Bavarian dialects is free (no authentication is required – it is how Catania Science Gateway is setup → for demonstration purposes)

  - Actions:

    - Antonio will send portlet .war file to Zoltan

    - Zoltan will integrate it into DARIAH portal

- The development to be finished by the of June

Semantic Search Engine

- Available in the long-tail Catania Science Gateway

- For now the PSSE will remain there

  - in order to integrate it with DARIAH portal, a migration to glassfish server of WS-PGRADE portal is required → postponed → will be done later

User engagement and sustainability plan

- Gergely and Giuseppe transformed the DARIAH CC wiki page into a page that promotes the DARIAH CC demonstrators and services

  - Services and demonstrators sub-sections are added but the text is missing

  - Davor suggested to open a new wiki page (sub-page) and move there the original DARIAH-CC wiki's text

  - Actions:

    - Antonio will add text for the gLibrary and Bavarian dialects dataset

    - Zoltan will add text for the DARIAH portal

    - Philipp and Tibor add text for the CDSTAR (once it is finished)

- The first version of the User involvement and sustainability plan is available at the link: https://docs.google.com/document/d/1VAvxzmJHrdMMf93YMjBMdxXpaq6dNUYWTAK1qurmOOc/edit#

  - Actions: all partners are asked to read the plan and comment and suggestions, deadline 15.6.2016 (Wed)

Annual meeting

- The formal length of possible contributions and the DARIAH annual meeting concept are still not defined → Davor will send email to Tibor and Sara Chambers

- Actions: Once he get the info, Davor will forward to the DARIAH-CC mailing list and discuss on the contribution

Other events

- Digital Humanities DH2016

  - poster presentation is accepted

  - Eveline need some help preparing it → Gergely with contact Eveline

- EURALEX conference

  - poster presentation and the workshop are submitted and accepted

  - How to decide who will attend the conference from the CC and what is need to be done prior to the workshop

- Action: Davor will arrange a skype call with Eveline and Gergely

- HaS (Humanities at Scale) European project - http://has.dariah.eu/

  - “...aim to integrate digitally enabled research in the arts and humanities in Europe and beyond and to operate a platform to enable trans-national arts and humanities research.”

  - HaS started a survey on DH Services (what researchers need)

    - the output of this survey can be input for the CC – integration with DARIAH portal

  - Actions: Davor will arrange a skype call with the HaS representatives. The idea of the call is to introduce DARIAH CC, who we are, our goals and outcomes and the forseen mutual benefits

- More effort has to be done on the CC visibility

  - Actions: Davor will contact the admin of the DARIAH web pages and try to put a short description of the DARIAH CC on the DARIAH web