## Slide 1: e-Infrastructure commons Updates
Technical Outreach Expert
Diego Scardaci

## Slide 2: Outline
Milestones & Deliverables
Marketplace
  Status of the design and assessment of the prototypes

## Slide 3: WP3 Milestones & Deliverables

## Slide 4: WP3 Deliverables and Milestones
August 2016: D3.7 - First release of the EGI Service Registry and Marketplace prototype (DEM)(FMI)
  Currently in external review
August 2016: M3.5 - The first version of the EGI Marketplace is demonstrated (DEM) (FMI)
  Prototypes available online but not showcased during the DI4R conference
October 2016: D3.8 - First data accounting prototype (DEM) (STFC)
  Plan agreed with STFC:
    Deliverable to be ready by Oct 27 (including internal review)
    External review in the first 2 weeks of November
    Deliverable to be finalised in the second half of November

## Slide 5: Next WP3 Deliverables and Milestones
February 2017: D3.9 Identity Management for Distributed User Communities (R) (GRNET)
February 2017: D3.10 Second release of the accounting and operational tools (OTHER) (CSIC, CNRS, STFC)
  Includes Accounting repository, accounting portal, Operations portal, GOCDB, ARGO, messaging infrastructure and security monitoring tools.
  Merge of old D3.10, D3.11 and D3.12
February 2017: D3.14 Report on data accounting (R) (STFC)
  Report of the Data Accounting activity: including the data usage record definition, storage solutions supported and integration with accounting repository
April 2017: D3.13 Second release of the EGI Service Registry and Marketplace prototype (DEM) (FMI)
April 2017: M3.6 The second version of the EGI Marketplace is demonstrated (FMI)

## Slide 6: Important dates for PM24 deliverable
D3.9 AAI, D3.10 Tools and D3.14 Data Accounting
Start External Review: 01.02
At AMB and PMB: 15.02
At QM: 22.02
At EC: 28.02

## Slide 7: Marketplace Status of the design and assessment of the prototypes

## Slide 8: Marketplace Data Model
Defined the data model for services in the EGI service catalogue
  Service areas (category in the marketplace)
  Services (sub-category in the marketplace)
  Service options (products in the marketplace)
Service area | Services
Compute | Cloud Compute, Cloud Container Compute and High-Throughput Compute
Storage | Online Storage, Archive Storage
Data | Data transfer, Content Distribution
Operations | Configuration Database, Service Monitoring
Security | Check-in, Attribute Management
Training | Training Infrastructure, FitSM

## Slide 9: Marketplace Assessment of the prototypes
Two prototypes available:
  Open IRIS based: http://egi.science-it.ch
  Prestashop based: http://vps302866.ovh.net/
Implementation of the defined data model
Both technologies present limitations for EGI
  See D3.7 for more details: https://documents.egi.eu/document/2914

## Slide 10: Next Steps
Design
Extend Integrated Management System (IMS) procedures to take into account the marketplace
Define workflow to automate the Access Request Management process
  Interfaces towards other EGI tools
Integrating Marketplace/LToS platform/e-Grant
  Unique interface for customers
Extend the data model for other service categories (e.g. thematic community platforms)
Criteria to on board and monitor services

## Slide 11: Next Steps
Assessment of the technologies
Evaluate the cost to customise PrestaShop and Open IRIS to satisfy the EGI requirements
Evaluate other technologies
  WPMUDEV.org: WordPress ecommerce plugin adopted by UberCloud