## Slide 1: e-Infrastructure commons Updates
Technical Outreach Expert
Diego Scardaci

## Slide 2: Outline
Milestones & Deliverables
Other important information
  Plan for exploitation and dissemination
  EGI ISO 20000 certification
    CHM and RDM processes
  New requirements queue
  New ARGO messaging service
  Update on the marketplace

## Slide 3: WP3 Milestones & Deliverables

## Slide 4: WP3 Deliverables and Milestones Delayed deliverables
October 2016: D3.8 - First data accounting prototype (DEM) (STFC)
  External review is running
  Expected comments by Feb 8th

## Slide 5: WP3 Deliverables and Milestones End PY2 (Feb 2017)
D3.9 Identity Management for Distributed User Communities (R) (GRNET)
  Current status: Only ToC available
D3.10 Second release of the accounting and operational tools (OTHER) (CSIC, CNRS, STFC)
  Includes Accounting repository, accounting portal, Operations portal, GOCDB, ARGO, messaging infrastructure and security monitoring tools.
  Merge of old D3.10, D3.11 and D3.12
  Current status: preparation of the full draft for internal review
D3.14 Report on data accounting (R) (STFC)
  Report of the Data Accounting activity: including the data usage record definition, storage solutions supported and integration with accounting repository
  Current status: internal review

## Slide 6: Important dates for PM24 deliverable
D3.9 AAI, D3.10 Tools and D3.14 Data Accounting
Start External Review: 01.02
At AMB and PMB: 15.02
At QM: 22.02
At EC: 28.02

## Slide 7: WP3 Deliverables and Milestones Next deadlines
April 2017: D3.13 Second release of the EGI Service Registry and Marketplace prototype (DEM) (FMI)
April 2017: M3.6 The second version of the EGI Marketplace is demonstrated (FMI)
June 2017: D3.15 Second Data Accounting prototype (DEM) (STFC)
June 2017: D3.16 Final report on the EGI Service Registry and Marketplace (R) (FMI)
August 2017: D3.17 Final release of the accounting and operational tools (OTHER) (CSIC, CNRS, STFC)

## Slide 8: WP3 Other important information

## Slide 9: Plan for Exploitation and Dissemination
Mandatory for each EGI-Engage result
  Result: any tangible or intangible output, more particularly data, knowledge or information
Why ?
  Creating a catalogue of project results (http://go.egi.eu/egi-engage-results)
  Develop an overall PEDR for the whole project

## Slide 10: EGI ISO 20000 Certification CHM and RDM processes
EGI ISO 20000 certification in progress
  Successfully audit last December
  Identified non conformities will be fixed soon
From now changes in the EGI tools and deployment of new release must go through:
  Change Management process
    To approve big requirements
    To approve new releases
    More details in Matthew’s presentation
  Release and Deployment Management process
    Use PROC23 to deploy a new release in production
      https://wiki.egi.eu/wiki/PROC23

## Slide 11: New requirement queues
New requirement queues for EGI tools in RT
  1 queue for tool replacing the old requirement queue
  AAI-check-in, acc-portal, acc-repository, AppDB, E-grant, GGUS, GOC-DB, Marketplace, Ops-Portal, service-monitoring
    2 SSO groups: General queue + watcher
    Only people in the general queue can close the ticket
    People in both queues receive notifications
  requirement queue only to be used for already existing ticket
PT leaders already added in the relevant queues
  Please, check if you receive the notification
  Inform me if you want to add other developers

## Slide 12: New ARGO Messaging service
ARGO Messaging Service (AMS)
  Open source implementation [1] of the Google PubSub service (available on the Google Cloud Platform).
  Simpler than the current Message Broker Network service
  Monitoring, Ops portal and accounting repository should start to test it
    Define a plan with Christos
    Migration to be completed by EGI-Engage
  Documentation: http://argoeu-devel.github.io/messaging/v1/

## Slide 13: Marketplace
Two prototypes implemented:
  PrestaShop based (Cyfronet)
    http://marketplace.egi.eu/
  Open IRIS based (FMI)
    http://egi.science-it.ch/
Currently under evaluation by EGI