## Slide 1: e-Infrastructure commons Updates
Technical Outreach Expert
Diego Scardaci

## Slide 2: Outline
Milestones & Deliverables
Final project review
Marketplace

## Slide 3: WP3 Milestones & Deliverables

## Slide 4: WP3 Deliverables and Milestones PY3 Status
April 2017: D3.13 Second release of the EGI Service Registry and Marketplace prototype (DEM) (FMI)
  Current status: Submitted to the EC
April 2017: M3.6 The second version of the EGI Marketplace is demonstrated (FMI)
  Current status: Submitted to the EC
June 2017: D3.15 Second Data Accounting prototype (DEM) (STFC) DELAYED
  External review
June 2017: D3.16 Final report on the EGI Service Registry and Marketplace (R) (FMI) DELAYED
  External review
August 2017: D3.17 Final release of the accounting and operational tools (OTHER) (CSIC, CNRS, STFC)
  Draft in preparation (ready end of this week, early next week)

## Slide 5: WP3 Deliverables and Milestones Next deadlines
August 2017: D3.17 Final release of the accounting and operational tools (OTHER) (CSIC, CNRS, STFC)
  All contributions received
  Working on the full draft

## Slide 6: WP3 Final project review

## Slide 7: Final project review
Final review on 23-24 October in Bruxelles
  Capacity of the meeting room is limited
  Participants:
    Project and EGI Directors
    WP Leaders
    Technical experts (by invitation)

## Slide 8: WP3 Contribution for the review
Slides
  I will ask your help to review the slides (Sept/Oct)
Activity metrics
  To be provided in the next weeks
Contributions for the periodic (M13-M30) and final reports

## Slide 9: 1st review - Feedback on WP3
Experts satisfied of WP3 work
  Services developed in a user-driven way
AAI:
  Requirements for AARC to fix the granularity issues of the current 4-layer domain model for LoA
  Consider prior art in the field of IdP discovery and its impact on the Uis
  Accounting linking: educate users on its implication
  EIDAS

## Slide 10: 1st review - Feedback on WP3
Marketplace:
  Service discovery in function of the different type of users
  Additional tools to be analysed: AppCara, App Marketplace, Juju, Alien4Cloud and Cloudify
  Recomments to take into account tools for open source cloud orchestration
  Architecture still in a very conceptual stage  to be improved in D3.16

## Slide 11: Feedback on WP3
For all tools:
  Installation and user guides
Accounting Portal:
  Architecture still in a very conceptual stage  to be improved in D3.17

## Slide 12: WP3 Activity Metrics
M.JRA1.AAI.1: Number of communities adopting federated IdP
M.JRA1.Marketplace.1: Number of entries in the EGI Marketplace (i.e. services, applications etc.)
M.JRA1.Accounting.1: Number of kinds of data repository systems being integrated with the EGI accounting software

## Slide 13: WP3 Activity Metrics
M.JRA1.Accounting.2: Number of kinds of storage systems being integrated with the EGI accounting software
M.JRA1.OpsTools.1: Number of new requirements introduced in the roadmap
M.JRA1.OpsTools.2: Number of probes developed to monitor cloud resources