## Slide 1: WP1 Project Management
Managing Director, EGI Foundation
EGI-Engage Administrative & Financial Coordinator
Yannick Legré

## Slide 2: Outline
Project overview
Financial Reporting (Y2 and all duration)
Use of resource (Y2 and all duration)
Achievements, issues
Summary

## Slide 3: Project overview

## Slide 4: PY2 Overview
Month 13: 1/03/2016
Month 30: 31/08/2017
Final review: 23-24/10/2017
Final Report due date: 31/10/2017
All figures are provisional and will be finalised for the submission due on 31 October 2017

## Slide 5: Amendment N2/Final budget redistribution
Amendment N2: Signed by EC 24 May 2017
Efforts redistribution after Amendment N2:
  SA2.3: EMBL returns 4 PMs
    CNRS is granted 2 PMs
    EGI Foundation is granted 2 PMs (TSA2.2: generic support activities to communities not involved in CC)
  In SA2.8 for DIRAC portal development: 3 PMs
    UAB left effort shifted to CNRS (1.62 PM)
    UMEA left effort shifted to CNRS (1.38 PM)
  1.6 PMs budget equivalent shifted from INFN to EGI Foundation for Tech Management activities in TNA1.2

## Slide 6: EC contribution (Amendment N2*)
Chart: EC contribution allocation
| 1 : Personnel costs | 2 : Subcontracting | 3 : OC and Travels
EC contribution | 7376647.5 | 20000 | 603352.5
EC contribution | 7376647.5 | 20000 | 603352.5 | 8000000
expenditure | Total Eligible Costs | EC contribution |  | 
 |  | Total | Direct | Indirect
1 : Personnel costs | 8,017,282 | 7,367,282 | 5,893,826 | 1,473,456
2 : Subcontracting | 20,000 | 20,000 | 20,000 | -
3 : OC and Travels | 612,718 | 612,718 | 490,174 | 122,544
Grand Total | 8,650,000 | 8,000,000 | 6,404,000 | 1,596,000
* Include changes after intermediate review
Notes: Unfunded efforts, Swiss, Poland, Asia

## Slide 7: Pre-Financing distribution
PRE FINANCING EC | Euros | Dates | %
Budget Total | 8,000,000 | 01/03/15 | 100%
maximum payment due to PGF retained 85% | 6,800,000 | - | 85%
pre-financing | 3,600,000 | 05/05/15 | 45%
EC interim payment PY1 | 2,871,239 | 20/07/16 | 36%
Final payment | 1,528,761 | 31/12/17 | 19%
PRE FINANCING EGI | Euros | Dates | % (*)
advance N1 | 2,700,000 | 10/07/15 | 42%
advance N2 | 167,903 | 14/03/16 | 3%
advance N3 | 2,478,496 | 16/09/16 | 38%
advance N4 | 1,043,210 | 01/02/17 | 16%
Advance N5 | 24,608 | 14/07/17 | INAF, EISCAT
Left pre-financing | 57,022 | - | 1%
* % on total EC payments |  |  | 
PRE-FINANCING BALANCE | EC payments | EGI payments | %
pre-financing | 3,600,000 | 2,867,903 | 44%
Interim payment PY1 | 2,871,239 | 3,546,314 | 55%
Balance | 6,471,239 | 6,414,217 | 99%
Chart: PRE-FINANCING BALANCE
| pre-financing | Interim payment PY1 | Balance
EC payments | 3600000 | 2871239 | 6471239
EGI payments | 2867903 | 3521706 | 6389609
Notes: Unfunded efforts, Swiss, Poland, Asia

## Slide 8: Financial Reporting

## Slide 9: Financial reporting PY2
Cost per WPs and per category
Chart: 
| 1 : Personnel costs | 2 : Subcontracting | 3 : OC and Travels | 4 : Indirect costs
Used PY2 | 5034259.73 | 26912.78 | 300286.83 | 55681.99
WPs | Used* PY1 12 months | Used* PY2 18 months
WP01: (NA1) | 537,785 | 734,681
WP02 (NA2) | 599,949 | 1,073,835
WP03 (JRA1) | 377,309 | 710,731
WP04 (JRA2) | 300,082 | 663,597
WP05 (SA1) | 257,205 | 486,688
WP06 (SA2) | 888,907 | 1,747,609
Grand Total Eligible costs | 2,961,237 | 5,417,141
*Include Unfunded partners’ cost |  | 
Grand Total Funding | 2,871,239 | 5,158,224
Unfunded costs ratio | 3% | 5%

## Slide 10: Finance reporting all duration
Cost per WPs and per category
Chart: Project costs vs Funding
| Total Eligible Costs | EC contribution
1 : Personnel costs | 8017282.406 | 7367282
2 : Subcontracting | 20000 | 20000
3 : OC and Travels | 612718 | 612718
WP | Planned* All duration | Used* all duration | %
WP01: (NA1) | 1,379,558 | 1,272,466 | 92%
WP02 (NA2) | 1,656,944 | 1,673,784 | 101%
WP03 (JRA1) | 1,029,500 | 1,088,040 | 106%
WP04 (JRA2) | 896,784 | 963,679 | 107%
WP05 (SA1) | 800,206 | 743,893 | 93%
WP06 (SA2) | 2,887,009 | 2,636,516 | 91%
Grand Total Eligible costs | 8,650,000 | 8,378,378 | 97%
*Include Unfunded partners’ cost |  |  | 
Grand Total Funding | 8,000,000 | 8,029,464 | 100.4%
Unfunded costs ratio | 8% | 4% | 

## Slide 11: Finance reporting all duration
Travel and Central Budget
Chart: 
| Project Review meetings | Other conf and meetings (inc support at external events | EGI Forums | Support Travels/Champions programme/ Unfunded Project Partners/Ext Partners | Printing, miscellaneous | EGI's events (invited Speakers) | Design costs | Project management tool | Subcontracting
BUDGET | 9000 | 60419 | 45000 | 73083 | 13273 | 54500 | 10000 | 20000 | 20000
EXPENDITURE | 6768.43 | 53851 | 42728.67 | 48399 | 5327 | 28484.98 | 10557.21 | 23903.13 | 24512.78
CATEGORY | % USED
Subcontracting | 123%
Project management tool | 120%
Design costs | 106%
EGI's events (invited Speakers) | 52%
Printing, miscellaneous | 40%
Support Travels/Champions/Unfunded Project Partners/Ext Partners | 66%
EGI Forums | 95%
Other conf and meetings (inc support at external events | 89%
Project Review meetings | 75%

## Slide 12: Finance reporting all duration
Travel and Central Budget description
Project Review meetings | Cost for final review not accounted ~3k
Other conf and meetings | 12-15 people traveling, ~462 Eur average costs per trip; incl. support at external events
EGI Forums | 2015 EGI community forums organised in Lisbon (May-15) and Bari (Nov-15) 2016 EGI Conferences in Amsterdam (Apr-16) DI4R2016 -Digital Infrastructures for Research 2016 co-organised by EGI, EUDAT, GÉANT, OpenAIRE and RDA Europe, and hosted by AGH Cyfronet in Kraków (Sept-16) 2017 EGI Conferences in Catania, IT (May-16)
Support Travels/Champions/Unfunded & Ext Partners | Support to Asian partners, to Elixir unfunded partners; outreach activities targeted at user communities; incl. Travel costs Diss. Team (3 people) to represent EGI at external events (as part of the communications and events task)
Printing, miscellaneous | Book of Abstracts; Event support material; Technical documentation e.g. FedCloud; brochures; Posters
EGI's events | EGI events costs (booths, badges, shipment), includes travel costs for invited speakers
Design costs | Book of Abstracts; Annual report; Event support; Glossy publication
Project management tool | Platform to monitor planned and use of project efforts, distribution of budget, collection of costs, incl. EGI-Engage Bank fee
Subcontracting | Costs ICT Legal Consulting role of EGI.eu and EGI-Engage partners with regards to compliance to data protection law

## Slide 13: EC Final distribution
Over-spending vs. Under-spending:
Over-spending partners: -291,731
Under-spending partners: 258,548
Distribution allocation: The AMB and PMB have already made a thorough assessment per WP to determine partners’ major contribution. First and second priorities have been allocated to partners:
WP2: CSIC/CESGA; CERN; ENGINEERING; CNR; FAO WP3: NIKHEF; CESGA; CNRS’SRCE
WP4: ENGINEERING; UPVLC; CESGA; IIASA
WP6:NIKHEF; CSC; INFN (Lifewatch)
Early Nov, the PO will prepare the final distribution for PMB review. It will be submitted to the EC financial dept. after the costs acceptance.

## Slide 14: Timeline until the final payment
Oct 31, 2017: Submission of the Financial statements, CFS, Periodic and
      Final report
Early Nov: Project office prepares and circulates a “Report on the
distribution of the Community's contribution”.
    PMB decides whether a meeting is necessary to discuss the
    document or process to a vote via email.
In December: The EC revises partners’ Financial statements:
            When no cost are rejected the “Report on the distribution of the Community's contribution” can be sent to the EC as soon as the last payment is released (15%)
        When clarifications are requested and/or costs are rejected, the payment is on hold until clearance and the “Report on the distribution of the Community's contribution” will be updated as required.

## Slide 15: Use of resources
Notes: Freedom on way to present

## Slide 16: Effort report – WPs PY2
Summary of PM consumption PY2
- WP1: include efforts in Sept for the financial and periodic report preparation
Work Package | M13 – M30 |  | 
 | Planned | PM used | %
WP01 (NA1) Project Management | 47 | 52 | 112%
WP02 (NA2) Strategy, Policy and Communications | 129 | 134 | 104%
WP03 (JRA1) E-Infrastructure Commons | 91 | 120 | 131%
WP04 (JRA2) Platforms for the Data Commons | 99 | 126 | 127%
WP05 (SA1) Operations | 70 | 67 | 95%
WP06 (SA2) Knowledge Commons | 292 | 279 | 96%
Grand Total | 728 | 777 | 107%
Chart: 
| WP01 (NA1) | WP02 (NA2) | WP03 (JRA1) | WP04 (JRA2) | WP05 (SA1) | WP06 (SA2)
Planned | 47.84 | 127.75 | 89.51 | 99.25 | 70.12 | 290.18
PM used | 52.27 | 132.94 | 116.69 | 123.51 | 65.57 | 276.35

## Slide 17: Effort report – WPs all duration
Summary of PM consumption M1-M30
WP3: additional contribution not foreseen in DoA (operate RCAuth, Master portal dev. & production) WP4: additional contribution for cloudkeeper , Fedcloud, APPDB, cloud GPGPU
Work Package | M1 – M30 |  | 
 | Planned | PM used | %
WP01 (NA1) Project Management | 88 | 93 | 107%
WP02 (NA2) Strategy, Policy and Communications | 204 | 208 | 102%
WP03 (JRA1) E-Infrastructure Commons | 153 | 180 | 118%
WP04 (JRA2) Platforms for the Data Commons | 162 | 190 | 117%
WP05 (SA1) Operations | 106 | 102 | 97%
WP06 (SA2) Knowledge Commons | 455 | 428 | 94%
Grand Total | 1,168 | 1,202 | 103%
Chart: 
| WP01 (NA1) | WP02 (NA2) | WP03 (JRA1) | WP04 (JRA2) | WP05 (SA1) | WP06 (SA2) | Grand Total
Planned | 88.6 | 204.0037 | 153.0089 | 161.9966 | 105.5294 | 453.8981 | 1167.0367
Used Y1-Y2 | 93.33 | 207.5942 | 176.9911 | 187.6073 | 100.9794 | 425.487 | 1191.9891

## Slide 18: Effort report – Competence Centres
Summary of PM consumption M1-M30
- BBMRI: more efforts provided by BBMRI-NL and BBMRI-CZ (total of 7 PMs)
- EISCAT: efforts underspent mainly in P2 (58% of the plan)
- ASIAN CC: unfunded, not all efforts have been reported
Chart: WP6 (SA2) Tasks plan vs. used all duration
| SA2.3 ELIXIR | SA2.4 BBMRI | SA2.5 MoBrain | SA2.6 DARIAH-ERIC | SA2.7 LifeWatch | SA2.8 EISCAT_3D | SA2.9 EPOS | SA2.10 Asian Pacific | WP06 Total
Planned | 34.498 | 25 | 65.5019 | 62.5 | 60 | 28 | 30.4982 | 57 | 455.4981
Used Y1-Y2 | 36.36 | 32.43 | 64.54 | 68.02 | 68.3 | 19.19 | 29.67 | 18.35 | 428.45

## Slide 19: Achievements/Issues

## Slide 20: NA1 Activities & Achievements Deliverable and milestones
 | Delay [days] | # of Deliverables & Milestones
All work packages | 8 | 52
NA1 | 13 | 3
NA2 | - 42 | 9
JRA1 | 31 | 13
JRA2 | 12 | 6
SA1 | 13 | 4
SA2 | 22 | 17

## Slide 21: NA1 Activities & Achievements Risk management
Risk registry review:
  By the AMB and PMB
  5 times during the project life time (10.2015, 3.2016, 9.2016, 2.2017 and 8.2017)
Risks surviving project lifetime
  All risks related to EGI Governance have been tracked within the EGI IMS
  Last project risk registry review aimed to detect those risks
  Ownership of these risks to be reassigned to appropriate service owners.

## Slide 22: NA1 Activities & Achievements Risk management
Deprecated risks
  16 were marked as deprecated
  kept together with previously deprecated risks for:
    Future references
    Lessons learned for future projects
21 risks which are still valid after the end of the project
  12 are at low risk level
  4 are at medium risk level
  5 are at high risk level
  Initial ownership:
    2 owned by NA1
    4 owned by NA2
    3 owned by JRA1
    9 owned by JRA4
    3 owned by SA1

## Slide 23: NA1 Activities & Achievements IMS Quality control
Key Performance Indicators (KPIs) are collected and monitored
Regular review of the IMS is performed with:
  External certification audit by TÜV-SÜD auditor
  Internal audits performed by external expert
  Process reviews performed by process owner
  Management reviews performed by IMS owner (Top management)

## Slide 24: NA1 Activities & Achievements IMS Quality control
Name | Date | By | No. of findings
Internal FitSM/ISO20k Audit | 20/05/2016 | Thomas Schaaf | 21
Internal IMS audit / pre-audit | 20/09/2016 22/09/2016 | Thomas Schaaf | 40
Management review | 11/10/2016 | Yannick Legré | 8
External IMS certification audit ISO 9001 & ISO/IEC 20000-1 (stage 1) | 28/10/2016 | Marcus Giese (TÜV-SÜD) | 9
Management review | 12/12/2016 | Yannick Legré | 4
External IMS certification audit ISO 9001 & ISO/IEC 20000-1 (stage 2) | 21/12/2016 23/12/2016 | Marcus Giese (TÜV-SÜD) | 22
All process review | 05/2017 | Yannick Legré Tiziana Ferrari | Not available
Internal Audit - ITSM Processes | 30/06/2017 | Thomas Schaaf | 16
Management review | 27/07/2017 | Yannick Legré | 7

## Slide 25: NA1 Activities & Achievements Continuous Improvement
100 total suggestions for improvements formally submitted
  53 closed suggestions
    48 suggestions implemented
    5 not supported
  47 open suggestions

## Slide 26: NA1 Activities & Achievements General Data Protection Regulation (GDPR)
GDPR Compliance assessment
  High impact: 0
  Medium impact: 44
  Low impact: 7
  N/A: 4
Implementation as from January 2018
Objective: 01 May 2018