## Slide 1: WP4/JRA2 Development of EGI Technical Platforms
WP4 Leader
Matthew Viljoen

## Slide 2: Outline
WP Overview
  Objectives, tasks, partners and effort
Activities and Achievements
  Task JRA 2.1 Federated Open Data (Lead: Cyfronet)
  Task JRA 2.2 Federated Cloud (Lead: IFCA-CSIC)
  Task JRA 2.3 e-Infrastructure Integration (Lead: EGI)
  Task JRA 2.4 Accelerated Computing (Lead: SAVBA)
Resources and Issues
Summary

## Slide 3: JRA2 (WP4) objectives
Tasks | Project Objectives
TJRA2.1 Federated Open Data | Analysis of open data use cases and requirements Design and develop the Open Data platform prototype Open Data platform demonstrator
TJRA2.2 Federated Cloud | Evolve the federated IaaS Cloud platform with functionalities required by the CCs Extend ‘open standards’-based interfaces exposing new capabilities Maintain interface support for future versions of popular Cloud Management Frameworks (CMFs)
TJRA2.3 e-Infrastructure Integration | Integration for gCube and the D4Science infrastructure EGI-EUDAT Harmonisation for Virtual Research Environments Canadian Advanced Network for Astronomical Research
TJRA2.4 Accelerated Computing | Enabling accelerated computing support in the Information System Enabling accelerated computing support in the HTC and Cloud middleware frameworks

## Slide 4
Compute
Storage and Data
Training
Applications
Cloud Compute
High-Throughput
Compute
Archive Storage
Data Transfer
FitSM training
Training
infrastructure
Applications
on Demand
Online Storage
Alpha services
Attribute Management
Check-in
Configuration Database
Content Distribution
Data Hub
Federated Data Manager
Service Monitoring
Workload Manager
Cloud Container Compute BETA
JRA2.2
JRA2.4
JRA2.1
Notes: The bigger picture
JRA 2.1 – federated open data
JRA 2.2 – federated cloud
JRA 2.4 – HTC + Cloud accelerated computing
(no JRA 2.3 – e-Infrastructure Interoperatibility)
Addressing technological gaps – meeting user needs that isn’t met by EGI at present, mainly because technology isn’t there

## Slide 5: Activities and Achievements
Notes: Main achievements of the work package

## Slide 6: Task JRA2.1
Federated Open Data

## Slide 7: JRA2.1 Federated Open Data Aim
A new prototype platform (and services)
to enable the easy discovery, access and usage of reference open data and user data
Notes: =

## Slide 8: Community Requirements
REQ1. Publication of open research data based on policies
REQ2. Make large data sets available without transferring them completely
REQ3. Enabling complex metadata queries
REQ4. Integration of the open data access data management with community portals
REQ5. Data identification, linking and citation
REQ6. Enabling sharing of data between researchers under certain conditions
REQ7. Sharing and accessing data across federations
REQ8. Long term data preservation
REQ9. Data provenance
Use of external services (e.g. EUDAT)
Notes: at the beginning of the project, custom questionnaires were created and distributed to: Biological and Medical Sciences
    (Human Brain Project, MoBRAIN, BBMRI) Environmental and Earth Sciences(EMSO, LifeWatch)
  Agriculture(Agrodat.hu, agINFRA)Astronomy & Astrophysics (A&A)(CTA, LoFAR, CANFAR) – for results, see M4.1
  requirements summarized here.
  9 originally, we’ve concentrated on only 8 – no Long Term Preservation

## Slide 9: EGI Open Data Platform architecture
EGI User 1 (VO x)
Anonymous
User 1
EGI User 2
(Onedata space)
Anonymous
User 2
Space Manager
DOI Registrar (e.g. DataCite)
Community Portal
Open Data Platform
Web GUI
POSIX
HTTP
OAI-PMH
CDMI
REST
REST
EGI Site 1
EGI Site 2
EGI Site 3
Cloud storage
EUDAT
Space Manager
Open Data Manager
Metadata Registry
OAI-PMH Data
Provider
Authentication and Authorization
Long Term Retention
Notes: ODP is a solution for a a gateway to storage – it’s not duplicating anything.
Federated approach of accessing data. Complexity completely hidden from users, who only need to chose 1) the data they want and 2) how they want to access it
Top – users accessing the way they chose Say each in turn.
Openaire – service for discovering journals, datasets. Fed by a metadata protocol called OAIPMH Open Archives Initiative Protocol for Metadata Harvesting)
DOIs – Digital Object Identifiers. Allow citation of datasets
Bottom – disparate storage with plugins installed making them work with ODP.
Its implementation in this project is based on Onedata, developed by Cyfronet

## Slide 10: EGI Open Data Platform Interactions
Private Resources
Data–set-1
Snapshot
Data-set-1.1
Data-set-1.1
Mounted to
/localdir/
Cloned
Data-set-1.1
Private Resources
4: Visit Collection
Web Page (HTTP)
6: opendata fork DOI.1
3: discover data
-> DOI.1
5: opendata mount remote
DOI.1 /localdir/
1: opendata create
snapshot Data-set-1
Public Services
For Data Discovery
2: opendata publish
collection Data-set-1.1
-> DOI.1
Notes: An example of how users formation interact with the ODP
User has a dataset on a private resource
Snapshots the data (Makes the the data readonly) & publishes it. Gets a DOI
Another user discovers it, visits the collection via ODP and mounts it.
User may forks the collection by copying to own space & continues to work on it privately.

## Slide 11: EGI DataHub (https://datahub.egi.eu)
A single point of entry for Open Data sets managed on FedCloud
EGI DataHub provides access to reference scientific data of public interest
Provides integration with EGI AppDB service for automatic open data set computation
Notes: Not in the orig. DoA, but we decided it would be a useful output of this task.
A prototype EGI Data as a Service – EGI DataHub for federating open data

## Slide 12: EGI Federated Data Gateway
Means for exposing user data to computing
Enabling technology for storage to be exposed to users
Means for storage providers to easily expose storage to users/VOs
Notes: Also same tech allows fed data managing of user data and brining it to computing.

## Slide 13: Advanced metadata support
Metadata can be attached to resources (files, folders) in simple key-value form, JSON or RDF
Users can define custom indexes over the metadata in order to filter their data collections
Metadata can be used for Open Data collections when published
Notes: conforming to ANY schema deemed useful to users.
Annotations. Provenance. etc.
maybe Dublin Core schema.

## Slide 14: DOI registration
ODP supports Handle system-based identifier services (e.g. DOI and PID)
Any user can register such service, provided they have a valid account with the registrar
Each file or collection can be accessed directly using DOI identifier
Notes: Tested with the testing instance of DataCite, provider of DOIs.
Update layout (use different one to make sure you have no overlapping EGI logo

## Slide 15: OAI-PMH interface
ODP supports full OAI-PMH Data Provider protocol
By default ODP will expose all metadata of shares which have been made publicly available
Currently Dublin Core is supported for record metadata but can be extended in the future
Notes: OAI PMH (Open Archives Initiative Protocol for Metadata Harvesting) was developed as part of this task.
low level mechanism for exposing the records and content of a repository. Can be used for repo interoperability
demoed at DI4R – dataset created with metadata. Assigned DOI & metadata explosed through OAI-PMH

## Slide 16: Onedatify – legacy data access
Open Data Platform enables seamless exposing of existing datasets directly from legacy storage
Easy to use script automatically installs and configures Oneprovider service, and connects it to EGI DataHub
Notes: e.g. for PanCancer 60TB indexed and made available for EGI DataHub
Developed as part of Engage

## Slide 17: Preparation for production and the future
Integration with EGI monitoring infrastructure
Usecases successfully completed advanced testing of Onedata (Earth Observation PoC)
Independent audit of documentation and security within INDIGO-DataCloud
Completed INDIGO Staged Rollout, will be added to the EGI repositories
  EGI ODP/Onedata will be further developed as part of:
XDC, Xtreme Data Cloud (from Nov ’17)
EOSC-hub (from Jan ‘18)

## Slide 18: Task JRA2.2
Federated Cloud

## Slide 19: JRA2.2 Federated Cloud Aim
Improve user experience
Develop new required functionality
Develop improved tools
Promoting EGI Federated Cloud adoption
Notes: Improve user experience
AppDB VMops Dashboard
Develop new required functionality
  VM snapshotting, resource modification
Develop improved tools
  Cloudkeeper, cloud-info-provider, AAI in OpenStack

## Slide 20: AppDB VMOps Dashboard
Web interface to deploy different topologies in the EGI Federated Cloud
  Based on the VMIs registered in the AppDB
  Control of the complete topology life-cycle
Infrastructure Manager (IM) as a backend
http://go.egi.eu/indigodemo - for a demo from EGI/INDIGO-DataCloud, from 1:32 to 3:39
Notes: Very significant output of this task – completely new way of GUI-only way of interacting with the FedCloud
been used in FedCloud trainings
and from new users (e.g. from EOSCpilot) – good feedback

## Slide 21: OCCI Improvements
Development and inclusion of VM snapshotting and VM resize support into new OCCI 1.2 standard
  Requested by EGI user communities
New implementation: OOI
  Initially targeted to OpenStack
  New architecture to ensure compatibility across CMF releases
  Now adopted by Synnefo (same codebase)
OCCI 1.2 support implemented in OOI and rOCCI
Notes: HIGHLIGHTS of development…
OCCI is the Open Cloud Computing Interface
a low level protocol and API for VM management tasks, independent of cloud management implementations (e.g. OS, ON)
enables interop. of tools: e.g. for deployment, scaling, monitoring

## Slide 22: VM Image synchronization tools
VM Image synchronization
  availability, propagation of updates/bugfixes
New product developed: CloudKeeper
  New design and architecture
  Decoupled different actions in separated components: VMI download, transformation, upload
  One single tool performing CMF-agnostic actions, per-CMF plugins to upload images
Agreement on new metadata published at the AppDB and propagated via CloudKeeper

## Slide 23: Information System
Refactored to use a template language and engine
  Same tool with different renderings
e.g. JSON rendering for INDIGO-DataCloud
Complete GLUE 2.1 draft into cloud-info-provider
  Comments sent to OGF GLUE-WG
    Approval of standard by end of year (expected)

## Slide 24: Task JRA2.3
e-Infrastructures Integration

## Slide 25: JRA2.3 e-Infrastructures Integration Aim
Improved service to users, regardless of their e-Infrastructure
Enabling of cross e-Infrastructure technical interoperability
Future proofing via alignment of standards
In scope: EGI-EUDAT, iMarine/D4Science, CANFAR

## Slide 26: EGI-EUDAT integration use cases
First use case ‘universal’ use case:
  VM instantiated on the EGI cloud federation for the interacting with EUDAT resources (B2STAGE, B2SAFE)
Requirement driven use cases:
  Call for cross-infrastructure case-studies in PM15 for driving developments selected ICOS and EPOS use cases
  ENES use case started on May 2017 after contacts during EGI Conference
  Building on the universal use

## Slide 27: gCube/D4Science integration
D4Science FedCloud Connector
  Relies on jOCCI SDK
  Using EGI VOMS authentication
  VA on AppDB
Able to spawn VMs on demand to execute computational models
Notes: d4science is a generic virtual research environment providing common services to ranges of earth scientists: computing, data
Bult on gCube open source sw

## Slide 28: gCube/D4Science exploitation
SLA establishment (Nov 2016)
  5 resource providers (CESGA, GeoGrid, IISAS, INFN-BARI, UPV-GRyCAP)
Testing of the integration (Nov 2016 – Apr 2017)
  Solved issues with networking configuration
  Tested reliability and availability of sites
Production (since May 2017)
  Users of the VREs now using EGI Federated Cloud as a platform for the execution of their models
Notes: now requesting more resources that we are in discussions about

## Slide 29: CANFAR interoperability
CANFAR – Canadian Advanced Network for Astronomy Research
Work to enable European astronomers to access and exploit CANFAR data via the EGI FedCloud
CANFAR software stack modified and deployed at INAF-OAT, usable by FedCloud users
Notes: CANFAR is the Canadian Advanced Network for Astronomy Research, a community platform for astronomy based on IVOA standards running on Compute Canada resources
Offers data access to astronomical data (archives and catalogues), Access control (GMS), user storage (VOSpace), cloud processing integrated with telescope data collections (OpenStack)
In 2014, > 7,000 users, > 1 PiB of data handled

## Slide 30: CANFAR interoperability - ongoing work
Full EGI Check-in - CADC Access Control components (X509 currently used)
Improving data movement between infrastructures
Better user and developer guides

## Slide 31: Task JRA2.4
Accelerated Computing

## Slide 32: JRA2.4 Accelerated Computing Aim
Making GPGPUs available through EGI services and facilitating their use
Notes: Accelerated Computing – a way to utilize energy efficient and powerful High Performance Computing capabilities
GPGPU – General Purpose Graphics Processing Unit, originally developed for better graphics rendering (by offloading processing from the CPU to the graphics card) thanks to the demands of the gaming industry
Now very prevalent and a cost effective means of increasing processing power in hardware.
2 parts to this work – enabling GPGPUs for High Through Computing, HTC and GPGPUs for Cloud, we’ll deal with them separately here.

## Slide 33: Accelerated computing in HTC
Starting from previous work of EGI Virtual Team (2012) and GPGPU Working Group (2013-2014)
CREAM-CE is the most popular grid interface (Computing Element) to a number of LRMSes (Torque, LSF, Slurm, SGE, HTCondor)
Most recent versions of these LRMSes do support natively GPUs (and MIC cards), i.e. servers hosting these cards can be selected by specifying LRMS directives
CREAM must be enabled to publish this information and support these
Notes: Local Resource Mgmnt Systems (LRMS)

## Slide 34: Work done
Identified the relevant GPU related parameters supported by the different LRMSes, and abstracted them to significant JDL attributes
Implemented the needed changes in CREAM Core and BLAH components
Extended the GLUE 2.1 schema draft with accelerator information
Wrote the info-providers according to extended GLUE 2.1 draft specifications
Testing and certification of the prototype
Releasing a CREAM update with full GPU/MIC support
Notes: MICs – Many Integrated Cores, a new arch from Intel
BLAH (Batch Local Ascii Helper) – protocol to manage jobs on different Local Resource Mgmnt Systems (LRMS)
a minimal interface for job submission

## Slide 35: Summary
  The CREAM GPU-enabled prototype was tested at 5 sites
  LRMSes: Torque, LSF, HTCondor, Slurm, and SGE LRMSes
  3 new JDL attributes defined: GPUNumber, GPUModel, MICNumber
  At 3 sites the prototype is run in “production”: QMUL and ARNES (Slurm) and CIRMMP (Torque/Maui)
  New classes and attributes describing accelerators proposed and included in GLUE2.1 draft after discussion with the OGF WG
A major release of CREAM is ready
  with GPU/MIC support for most LRMSes
  with the GLUE2.1 draft prototype as information system
    future official approval of GLUE 2.1 would occur after the specification is revised based on prototype lessons learned
  with new Puppet module for the CE site with support for GPU/MIC and GLUE 2.1
  its CentOS7 version will be included in the next UMD 4.6.0 scheduled at mid November 2017
Notes: CIRMMP is fully dedicated to MoBrain/WeNMR/West-Life community (i.e. structural biology) via the enmr.eu VO, see also the full reports in EGI_Engage deliverables D6.7 (CIRMMP - metalloproteins and metalloenzymes research)
At QMUL their main user is icecube, they do simulations. (IceCube Neutrino Observatory, Antarctica)

## Slide 36: Accelerated computing in Cloud
For using GPGPU in clouds, the GPGPU must be supported in all layers including virtualization, CMF and higher tools
Virtualization technologies used:
  KVM with PCI passthrough
    Widely used but with limitations
  Container-based technologies
    LXD with GPU is promising
    But limited support in cloud middleware
Notes: Rather than software development, this task is mainly:
advanced config of Cloud Mgmnt Frameworks
testing/benhmarking
documentation & ease of deployment
has led to GGPU enabled FedCloud sites in prod.
LXD - pure-container hypervisor – an advanced system container manager that uses containers rather than VMs. LOWER OVERHEAD

## Slide 37: IISAS-GPUCloud site
Openstack GPGPU site at IISAS
Site is integrated into EGI Federated Cloud and in production
Access via command line or via the Openstack Horizon portal

## Slide 38: Information system
GLUE 2.1 as starting point for Accelerator-aware info provider
For HTC:
  New GLUE object, the Accelerator Environment, representing a set of homogeneous accelerator devices.
  New attributes and associations for existing objects such as Computing Manager, Computing Share and Execution Environment.
For Cloud: Cloud Compute Virtual Accelerator
  New entity, the Cloud Compute Virtual Accelerator
  New attributes and associations for existing objects such as Cloud Compute Service
Notes: other work related to GPGPU includes other services req for integration into the eInfra:
INFO SYSTEM – included in automatic discovery of resources

## Slide 39: Accounting
For clouds, extended accounting records with new items for describing accelerators:
  AcceleratorCount,
  AcceleratorProcessors,
  AcceleratorDuration,
  AcceleratorWallDuration,
  AcceleratorBenchmarkType,
  AcceleratorBenchmark,
  AcceleratorType
Modification of accounting tools for supporting new accelerator-related items

## Slide 40: Docker support
For easy exploitation of accelerated computing
  Chose a site with GPGPUs
  Bring up a VM with a GPGPU-enabled flavour
  Run docker
  $>docker run --name=XXXXXX \
  --device=/dev/nvidia0:/dev/nvidia0 \
  --device=/dev/nvidia1:/dev/nvidia1 \
  --device=/dev/nvidiactl:/dev/nvidiactl \
  --device=/dev/nvidia-uvm:/dev/nvidia-uvm.
  Works with udocker from INDIGO-Datacloud (used in production by MoBrain CC)
Notes: for ease of usage.

## Slide 41: Use of Resources and Issues
Notes: Numbers will be provided by PO, work package leaders must provide explanation

## Slide 42: Resource usage across WP
Moderate overspend in 3 tasks
Reasons:
  Software development unforseen in DoA
  Extra work unforseen in DoA (ODP services)
Task | Planned PM | Reported PM | Deviation
JRA2.1 | 45 | 56 | 125%
JRA2.2 | 63 | 77 | 122%
JRA2.3 | 35 | 38 | 108%
JRA2.4 | 19 | 19 | 100%
JRA2 | 162 | 190 | 117%

## Slide 43: Primary overspending partners
Task | Partner | Planned | Reported |  | % | Reason |  | 
JRA2.1 | Agro-Know | 3 | 10.8 | +7.8 | 360% | Additional work done validating their testcase at the beginning of the project. |  | 
JRA2.2 | CSIC | 5.5 | 10.1 | +4.6 | 183% | Mistaken reporting of work that was actually done in WP6 and JRA2.3 |  | 
JRA2.2 | CESNET | 25 | 28.3 | +3.3 | 113% | Cloudkeeper work that was unforseen |  | 
JRA2.2 | CESGA | 5 | 8 | +3.3 | 160% | VM image maintenance for local storage management |  | 
JRA2.1 | UPVLC | 1 | 3.5 | +2.5 | 349% | Additional work done validating their testcase at the beginning of the project. |  | 
JRA2.1 | CYFRONET | 36 | 38.5 | +2.5 | 107% | EGI DataHub setup and maintenance. Testing and supporting EOPoC. Not in DoA |  | 
JRA2.2 | UPVLC | 6 | 8.1 | +2.1 | 134% | Unforseen work done with the IM in the context of the AppDB VMOps dashboard |  | 

## Slide 44: Summary
Notes: Freedom on way to present

## Slide 45: Summary
Objective 3 (O3): Offer and expand an e-Infrastructure Commons solution
  Introduction of an Open Data Platform
  Improve integration of FedCloud by developing improvements of different Cloud Middleware Frameworks
  Integration with partner e-Infrastructures in Europe and worldwide
Objective 4 (O4): Open data platform and the European Big Data Value.
  Prototype of EGI DataHub for sharing open data
  Prototype of EGI Federated Data Gateway for federating user data
  Tools for data publishing and importing of existing data
Objective 5 (O5): Promotion the adoption and extension of the current EGI services
  Enhancement of OCCI with new extensions (snapshots of running VM and changing resources of running VMs)
  Development of the AppDB VMOps Dashboard
  Accelerated computing capability brought to production on the Fedcloud and a production ready prototype CREAM now ready for HTC
Notes: Achievements grouped by objectives

## Slide 46: Key exploitable results
KER name | Description
Software and services | 
Tools for federated service management | Technological innovation and new services in the area of Service Registry and Marketplace and resource allocation. Evolved EGI accounting system. Adapted operations tools to new technologies and to satisfy new requirements from service providers and user communities.
Open Data Platform | A platform designed to make data discoverable and available in an easy way across all EGI federated resources
Improved Federated Cloud Computing | Improved EGI federated Cloud platform with new IaaS capabilities; Integrated existing commercial and public IaaS Cloud deployments and e-Infrastructures with the current EGI production infrastructures
Notes: All KERs have been met.
Adapted operations tools to new technologies and to satisfy new requirements from service providers and user communities. – ODP, cloudkeeper, appdb vmops dashboard, occi (but isn’t this already covered by WP3???)