## Slide 1: Deliverables to PM12 (PQ4)
TIMETABLE | DOCUMENTS
PM 10 (February 2011) ToC due: 17 January First draft: 1 February Deadline: 28 February | D2.7 EGI Sustainability Plan
PM 11 (March 2011) ToC due: 17 February First draft: 1 March Deadline: 31 March | D1.3 Annual Report on Quality Status D2.8 Annual Report on EGI and its External Relations activity D3.2 Annual Report on EGI's User Community Services D4.2 Annual Report on the EGI Production Infrastructure D5.3 Annual Report on the status of Software Provisioning activity and the work of DMSU D6.3 Annual Report on the HUC Tools and Services D7.1 Annual Report on Operational Tool maintenance and development activity
PM 12 (April 2011) ToC due: 17 March First draft: 1 April Deadline: 30 April | D1.4 Annual Project Report

## Slide 2: Deliverables to PM15 (PQ5)
TIMETABLE | DOCUMENTS
PM 13 (May 2011) ToC due: 17 April First draft: 1 May Deadline: 31 May | D1.5 Quality Plan and Project Metrics D2.9 Dissemination Plan D2.10 EGI-InSPIRE Presentation
PM 14 (June 2011) ToC due: 17 May First draft: 1 June Deadline: 30 June | 
PM 15 (July 2011) ToC due: 17 June First draft: 1 July Deadline: 31 July | D3.3 User Community Support Process D5.4 UMD Roadmap

## Slide 3: Milestones to PM12 (PQ4)
TIMETABLE | DOCUMENTS
PM 10 (February 2011) ToC due: 17 January First draft: 1 February Deadline: 28 February | MS108 Global Task Review MS109 NGI International Task Review MS110 Work of the Asia Pacific Region – delayed to PM12 MS214 Security Activity within EGI MS606 HUC Software Roadmap
PM 11 (March 2011) ToC due: 17 February First draft: 1 March Deadline: 31 March | 
PM 12 (April 2011) ToC due: 17 March First draft: 1 April Deadline: 30 April | MS215 EGI Newsletter MS216 EGI User Forum MS607 Hydra service deployment on a multi-servers configuration MS608 Integration of the VisIVO server with the production infrastructure

## Slide 4: Milestones to PM15 (PQ5)
TIMETABLE | DOCUMENTS
PM 13 (May 2011) ToC due: 17 April First draft: 1 May Deadline: 31 May | MS506 EGI Software Repository –Architecture and Plans MS609 HUC Contact Points and the Support Model MS705 CIC Operations Portal Work Plan MS706 Operational Tools Accounting Work Plan
PM 14 (June 2011) ToC due: 17 May First draft: 1 June Deadline: 30 June | MS217 Dissemination Handbook MS306 User Support Contacts MS409 Deploying software into the EGI Production Infrastructure MS410 EGI Helpdesk and the NGI Support Units MS411 Operational Level Agreements within the EGI Production Infrastructure MS507 Deployed Middleware Support Unit Operations Procedures MS508 Software Provisioning Process MS707 Roadmap for the Maintenance and Development of the Deployed Operational Tools
PM 15 (July 2011) ToC due: 17 June First draft: 1 July Deadline: 31 July | MS112 Quarterly Report MS218 EGI Newsletter MS219 Establishing the External Relations Area of the Website MS307 User Support Metrics MS412 Operational Security Procedures MS610 Services for High Energy Physics MS611 Services for the Life Science Community