## Slide 1: Session 2
WP8 Competence Centres – Kickoff meeting
Gergely Sipos
EGI Foundation
Gergely.sipos@egi.eu

## Slide 2: Collaborative tools (Based on Pre-AMB meeting – Dec 20.)
EOSC-hub Confluence space:
  https://wiki.eosc-hub.eu/display/EOSC/WP8+Competance+Centres
Indico  Meeting agendas and materials:
  https://indico.egi.eu/indico/category/211/  WP8 or task meetings
Mailing lists (in preparation):
  WP8 mailing lists to be setup  Task leaders and deputies
  Task email lists to be setup  Please send me a list of emails you want to have on your list
Google drive shared folder (in preparation)
Some tools are provisional offered under the EGI.eu domain
  Switch to the EOSC-hub domain foreseen in January
Teleconference tool?

## Slide 3: Expected Output from WP8 kickoff meeting (1/2)
WP Work plan
  Detailed 12 month work plan specifying distribution of activities by task
    To be approved by end of Jan 2018
Key Exploitable Results
  6 is already in the DoA. ICOS and DMCC+ are missing
  Details to be collected (as soon as the template is defined)
Define WP regular meetings
  CC kickoff meetings
  CC task-level meetings – Monthly?
  CC task leaders’ meeting – Needed?
  F2f meetings
    At RI forums
    At EOSC-hub forums (2/year)

## Slide 4: WP Work Plan – Table per task
Activity identifier | Task Name | Start date (mm/yy) | End date (mm/yy) | Status | Dependencies | Issues
10.3.1 | Description 1 | 01/18 | 03/18 | Done |  | 
10.3.2 | Description 2 | 02/18 | 05/18 | Ongoing |  | 
… |  |  |  | Planned |  | 
10.3.N | Description N |  |  | Planned | 10.3.1 | 
Activity identifier: task number + incremental id
Task Name: short description
Status: Planned/Ongoing/Done
Dependencies: list of activity identifiers
A tool to record the WP Work Plans will be provided soon
Activity identifier | Task Name | Start date (mm/yy) | End date (mm/yy) | Status | Dependencies | Issues
10.3.1 | Description 1 | 01/18 | 03/18 | Done |  | 
10.3.2 | Description 2 | 02/18 | 07/18 | Ongoing |  | 
… |  |  |  | Planned |  | 
10.3.N | Description N |  |  | Planned | 10.3.1 | 

## Slide 5: Expected Output from WP8 kickoff meeting (2/2)
Preliminary quality metrics
  Final target is defining 5 quality metrics per WP
    Some examples
      Number of scientific publications supported
      Number of entries in the service catalogue
      Amount of VMs instantiated
      Number of users per thematic service
      Number of training modules produced and kept up-to
EOSC-hub/OpenAIRE Advance collaboration
  Assessment and impact on the WP work plan
Inputs for AMB meetings
  Short, written input from each CC. Details TBD
  Monthly frequency (TBC)

## Slide 6: Training and technical support
Series of webinars?
F2F workshop? Hackathon?
  EOSC-hub all-hands (April-May) – too late?
Invite Service experts to CC meetings?
‘Interest groups’? – E.g. Jupyter; Containers

## Slide 7: Compute & storage
Demo/pilot scale capacity should be already budgeted in your CC (!)
Many of the common services have catch-all instances for ‘new communities’
Production scale operation with VA in WP13:
  Marine, EISCAT_3D (M19)
For others:
  OLA negotiation (with providers) within and beyond the project
  SLA towards users for the ‘whole stack’

## Slide 8
OpenAIRE-Advance – EOSC-hub
Research
data
Research
Software
e-infra Tools &
Services
Research
data
Scientific process
Research literature:
Articles, docs, white papers
01101010
01100001
11010010
01101010
01100001
11010010
Research Infrastructures
Publishing packages of products to enable reproducibility
Publishing an up-to-date record of research products metadata and links
Publishing of all kinds of research products and semantic links in between
Enabling transparent
evaluation
Enabling reproducibility
Long-tail users
Open Science
Access and Publishing
Support to create and operate own infrastructure
Catch-all infrastructure
Open Science
Access and Publishing
Discover re-usable objects
Zenodo
Applications on demand
B2SHARE
Setup and execute custom analysis
EOSC-hub/OpenAIRE Advance collaboration

## Slide 9
Some example driver use cases
Researchers depositing publications in OpenAIRE should be able to include references to datasets and application services stored in EOSC-hub.
Researchers should be able to import datasets from OpenAIRE (Zenodo) into EOSC-hub compute and application service to carry out data analysis.
Researchers should be able to export analysis result data from EOSC-hub compute and application services to OpenAIRE (Zenodo) to share these data with broader audiences.
User communities should be able to collect and visualise research impact data about the use of their community data and application services that are part of EOSC-hub.